{"text_format":"3","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"defined_names":3},"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":197,"n_cols":30,"rows_kept":197,"merged":[[0,0,0,26],[2,0,2,26],[4,0,6,0],[4,1,4,3],[4,4,6,4],[4,5,6,5],[4,6,6,6],[4,7,6,7],[4,8,6,8],[4,9,4,10],[4,11,6,11],[4,12,6,12],[4,13,4,17],[4,18,4,23],[4,24,6,24],[4,25,6,25],[4,26,6,26],[5,1,6,1],[5,2,6,2],[5,3,6,3],[5,9,6,9],[5,10,6,10],[5,13,6,13],[5,14,5,17],[5,18,6,18],[5,19,6,19],[5,20,6,20],[5,21,5,23]]}
["沅江市2022年度巩固拓展脱贫攻坚成果和乡村振兴项目库动态调整项目申报表"]
[]
["单位：（盖章）                                                                                                                                                                                              时间：20XX年X月X日"]
[]
["序号","项目类别",null,null,"乡","村","项目名称","建设性质","实施地点","时间进度",null,"责任单位","建设内容及规模","资金规模和筹资方式",{"$nulls":4},"受益对象",{"$nulls":5},"绩效目标","联农带农机制","备注"]
[null,"项目类型","二级项目类型","项目子类型",{"$nulls":5},"计划开工时间","计划完工时间",null,null,"项目预算总投资（万元）","其中",{"$nulls":3},"受益村数（个）","受益户数（户）","受益人口数（人）","其中"]
[{"$nulls":14},"财政衔接资金（万元）","除财政衔接资金外的统筹整资金（万元）","其他财政资金（万元）","其他筹措资金（万元）",{"$nulls":3},"受益脱贫村数（个）","受益脱贫户数及防止返贫监测对象户数（户）","受益脱贫人口数及防止返贫监测对象人口数（人）"]
[1,"产业发展","配套设施项目","配套设施项目","琼湖街道","九只树村","九只树村产业配套项目","新建","九只树村","2022-08-01","2022-12-01","九只树村","村庄产业配套建设",{"$f":"O8+P8+Q8+R8","v":80},80,null,null,0,1,56,129,1,54,110,"完成建设规划内容","通过产业分红和用工用劳",null,"中央第二批沅振发〔2022〕5号",80,"沅财农指〔2022〕8号"]
[2,"乡村建设行动","农村基础设施","公路建设","琼湖街道","保民村","保民村通组道路建设","新建","保民村","2022-08-01","2022-12-01","保民村","新建道路3.5公里",{"$f":"O9+P9+Q9+R9","v":40},40,null,null,0,1,108,272,1,18,31,"完成既定目标","方便群众出行",null,"省第二批沅振发〔2022〕9号",40,"沅财农指〔2022〕13号"]
[3,"乡村建设行动","农村基础设施","小型农田水利设施","琼湖街道","澎湖村","琼湖街道2022年澎湖村整修沟渠项目","新建","澎湖村","2022-08-01","2022-12-01","澎湖村","整修沟渠",5,5,null,null,0,1,19,51,1,19,51,"完成既定目标","提高群众生活水平",null,285,5,"沅财农指〔2022〕21号"]
[4,"乡村建设行动","农村基础设施","小型农田水利设施","琼湖街道","保民村","琼湖街道2022年保民村水利设施管道维护","新建","保民村","2022-08-01","2022-12-01","保民村","水利设施管道维护",10,10,null,null,0,1,99,251,1,99,251,"完成既定目标","提高群众生活水平",null,"县级",10,"沅财农指〔2022〕22号"]
[1,"乡村建设行动","农村基础设施","农村道路建设","胭脂湖街道","永建村","永建村道路附属基础设施建设","新建","永建村","2022-06-01","2022-08-01","乡村振兴局","道路路基拓宽及挡土墙建设",{"$f":"O12+P12+Q12+R12","v":6},6,null,null,0,1,163,783,0,45,122,"项目（工程）验收合格率100%","①提高群众生产生活水平\n②便利群众出行",null,"中央第二批沅振发〔2022〕5号",6,"沅财农指〔2022〕8号"]
[2,"乡村建设行动","农村基础设施","农村道路建设","胭脂湖街道","胭脂湖村","胭脂湖村道路拓宽及配套基础设计建设","扩建","胭脂湖村","2022-06-01","2022-08-01","乡村振兴局","道路拓宽2米共700米左右",10,10,null,null,0,1,128,650,0,60,151,"项目（工程）验收合格率100%","①提高群众生产生活水平\n②便利群众出行",null,"中央第二批沅振发〔2022〕5号",10,"沅财农指〔2022〕8号"]
[3,"产业发展","生产项目","种植业基地","胭脂湖街道","杨梅山村","杨梅姑娘果蔬合作社","新建","杨梅山村","2022-06-01","2022-08-01","乡村振兴局","休闲亭三座，果蔬长廊一座，体验式餐厅100平方米，亲子园200平方米",20,20,null,null,0,1,2204,6589,1,4,12,"促进农业经济发展，带动农户增收增产，公司积极发展生产，开拓市场，指导农户参与分享收益，带动乡村振兴和周边农民脱贫致富增收","1、带动地方产业发展\n2、新增就业岗位",null,"中央第二批沅振发〔2022〕5号",20,"沅财农指〔2022〕8号"]
[4,"产业发展","生产项目","养殖业基地","胭脂湖街道","南竹山村","初聚种养合作社","新建","南竹山村","2022-06-01","2022-08-01","乡村振兴局","莲藕大头鱼产业项目",20,20,null,null,0,1,163,452,0,15,32,"促进农业经济发展，带动农户增收增产，公司积极发展生产，开拓市场，指导农户参与分享收益，带动乡村振兴和周边农民脱贫致富增收","1、带动地方产业发展\n2、新增就业岗位",null,"中央第二批沅振发〔2022〕5号",20,"沅财农指〔2022〕8号"]
[5,"产业发展项目","配套基础设施项目","小型农田水利设施建设","胭脂湖街道","南竹山村","渠道新建硬化","新建","南竹山村","2022-08-01","2022-09-01","乡村振兴局","900米",30,30,null,null,0,1,160,400,0,10,15,"促进农业经济发展，带动农户增收增产，公司积极发展生产，开拓市场，指导农户参与分享收益，带动乡村振兴和周边农民脱贫致富增收","1、解决积水，使农田增产增收\n2、带动务工就业",null,"省第二批沅振发〔2022〕9号",30,"沅财农指〔2022〕13号"]
[6,"产业发展项目","配套基础设施项目","小型农田水利设施建设","胭脂湖街道","三眼塘村","三眼塘村后里冲塘\n山塘清淤","维修","三眼塘村1组","2022-09-01","2022年10月","乡村振兴局","后里冲塘清淤清运土方\n3300方",5,5,0,0,0,1,74,206,0,18,45,"项目（工程）验收合格率100%","提高群众生产生活水平，便利农业用水灌溉，提高群众满意度",null,285,5,"沅财农指〔2022〕21号"]
[7,"乡村建设行动","农村基础设施","农村道路建设","胭脂湖街道","赤塘村","11组挡土墙","新建","赤塘村12组","2022-06-01","2022-08-01","赤塘村","挡土墙新建156.24m³",10,10,0,0,0,1,56,143,0,56,113,"项目（工程）验收合格率100%","方便群众出行，便于农业生产，为群众增收",null,285,10,"沅财农指〔2022〕21号"]
[8,"产业发展","生产项目","种植业基地","胭脂湖街道","南竹山村","大山岭产业园产业发展","新建","南竹山村","2022-01-01","2022-11-01","南竹山村","48亩",30,30,0,0,0,1,163,452,0,18,37,"促进农业经济发展，带动农户增收增产，公司积极发展生产，开拓市场，指导农户参与分享收益，带动乡村振兴和周边农民脱贫致富增收","1、带动地方产业发展\n2、新增就业岗位3、打造红色观光产业园",null,285,30,"沅财农指〔2022〕21号"]
[1,"产业发展","配套基础","产业园","新湾镇","桥北村","桥北村经济合作社-橘柚示范园","产业发展","桥北村东风组","2022-06-01","2022-10-01","乡村振兴局","桥北村橘柚示范园蓄水池建设及土地平整",20,20,null,null,0,1,1220,2978,0,41,101,"项目带动脱贫人口直接受益102人","①提高群众生产生活水平 ②增加集体经济收入③带动脱贫户41户102人发展后续帮扶产业",null,"中央第二批沅振发〔2022〕5号",20,"沅财农指〔2022〕8号"]
[2,"乡村建设行动","农村基础设施","农村道路建设","新湾镇","桥北村","桥北村广花组、郭家组拓宽公路硬化","基础设施","桥北村广花组、郭家组","2022-08-01","2022-10-01","乡村振兴局","桥北村广花组、郭家组拓宽了2.5米路基的800米长路段进行硬化",{"$f":"O21+P21+Q21+R21","v":30},30,null,null,0,1,143,353,0,5,13,"项目带动脱贫人口直接受益13人","①提高群众生产生活水平②解决脱贫户5户13人的出行安全及发展经济问题",null,"省第二批沅振发〔2022〕9号",30,"沅财农指〔2022〕13号"]
[3,"乡村建设","农村基础设施","农村道路建设","新湾镇","桥北村","桥北村广花组、枫树组道路拓宽路基建设","基础设施","桥北村广花组、枫树组","2022-08-01","2022-10-01","乡村振兴局","桥北村广花组、枫树组800米路段道路拓宽2.5米（含两边各0.5米绿化带）路基建设",10,10,null,null,0,1,146,365,0,2,7,"项目带动脱贫人口直接受益7人","①提高群众生产生活水平②解决脱贫户2户7人的出行安全及发展经济问题",null,"省第二批沅振发〔2022〕9号",10,"沅财农指〔2022〕14号"]
[4,"乡村建设行动","农村基础设施","农村道路建设","新湾镇","杨阁老村","杨阁老村何家组道路200米拓宽","基础设施建设","杨阁老村何家组","2022-08-20","2022-10-01","乡村振兴局","何家组道路约拓宽200米",10,10,null,null,0,1,110,320,0,4,11,"项目带动脱贫人口直接受益13人","①提高群众生产生活水平②解决脱贫户4户11人的出行安全及发展经济问题",null,"省第二批沅振发〔2022〕9号",10,"沅财农指〔2022〕13号"]
[5,"乡村建设行动","农村基础设施","农村道路建设","新湾镇","莲花村","新湾镇莲花村罗家组公路硬化项目","基础设施建设","莲花村罗家组","2022-10-01","2022-12-01","乡村振兴局","罗家组道路硬化250米",10,10,null,null,0,1,52,210,0,4,12,"项目带动脱贫人口直接受益12人","提高群众生产生活水平，解决脱贫户4户12人道路出行问题",null,"省第二批沅振发〔2022〕9号",10,"沅财农指〔2022〕13号"]
[6,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","新湾镇","老屋冲村","新湾镇老屋冲村大冲片区公路硬化项目","新建","老屋冲村大冲村","2022-09-01","2022-10-01","老屋冲村","公路硬化850米",38,38,null,null,0,1,182,402,0,10,24,"项目带动脱贫人口直接受益24人","1、提高群众生产生活水平。2.解决脱贫户16户40人的出行安全及发展经济问题",null,"县级",38,"沅财农指〔2022〕23号"]
[7,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","新湾镇","老屋冲村","新湾镇老屋冲村兰花片区公路硬化项目","新建","老屋冲村兰花村","2022-09-01","2022-10-01","老屋冲村","公路硬化750米",32,32,null,null,0,1,126,296,0,8,20,"项目带动脱贫人口直接受益20人","1、提高群众生产生活水平。2.解决脱贫户16户40人的出行安全及发展经济问题",null,"县级",32,"沅财农指〔2022〕23号"]
[8,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","新湾镇","老屋冲村","新湾镇老屋冲村-基础设施-关王组到桂枝园组公路硬化项目","新建","老屋冲村","2022-10-01","2022-11-01","老屋冲村","公路硬化150米",7,7,null,null,0,1,104,270,0,3,6,"项目带动脱贫人口直接受益6人","1、提高群众生产生活水平。2.解决脱贫户3户6人的出行安全及发展经济问题",null,285,7,"沅财农指〔2022〕21号"]
[9,"乡村建设行动","农村基础设施","农村道路建设","新湾镇","周公湖村","周公湖村烂泥组（学海路）公路硬化项目","基础设施建设","周公湖村烂泥组","2022-11-01","2022-12-01","周公湖村","烂泥组道路\n硬化长180米、宽3米",6,6,null,null,0,1,12,43,0,3,6,"项目带动脱贫人口直接受益6人","①提高群众生产生活水平②解决脱贫户3户6人的出行安全及发展经济问题",null,285,6,"沅财农指〔2022〕21号"]
[10,"产业发展","配套基础","产业园","新湾镇","新湾村","新湾村产业发展柑橘品改基地水利配套（喷滴灌）建设项目","产业发展","新湾村张家村组、东兴组","2022-10-01","2022-12-01","新湾村","新湾村张家村组、东兴组70亩喷滴灌安装",10,10,null,null,0,1,76,190,1,7,13,"项目带动脱贫人口直接受益13人","①农户通过土地流转，增加了群众经济收入②带动了当地的产业发展，解决了群众的就业",null,285,10,"沅财农指〔2022〕21号"]
[11,"乡村建设行动","农村基础设施","农村道路建设","新湾镇","莲花村","新湾镇莲花村罗家组至横冲组公里硬化项目","基础设施建设","莲花村罗家组-横冲组","2022-10-01","2022-12-01","莲花村","罗家组-横冲组道路硬化125米",5,5,null,null,0,1,45,180,0,2,7,"项目带动脱贫人口直接受益7人","提高群众生产生活水平，解决脱贫户2户7人道路出行问题",null,285,5,"沅财农指〔2022〕21号"]
[12,"乡村建设行动","农村基础设施","农村道路建设","新湾镇","莲花村","新湾镇莲花村朱雀组公路硬化项目","基础设施建设","莲花村朱雀组","2022-10-01","2022-12-01","莲花村","朱雀组道路硬化750米",30,30,null,null,0,1,56,208,0,5,15,"项目带动脱贫人口直接受益15人","提高群众生产生活水平，解决脱贫户5户15人道路出行问题",null,"县级",30,"沅财农指〔2022〕22号"]
[13,"乡村建设","人居环境整治","村容村貌提升","新湾镇","桥北村","桥北村人居环境整治建设","人居环境整治","桥北村","2022-09-01","2022-10-01","桥北村","村容村貌提升",30,30,null,null,0,1,188,442,0,1,2,"项目带动脱贫人口直接受益2人","人居环境整治建设，提升群众生活环境",null,285,30,"沅财农指〔2022〕21号"]
[14,"乡村建设","农村基础设施","农村道路建设","新湾镇","桥北村","桥北村道路及配套设施建设","基础设施","桥北村","2022-09-01","2022-10-01","桥北村","桥北村道路及配套设施建设",40,40,null,null,0,1,194,481,0,5,13,"项目带动脱贫人口直接受益13人","完善村级基础设施配套设施，提高群众生产生活水平",null,"县级",40,"沅财农指〔2022〕22号"]
[1,"产业发展","生产项目","种植业基地","南嘴镇","百家沟村","百家沟村产业园建设","新建","百家沟村","2022-09-01","2022-12-01","乡村振兴局","1、柑桔品改基地建设\n2、红薯深加工生产线\n3、冷水鱼养殖山塘维修",128,80,null,null,48,1,1488,4247,1,118,281,"满意度指标、服务对象满意度指标、受益建档立卡贫困人口满意度≥95%","①完善村级基础设施，提高群众生产生活水平；\n②增加村集体经济，带动群众增收增产。",null,"中央第二批沅振发〔2022〕5号",80,"沅财农指〔2022〕8号"]
[2,"乡村建设行动","农村基础设施","产业路建设","南嘴镇","和谐村","油茶基地基干道建设","新建","和谐村","2022-10-01","202年10月","乡村振兴局","油茶基地基干道建设",13,10,null,null,3,1,136,408,0,0,13,"提高村民收入","推动油茶发展",null,"中央第二批沅振发〔2022〕5号",10,"沅财农指〔2022〕8号"]
[3,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","南嘴镇","南嘴村","南嘴村示范路周家湾段建设","新建","南嘴村","2022-07-01","2022-08-31","乡村振兴局","示范路路基扩宽",8,5,null,null,3,1,347,1877,0,21,122,"满意度指标、服务对象满意度指标、受益建档立卡贫困人口满意度≥95%","①完善村级基础设施，提高群众生产生活水平；\n②增加村集体经济，带动群众增收增产。",null,"省第二批沅振发〔2022〕9号",5,"沅财农指〔2022〕13号"]
[4,"产业发展","配套基础设施项目","产业园区","南嘴镇","兴南村","兴南村产业路拓宽整修","扩建","兴南村","2022-09-01","2022-09-01","乡村振兴局","2公里主路拓宽1.5米",35,10,null,null,25,1,304,987,0,21,39,"满意度指标、服务对象满意度指标、受益建档立卡贫困人口满意度≥95%","①完善村级基础设施，提高群众生产生活水平；\n②增加村集体经济，带动群众增收增产。",null,"省第二批沅振发〔2022〕9号",10,"沅财农指〔2022〕13号"]
[5,"产业发展","生产项目","种植业基地","南嘴镇","百家沟村","柑桔品改","新建","百家沟村","2022-10-01","2023-04-01","乡村振兴局","柑桔品改基地建设",45,45,null,null,0,1,1488,4247,1,118,281,"满意度指标、服务对象满意度指标、受益建档立卡贫困人口满意度≥95%","①完善村级基础设施，提高群众生产生活水平；\n②增加村集体经济，带动群众增收增产。"]
[6,"产业发展","生产项目","种植业基地","南嘴镇","百家沟村","红薯深加工项目","新建","百家沟村","2022-09-01","2022-12-01","乡村振兴局","红薯深加工生产线",45,45,null,null,0,1,1488,4247,1,118,281,"满意度指标、服务对象满意度指标、受益建档立卡贫困人口满意度≥95%","①完善村级基础设施，提高群众生产生活水平；\n②增加村集体经济，带动群众增收增产。"]
[7,"乡村建设行动","农村基础设施","农村供水保障设施建设","南嘴镇","百家沟村","山塘整修及沟港清淤","新建","百家沟村","2022-11-01","2023-03-01","乡村振兴局","山塘整修及沟港清淤",40,40,null,null,0,1,1488,4247,1,118,281,"满意度指标、服务对象满意度指标、受益建档立卡贫困人口满意度≥95%","①完善村级基础设施，提高群众生产生活水平；\n②增加村集体经济，带动群众增收增产。"]
[8,"乡村建设行动","农村公共服务","其他","南嘴镇","百家沟村","文化广场新建","新建","百家沟村","2022-09-01","2022-12-31","乡村振兴局","包括篮球场新建、健身场所新建等",85,85,null,null,0,1,1488,4247,1,118,281,"满意度指标、服务对象满意度指标、受益建档立卡贫困人口满意度≥95%","①完善村级基础设施，提高群众生产生活水平；\n②增加村集体经济，带动群众增收增产。"]
[9,"产业发展项目","配套基础设施项目","小型农田水利设施建设","南嘴镇","目北村","南嘴镇目平湖北村沟渠清淤","新建","目平湖北村","2022-10-01","2022-12-01","乡村振兴局","清淤1公里",6,3,null,null,3,1,65,180,0,11,23,"满意度指标、服务对象满意度指标、受益建档立卡贫困人口满意度≥95%","①完善村级基础设施，提高群众生产生活水平；\n②增加村集体经济，带动群众增收增产。",null,285,3,"沅财农指〔2022〕21号"]
[1,"产业发展","生产项目","种植业基地","草尾镇","东红村","稻虾综合种养","改扩建","东红村九组","2022-08-01","2022-10-01","乡村振兴局","800米",10,10,null,null,0,1,20,82,1,3,8,1,"提高群众生产生活水平",null,"省第二批沅振发〔2022〕9号",10,"沅财农指〔2022〕14号"]
[2,"乡村建设行动","村容村貌提升","渠道疏洗","草尾镇","人益村","渠道疏洗","改扩建","民兵渠道","2022-08-01","2022-10-01","乡村振兴局","渠道疏洗3100米",5,5,null,null,0,1,1020,3200,1,67,165,1,"提高群众生产生活水平",null,"省一沅振发〔2022〕10号",5,"沅财农指〔2022〕15号"]
[3,"乡村建设行动","村容村貌提升","渠道疏洗","草尾镇","人益村","渠道疏洗","改扩建","1斗渠","2022-09-01","2022-10-01","乡村振兴局","渠道疏洗1600米",3,3,null,null,0,1,600,1700,1,27,78,1,"提高群众生产生活水平",null,"省第二批沅振发〔2022〕9号",3,"沅财农指〔2022〕13号"]
[4,"乡村建设行动","村容村貌提升","机埠维修","草尾镇","人益村","机埠维修","改扩建","电排机埠","2022-06-01","2022-10-01","乡村振兴局","机埠维修3台",{"$f":"O46+P46+Q46+R46","v":10},10,null,null,0,1,1020,3200,1,67,165,1,"提高群众生产生活水平",null,"省一沅振发〔2022〕10号",10,"沅财农指〔2022〕15号"]
[5,"乡村建设行动","农村基础设施","公路硬化","草尾镇","长乐村","公路硬化","改扩建","长乐村","2022-09-01","2022-10-01","乡村振兴局","3公里",6,6,null,null,0,1,40,136,1,10,35,1,"提高群众生产生活水平",null,"省一沅振发〔2022〕10号",6,"沅财农指〔2022〕15号"]
[6,"乡村建设行动","农村基础设施","公路路基平整","草尾镇","大福村","公路路基平整","改扩建","大福村19组","2022-08-01","2022-10-01","乡村振兴局","大福村19组灌渠公路是大福村北部重要公路之一，全长1000米，路基低洼不平，需平整，且加铺卵石。",3,3,null,null,0,1,500,1800,1,32,90,1,"①提升大福村北部整体运输能力。②：改善周边群众出行状况。",null,"省第二批沅振发〔2022〕9号",3,"沅财农指〔2022〕13号"]
[7,"乡村建设行动","农村基础设施","公路硬化","草尾镇","大福村","公路硬化","改扩建","大福村19组","2022-09-01","2022-10-01","乡村振兴局","大福村19组灌渠公路，全长1000米，需硬化",5,5,null,null,0,1,500,1800,1,26,84,1,"①提升大福村北部整体运输能力。②：改善周边群众出行状况。",null,"省一沅振发〔2022〕10号",5,"沅财农指〔2022〕15号"]
[8,"乡村建设行动","农村基础设施","公路维修","草尾镇","草尾社区","公路维修","改扩建","草尾社区","2022-10-01","2022-10-01","乡村振兴局","1.2公里",3,3,null,null,0,1,120,364,1,0,0,1,"提高居民\n生活水平，方便出行。",null,"省一沅振发〔2022〕10号",3,"沅财农指〔2022〕15号"]
[9,"乡村建设行动","村容村貌提升","机埠维修","草尾镇","大同闸村","机埠维修","改扩建","大同闸村东排渠","2022-09-01","2022-10-01","乡村振兴局","东排渠机埠一座",22,22,null,null,0,1,62,163,1,9,15,1,"提高群众生产生活水平",null,"省一沅振发〔2022〕10号",22,"沅财农指〔2022〕15号"]
[10,"乡村建设行动","农村基础设施","公路维修","草尾镇","大同闸村","公路维修","改扩建","大跃片、东堤路","2022-09-01","2022-10-01","乡村振兴局","80米",5,5,null,null,0,1,35,98,1,9,15,1,"提高居民\n生活水平，方便出行。",null,"省一沅振发〔2022〕10号",5,"沅财农指〔2022〕15号"]
[11,"乡村建设行动","村容村貌提升","渠道疏洗","草尾镇","人和村","渠道疏洗","改扩建","四斗渠","2022-09-01","2022-10-01","乡村振兴局","四斗渠疏洗及两边道路扫障",5,5,null,null,0,1,126,420,1,8,31,1,"提高群众生产生活水平",null,"省一沅振发〔2022〕10号",5,"沅财农指〔2022〕15号"]
[12,"乡村建设行动","农村基础设施","公路硬化","草尾镇","和平村","公路硬化","改扩建","新征片5组","2022-07-01","2022-10-01","乡村振兴局","道路硬化200米",10,10,null,null,0,1,48,186,1,12,40,1,"提高群众生产生活水平",null,"省一沅振发〔2022〕10号",10,"沅财农指〔2022〕15号"]
[13,"乡村建设行动","农村基础设施","公路维护","草尾镇","双东村","公路维护","改扩建","草尾社区","2022-10-01","2022-10-01","乡村振兴局","0.8公里",3,3,null,null,0,1,100,280,1,0,0,1,"提高居民\n生活水平，方便出行。",null,"省第二批沅振发〔2022〕9号",3,"沅财农指〔2022〕13号"]
[14,"乡村建设行动","农村基础设施","公路路基建设","草尾镇","民主村","公路路基建设","改扩建","村部与大堤之间","2022-08-01","2022-10-01","乡村振兴局","0.3公里",10,10,null,null,0,1,450,1300,1,22,67,1,"提高群众生产生活水平",null,"省第二批沅振发〔2022〕9号",10,"沅财农指〔2022〕13号"]
[15,"产业发展","生产项目","种植业基地","草尾镇","上码头村","稻虾综合种养","新建","草尾镇上码头村","2022-05-01","2022-10-01","乡村振兴局","100亩",45,20,null,null,25,1,35,42,1,2,4,"项目带动脱贫人口直接受益46人","提高群众生产生活水平",null,"中央第二批沅振发〔2022〕5号",20,"沅财农指〔2022〕8号"]
[16,"乡村建设行动","人居环境整治提升","村容村貌提升","草尾镇","上码头村","人居环境整治提升","改扩建","草尾镇上码头村","2022-05-01","2022-10-01","乡村振兴局","公路硬化0.3公里；渠道疏洗500米；涵闸维修6处；公路维修0.2公里；渠道整修400米；",30,30,null,null,0,1,65,153,1,6,12,"项目带动脱贫人口直接受益153人","提高群众生产生活水平",null,"省第二批沅振发〔2022〕9号",30,"沅财农指〔2022〕13号"]
[17,"乡村建设行动","农村基础设施","公路维修","草尾镇","上码头村","公路维修","改扩建","草尾镇上码头村","2022-05-01","2022-10-01","乡村振兴局","0.2公里",9,9,null,null,0,1,34,45,1,5,10,1,"提高群众生产生活水平",null,"省一沅振发〔2022〕10号",9,"沅财农指〔2022〕15号"]
[18,"乡村建设行动","村容村貌提升","渠道疏洗","草尾镇","新安村","渠道疏洗","改扩建","草尾镇新安村","2022-05-01","2022-11-01","乡村振兴局","1500米",5,5,null,null,0,1,26,58,1,8,28,1,"提高群众生产生活水平",null,285,5,"沅财农指〔2022〕21号"]
[19,"乡村建设行动","农村基础设施","简易机耕路建设","草尾镇","乐园村","简易机耕路建设","新建","草尾镇乐园村","2022-08-01","2022-10-01","乡村振兴局","1.1公里",10,10,null,null,0,1,106,390,1,11,27,1,"提高群众生产生活水平",null,285,10,"沅财农指〔2022〕21号"]
[20,"乡村建设行动","农村基础设施","机埠维修","草尾镇","立新村","机埠维修","维修","草尾镇立新村","2022-04-01","2022-10-01","乡村振兴局","2处",10,10,null,null,0,1,86,380,0,5,8,1,"提高群众生产生活水平",null,285,10,"沅财农指〔2022〕21号"]
[1,"产业发展","生产项目","种植业基地","阳罗洲镇","大中村","沅江市_产业项目_2022年沅江市阳罗洲镇大中村经济合作社","新建","阳罗洲镇大中村","2022-06-10","2022-06-25","乡村振兴局","粮食8000亩",80,80,null,null,0,1,32,113,1,28,103,"带动脱贫户及监测户人均年增收500元","受益对象人均年增收500元",null,"中央第二批沅振发〔2022〕5号",80,"沅财农指〔2022〕8号"]
[2,"产业发展","生产项目","种植业基地","阳罗洲镇","胜利村","沅江市_产业项目_阳罗洲镇2022年湖南宴府农业科技有限公司","维修","阳罗洲镇胜利村","2022-06-10","2022-06-25","乡村振兴局","蔬菜 300亩",20,20,null,null,0,1,55,132,0,40,112,"带动脱贫户及监测户人均年增收500元","受益对象年均纯收入增收500元",null,"中央第二批沅振发〔2022〕5号",20,"沅财农指〔2022〕8号"]
[3,"产业发展","生产项目","种植业基地","阳罗洲镇","七子浃村","沅江市_产业项目_阳罗洲镇2022年鼎胜稻虾供养合作社","扩建","阳罗洲镇七子浃村","2022-08-25","2022-09-10","乡村振兴局","厂房扩建",10,10,null,null,0,1,77,232,0,57,187,"带动脱贫户及监测户人均年增收200元","受益对象年均纯收入增收200元",null,"省第二批沅振发〔2022〕9号",10,"沅财农指〔2022〕14号"]
[4,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","阳罗洲镇","吕丰村","沅江市_村基础设施_阳罗洲镇2022年吕丰村渔场9支渠道路修整","维修","阳罗洲镇吕丰村","2022-08-25","2022-09-10","乡村振兴局","道路整修",10,10,null,null,0,1,220,620,0,114,358,"带动脱贫户及监测户人均年增收200元","便利群众出行",null,"省第二批沅振发〔2022〕9号",10,"沅财农指〔2022〕13号"]
[5,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","阳罗洲镇","富安村","沅江市_村基础设施_阳罗洲镇2022年富安村富安村一组南吉渠破碎板维修","维修","阳罗洲镇富安村","2022-08-25","2022-09-10","乡村振兴局","道路整修",5,5,null,null,0,1,350,650,0,102,286,"带动脱贫户及监测户人均年增收200元","便利群众出行",null,"省第二批沅振发〔2022〕9号",5,"沅财农指〔2022〕13号"]
[6,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","阳罗洲镇","宝三村","沅江市_村基础设施_阳罗洲镇2022年宝三村九组桥梁新建","新建","阳罗洲镇宝三村","2022-08-25","2022-09-10","乡村振兴局","桥梁新建",5,5,null,null,0,1,16,52,0,10,34,"带动脱贫户及监测户人均年增收150元","便利群众出行",null,"省第二批沅振发〔2022〕9号",5,"沅财农指〔2022〕13号"]
[7,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","阳罗洲镇","富民村","沅江市_村基础设施_阳罗洲镇2022年富民村光明渠西兴丰七组公路修整","维修","阳罗洲镇富民村","2022-08-25","2022-09-10","乡村振兴局","公路修整",5,5,null,null,0,1,210,460,0,75,266,"带动脱贫户及监测户人均年增收200元","便利群众出行",null,"省第二批沅振发〔2022〕9号",5,"沅财农指〔2022〕13号"]
[8,"乡村建设行动","人居环境整治","村容村貌提升","阳罗洲镇","永兴社区","沅江市_村基础设施_阳罗洲镇2022年村容村貌提升","维修","阳罗洲镇永兴社区","2022-08-25","2022-09-10","乡村振兴局","人居环境整治",8,8,null,null,0,1,87,302,0,0,0,"改善人居环境","改善人居环境",null,"省第二批沅振发〔2022〕9号",8,"沅财农指〔2022〕13号"]
[9,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","阳罗洲镇","七子浃村","沅江市_村基础设施_阳罗洲镇2022年七子浃村九斗道路硬化","维修","阳罗洲镇七子浃村","2022-08-25","2022-09-10","阳罗洲镇七子浃村","道路硬化",10,10,null,null,0,1,520,1558,0,28,62,"带动脱贫户及监测户人均年增收200元","便利群众出行",null,285,10,"沅财农指〔2022〕21号"]
[10,"乡村建设行动","农村基础设施","小型农田水利设施建设","阳罗洲镇","兴乐村","沅江市_村基础设施_阳罗洲镇2022年兴乐村二组排水渠渠道清淤","维修","阳罗洲镇兴乐村二组","2022-10-08","2022-10-15","阳罗洲镇兴乐村","渠道清淤",5,5,null,null,0,1,23,72,1,23,72,"带动脱贫户及监测户人均年增收200元","便利群众生产",null,285,5,"沅财农指〔2022〕21号"]
[1,"乡村建设行动","基础设施设备","四季红镇数字乡村平台建设","四季红镇","四季红镇","四季红镇数字乡村平台建设","新建","四季红镇","2022-08-01","2022-08-01","四季红镇","7村1社区建设数字乡村平台",20,20,null,null,0,8,312,1079,2,16,35,"增加群众收入","增加群众收入",null,"省第二批沅振发〔2022〕9号",20,"沅财农指〔2022〕13号"]
[2,"乡村建设行动","人居环境整治","斗渠清淤扫障整治工程","四季红镇","先锋村","先锋村十斗渠清淤扫障整治工程","新建","先锋村十组","2022-08-01","2022-08-01","玉鹊村","渠道清淤扫障105米",5,5,null,null,0,1,41,117,null,3,5,"改善群众生活条件、群众满意度≥100%","改善群众生活条件",null,"省第二批沅振发〔2022〕9号",5,"沅财农指〔2022〕13号"]
[3,"乡村建设行动","人居环境整治","斗渠清淤扫障整治衬砌工程","四季红镇","四季红社区","四季红社区五星七组斗渠清淤扫障整治衬砌工程","新建","四季红社区五星七组","2022-08-01","2022-08-01","四季红社区","渠道清淤扫障衬砌120米，",10,10,null,null,0,1,53,203,null,5,9,"改善群众生活条件、群众满意度≥100%","改善群众生活条件",null,"省第二批沅振发〔2022〕9号",10,"沅财农指〔2022〕13号"]
[4,"乡村建设行动","美丽村庄建设","美丽村庄建设","四季红镇","玉鹊村","玉鹊村11、2、3、6、7组沿线美丽村庄整体规划建设","新建","玉鹊村11、2、3、6、7组","2022-08-01","2022-09-01","玉鹊村","各组人居环境整治、八个一建设",30,30,null,null,0,1,175,915,null,25,73,"改善群众生活条件、群众满意度≥100%","改善群众生活条件",null,"省第二批沅振发〔2022〕9号",30,"沅财农指〔2022〕13号"]
[5,"乡村建设行动","基础设施设备","四季红村3组机耕道砂石硬化","四季红镇","四季红村","四季红镇四季红村3组机耕道砂石硬化","新建","四季红村3组","2022-07-01","2022-07-01","四季红村","3组机耕道砂石硬化500米",10,10,null,null,0,1,89,326,1,16,35,"增加群众收入","增加群众收入",null,"中央第二批沅振发〔2022〕5号",10,"沅财农指〔2022〕8号"]
[6,"产业发展","配套设施项目","玉鹊村丰年农业有限公司","四季红镇","玉鹊村","玉鹊村丰年农业有限公司配套","新建","玉鹊村","2022-07-01","2022-08-01","玉鹊村","产业发展配套设施建设",20,20,{"$nulls":3},1,320,1260,0,24,56,"改善群众生活条件、群众满意度≥100%","改善群众生活条件",null,"中央第二批沅振发〔2022〕5号",20,"沅财农指〔2022〕8号"]
[7,"产业发展","配套设施项目","龙虾交易市场配套设施建设","四季红镇","安心村","龙虾交易市场配套设施建设","新建","安心村原加工厂","2022-08-01","2022-08-01","安心村","龙虾交易市场地坪、排水等设施",10,10,null,null,0,1,300,900,null,41,96,"增加群众收入","增加群众收入",null,"省第二批沅振发〔2022〕9号",10,"沅财农指〔2022〕14号"]
[8,"产业发展","生产项目","种植业基地","四季红镇","四季红村","四季红村9组菜园美化布局","新建","四季红村9组","2022-08-01","2022-10-01","四季红村","9组居民组美丽屋场建设",10,10,{"$nulls":3},1,45,114,1,26,76,"改善群众生活条件、群众满意度≥100%","改善群众生活条件",null,"市第一批",10,"沅财农指〔2022〕16号"]
[9,"乡村建设行动","基础设施设备","土方填筑","四季红镇","四季红村","四季红村中心渠土石方工程","新建","四季红村中心渠","2022-08-01","2022-10-01","四季红村","土方填筑及渠道建设",15,15,{"$nulls":3},1,297,830,1,26,76,"改善群众生活条件、群众满意度≥100%","改善群众生活条件",null,"市第一批",15,"沅财农指〔2022〕16号"]
[10,"乡村建设行动","基础设施设备","挡土墙建设","四季红镇","四季红村","四季红村中心渠挡土墙工程","新建","四季红村中心渠","2022-08-01","2022-10-01","四季红村","挡土墙、水泥板建设",25,25,{"$nulls":3},1,297,830,1,26,76,"改善群众生活条件、群众满意度≥100%","改善群众生活条件",null,"市第一批",25,"沅财农指〔2022〕16号"]
[11,"乡村建设行动","基础设施设备","渠道硬化","四季红镇","阳雀洪村","阳雀洪村印刷厂配套设施建设（渠道硬化）","新建","阳雀洪印刷厂周边渠道","2022-09-01","2022-10-01","阳雀洪村","渠道衬砌、硬化500米",10,10,{"$nulls":3},1,40,118,1,24,68,"改善群众生产生活条件、群众满意度≥100%","改善群众生产生活条件",null,285,10,"沅财农指〔2022〕21号"]
[1,"乡村建设","农村基础设施","小型农田水利设施建设","黄茅洲镇","洞庭滨村","村级渠道清淤","扩建","洞庭滨村","2022-09-01","2022-12-01","乡村振兴局","渠道清淤南排渠3300米",{"$f":"O84+P84+Q84+R84","v":10},10,null,null,0,1,661,2062,1,38,104,"收益建档立卡贫困人口满意度≥95%","农业生产灌溉"]
[2,"产业发展","配套设施项目","农村道路建设（通村、通户路）","黄茅洲镇","黄茅洲村","湖南省碧蓝生态农业发展有限公司基地基础设施建设","新建","黄茅洲村","2022-08-01","2022-10-01","乡村振兴局","新修栈道75米，4个大棚架设遮阳布",10,10,null,null,0,1,245,520,1,23,85,"完善基础设施带动产业发展","群众满意度≥95%",null,"省第二批沅振发〔2022〕9号",10,"沅财农指〔2022〕13号"]
[3,"产业发展","配套设施项目","农村道路建设（通村、通户路）","黄茅洲镇","黄栗塘村","道路维修","维修","黄栗塘村安南7组","2022-08-01","2022-12-01","乡村振兴局","240米",10,10,null,null,0,1,246,785,1,35,80,"完善基础设施带动产业发展","群众满意度≥95%",null,"省第二批沅振发〔2022〕9号",10,"沅财农指〔2022〕13号"]
[4,"乡村建设","农村基础设施","小型农田水利设施建设","黄茅洲镇","晒袍社区","田耕道建设","维修","长青三组","2022-08-01","2022-12-01","乡村振兴局","550米",6,6,null,null,0,1,250,567,1,4,9,"收益建档立卡贫困人口满意度≥95%","便于运输和出行",null,"省第二批沅振发〔2022〕9号",6,"沅财农指〔2022〕13号"]
[5,"乡村建设","农村基础设施","人居环境","黄茅洲镇","柳树坪村","人居环境提质改造工程","新建","柳树坪村","2022-08-01","2022-10-01","乡村振兴局","2100米",50,50,null,null,0,1,387,826,1,26,75,"收益建档立卡贫困人口满意度≥95%","便于运输和出行",null,"省第二批沅振发〔2022〕9号",50,"沅财农指〔2022〕13号"]
[6,"乡村建设","农村基础设施","农村道路建设（拓宽、维修）","黄茅洲镇","志成垸村","道路加宽维修","扩建、","志成垸村","2022-08-01","2022-12-01","乡村振兴局","志成8.9.10组",10,10,null,null,0,1,246,528,1,15,54,"收益建档立卡贫困人口满意度≥95%","便于运输和出行",null,285,10,"沅财农指〔2022〕21号"]
[7,"乡村建设","农村基础设施","农村道路建设（拓宽、维修）","黄茅洲镇","民心村","道路加宽维修","新建","民心村","2022-08-01","2022-12-01","乡村振兴局","480米",15,15,null,null,0,1,864,3346,1,35,79,"收益建档立卡贫困人口满意度≥95%","便于运输和出行",null,285,15,"沅财农指〔2022〕21号"]
[8,"乡村建设","农村基础设施","水利设施建设","黄茅洲镇","金南村","整修渠道","维修","金南村","2022-08-01","2022-12-01","乡村振兴局","900米",8,8,null,null,0,1,515,1485,1,33,84,"收益建档立卡贫困人口满意度≥95%","便于农业生产灌溉",null,285,8,"沅财农指〔2022〕21号"]
[9,"乡村建设","农村基础设施","水利设施建设","黄茅洲镇","晒袍社区","机耕道整修","维修","长青二组","2022-10-01","2022-12-01","乡村振兴局","680米",8,8,null,null,0,1,"250",567,1,3,8,"收益建档立卡贫困人口满意度≥95%","便于运输和出行",null,285,8,"沅财农指〔2022〕21号"]
[10,"乡村建设","农村基础设施","美丽村庄建设","黄茅洲镇","柳树坪村","渠道护坡","新建","柳树坪村","2022-08-01","2022-10-01","乡村振兴局","920米",20,20,null,null,0,1,1020,3424,1,61,125,"收益建档立卡贫困人口满意度≥95%","提高群众文化活动水平，推进农村文化发展",null,285,20,"沅财农指〔2022〕21号"]
[1,"乡村建设","农村基础设施","农村道路建设（通村、通户路）","南大膳镇","同丰垸村","南大膳镇同丰垸村基础设施公路拓宽项目10W","扩建","同丰垸村","2022-08-10","2022-08-20","同丰垸村","0.25KM",10,10,null,null,0,1,25,76,1,6,17,"便于群众出行，群众满意度100%","提升群众生产生活条件",null,"省第二批沅振发〔2022〕9号",10,"沅财农指〔2022〕13号"]
[2,"乡村建设","农村基础设施","其他","南大膳镇","合利红村","南大膳镇合利红村基础设施危桥改造项目10W","维修","合利红村","2022-08-04","2022-08-11","合利红村","1座",10,10,null,null,0,1,76,198,0,14,41,"便于群众出行，群众满意度100%","提升群众生产生活条件",null,"省第二批沅振发〔2022〕9号",10,"沅财农指〔2022〕13号"]
[3,"产业发展","配套基础设施项目","小型农田水利设施建设","南大膳镇","牛洲村","南大膳镇牛洲村基础设施渠道衬砌项目10W","新建","牛洲村","2022-08-06","2022-08-11","牛洲村","0.2KM",10,10,null,null,0,1,22,54,0,4,13,"便于群众生产生活，群众满意度100%","提升群众生产生活条件",null,"省第二批沅振发〔2022〕9号",10,"沅财农指〔2022〕13号"]
[4,"乡村建设","农村基础设施","农村道路建设（通村、通户路）","南大膳镇","南大渔村","南大膳镇南大渔村基础设施道路维修项目3W","维修","南大渔村","2022-08-12","2022-08-22","南大渔村","0.2km",3,3,{"$nulls":3},1,18,44,0,6,13,"便于群众出行，群众满意度100%","提升群众生产生活条件",null,"省第二批沅振发〔2022〕9号",3,"沅财农指〔2022〕13号"]
[5,"乡村建设","农村基础设施","农村道路建设（通村、通户路）","南大膳镇","南大河村","南大膳镇南大河村基础设施道路拓宽项目10W","扩建","南大河村","2022-08-11","2022-08-22","南大河村","0.5km",10,10,{"$nulls":3},1,32,86,0,16,42,"便于群众出行，群众满意度100%","提升群众生产生活条件",null,"省第二批沅振发〔2022〕9号",10,"沅财农指〔2022〕13号"]
[6,"乡村建设","农村基础设施","农村道路建设（通村、通户路）","南大膳镇","义南村","南大膳镇义南村基础设施道路维修项目3W","维修","义南村","2022-08-14","2022-08-21","义南村","0.12km",3,3,{"$nulls":3},1,16,35,0,4,11,"便于群众出行，群众满意度100%","提升群众生产生活条件",null,"省第二批沅振发〔2022〕9号",3,"沅财农指〔2022〕13号"]
[7,"乡村建设","农村基础设施","农村道路建设（通村、通户路）","南大膳镇","灵官嘴村","南大膳镇灵官嘴村基础设施道路硬化项目3W","新建","灵官嘴村","2022-07-23","2022-07-25","灵官嘴村","0.056km",3,3,{"$nulls":3},1,13,38,0,6,19,"便于群众出行，群众满意度100%","提升群众生产生活条件",null,"省第二批沅振发〔2022〕9号",3,"沅财农指〔2022〕13号"]
[8,"乡村建设","农村基础设施","农村道路建设（通村、通户路）","南大膳镇","石东港村","南大膳镇石东港村基础设施道路拓宽及配套工程30W","扩建","石东港村","2022-07-25","2022-08-06","石东港村","1km",30,30,{"$nulls":3},1,88,212,0,14,46,"便于群众出行，群众满意度100%","提升群众生产生活条件",null,"省第二批沅振发〔2022〕9号",30,"沅财农指〔2022〕13号"]
[9,"产业发展","生产项目","种植业基地","南大膳镇","石东港村","南大膳镇石东港村优质稻生产基地建设项目20W","新建","石东港村","2022-06-11","2022-06-25","石东港村","1500亩",20,20,null,null,0,1,232,842,0,24,79,"提高群众满意度","提供产前产中产后服务，和农户签订订单收购合同",null,"中央第二批沅振发〔2022〕5号",20,"沅财农指〔2022〕8号"]
[10,"乡村建设","农村基础设施","农村道路建设（通村、通户路）","南大膳镇","同丰垸村","南大膳镇同丰垸村基础设施公路拓宽项目20W","扩建","同丰垸村","2022-08-01","2022-08-02","同丰垸村","1.5KM",20,20,{"$nulls":3},1,127,349,1,14,31,"便于群众出行，群众满意度100%","提升群众生产生活条件",null,"市第一批",20,"沅财农指〔2022〕16号"]
[11,"产业发展","生产项目","种植业基地","南大膳镇","同丰垸村","南大膳镇同丰垸村优质稻基地项目（一家亲30W）","新建","同丰垸村","2022-08-05","2022-08-15","同丰垸村","一家米业优质稻基地及仓储烘干",30,30,{"$nulls":3},1,2310,6690,1,132,349,"提高群众满意度","提供产前产中产后服务，和农户签订订单收购合同",null,"市第一批",30,"沅财农指〔2022〕16号"]
[12,"乡村建设","农村基础设施","小型农田水利设施","南大膳镇","合利红村","南大膳镇合利红村基础设施渠道梳洗项目5W","维修","合利红村","2022-09-12","2022-09-16","合利红村","1.6km",5,5,{"$nulls":3},1,76,198,0,14,41,"提高群众满意度","提升群众生产生活条件",null,285,5,"沅财农指〔2022〕21号"]
[1,"产业发展","生产项目","养殖业基地","共华镇","八形汊村","2022共华镇八形汊村产业发展甲鱼养殖和基地建设","新建","八形汊村","2022-06-30","2022-07-19","八形汊村","甲鱼养殖基地20亩",20,20,{"$nulls":3},1,30,150,0,null,null,"项目验收合格率100%","提高群众生产生活水平",null,"中央第二批沅振发〔2022〕5号",20,"沅财农指〔2022〕8号"]
[2,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","共华镇","东合村","2022共华镇东合村公路路基拓宽","新建","东合村","2022-10-18","2022-11-30","东合村","路基拓宽2公里",10,10,{"$nulls":3},1,200,395,0,null,null,"项目验收合格率100%","提高群众生产生活水平",null,"省一沅振发〔2022〕10号",10,"沅财农指〔2022〕15号"]
[3,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","共华镇","宪成垸村","2022共华镇宪成垸村公路建设","新建","宪成垸村","2022-08-09","2022-11-30","宪成垸村","道路硬化0.2公里",5,5,{"$nulls":3},1,100,100,0,null,null,"项目验收合格率100%","提高群众生产生活水平",null,"省第二批沅振发〔2022〕9号",5,"沅财农指〔2022〕13号"]
[4,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","共华镇","白沙洲村","2022共华镇白沙洲村道路建设","新建","白沙洲村","2022-08-09","2022-08-26","白沙洲村","道路硬化0.2公里",5,5,{"$nulls":3},1,60,100,0,null,null,"项目验收合格率100%","提高群众生产生活水平",null,"省第二批沅振发〔2022〕9号",5,"沅财农指〔2022〕13号"]
[5,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","共华镇","八形汊村","2022共华镇八形汊村沿河道路路基及配套设施建设","新建","八形汊村","2022-08-09","2022-08-08","八形汊村","路基建设2.8公里",30,30,{"$nulls":3},1,300,600,0,null,null,"项目验收合格率100%","提高群众生产生活水平",null,"省第二批沅振发〔2022〕9号",30,"沅财农指〔2022〕13号"]
[6,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","共华镇","八形汊村","2022共华镇八形汊村道路配套设施建设","新建","八形汊村","2022-09-21","2022-09-27","八形汊村","路基建设0.5公里、涵闸建设1座",30,30,{"$nulls":3},1,300,300,0,null,null,"项目验收合格率100%","提高群众生产生活水平",null,285,30,"沅财农指〔2022〕21号"]
[7,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","共华镇","团湖洲村","2022共华镇团湖洲村道路路基建设","新建","团湖洲村","2022-09-21","2022-11-30","团湖洲村","路基建设1公里",5,5,{"$nulls":3},1,36,106,1,null,null,"项目验收合格率100%","提高群众生产生活水平",null,285,5,"沅财农指〔2022〕21号"]
[8,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","共华镇","黄土包村","2022共华镇黄土包村道路路基建设","新建","黄土包村","2022-09-21","2022-10-11","黄土包村","路基建设1公里",3,3,{"$nulls":3},1,20,40,0,null,null,"项目验收合格率100%","提高群众生产生活水平",null,285,3,"沅财农指〔2022〕21号"]
[9,"产业发展","生产项目","种植业基地","共华镇","紫红洲村","2022共华镇紫红洲村艾草基地建设","新建","紫红洲村","2022-08-18","2022-11-30","紫红洲村","艾草基地80亩",50,50,{"$nulls":3},1,200,500,0,null,null,"项目验收合格率100%","提高群众生产生活水平",null,"市第一批",50,"沅财农指〔2022〕16号"]
[10,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","共华镇","福安村","2022共华镇福安村道路及配套设施建设","新建","福安村","2022-09-21","2022-10-24","福安村","道路硬化963平方，渠道梳洗6公里",50,50,{"$nulls":3},1,265,407,1,null,null,"项目验收合格率100%","提高群众生产生活水平",null,"县级",50,"沅财农指〔2022〕22号"]
[1,"乡村建设","农村基础设施","农村道路建设（通村、通户路）","泗湖山镇","两鲜村","泗湖山镇两鲜村-基础设施-鲜鱼塘片六组倒口公路护坡和硬化","新建","两鲜村鲜鱼塘片六组","2022-08-01","2022-10-01","乡村振兴局","公路硬化、护坡120米",{"$f":"O116+P116+Q116+R116","v":20},20,null,null,0,1,100,216,0,6,12,"受益脱贫人口满意度≧98%","①完善村级基础设施，提高群众生产生活水平；\n②方便全村贫困户与非贫困户农业生产。",null,"省第二批沅振发〔2022〕9号",20,"沅财农指〔2022〕13号"]
[2,"乡村建设","农村基础设施","小型农田水利设施","泗湖山镇","华星村","泗湖山镇华星村-基础设施-星台片五、六组和十六组界沟疏洗","新建","星台片五、六组和十六组","2022年8组","2022-10-01","乡村振兴局","约1000米",{"$f":"O117+P117+Q117+R117","v":3},3,null,null,0,1,1,20,0,8,20,"受益脱贫人口满意度≥98%","①完善村级基础设施，提高群众生产生活水平；\n②方便全村贫困户与非贫困户农业生产。",null,"省第二批沅振发〔2022〕9号",3,"沅财农指〔2022〕13号"]
[3,"乡村建设","农村基础设施","农村道路建设（通村、通户路）","泗湖山镇","泗湖山社区","泗湖山镇泗湖山社区-基础设施-泗湖山村二组、四组、七组二级田间道铺卵石","维修","泗湖山村二组、四组、七组二级田间道铺卵石","2022-08-01","2022-10-01","乡村振兴局","1300米",{"$f":"O118+P118+Q118+R118","v":5},5,null,null,0,1,150,600,1,21,43,"受益脱贫人口满意度≥98%","①完善村级基础设施，提高群众生产生活水平；\n②方便全村贫困户与非贫困户农业生产。",null,"省第二批沅振发〔2022〕9号",5,"沅财农指〔2022〕13号"]
[4,"乡村建设","农村基础设施","农村道路建设（通村、通户路）","泗湖山镇","朱冯村","泗湖山镇朱冯村-基础设施-冯家湾1组土撑清除道路拉直","新建","朱冯村冯家湾1组土撑清除道路拉直","2022-08-01","2022-12-01","乡村振兴局","土撑清除\n道路拉直",{"$f":"O119+P119+Q119+R119","v":10},10,null,null,0,1,540,1280,0,55,116,"受益脱贫人口满意度≥98%","①完善村级基础设施，提高群众生产生活水平；\n②方便全村贫困户与非贫困户农业生产。",null,"省第二批沅振发〔2022〕9号",10,"沅财农指〔2022〕13号"]
[5,"乡村建设","农村基础设施","农村道路建设（通村、通户路）","泗湖山镇","南竹脑村","泗湖山镇南竹脑村-基础设施-南护桥桥面维修","维修","南竹脑村十三组","2022-08-01","2022-10-01","乡村振兴局","桥面维修",{"$f":"O120+P120+Q120+R120","v":5},5,null,null,0,1,40,120,0,8,16,"受益脱贫人口满意度≥95%","①完善村级基础设施，提高群众生产生活水平；\n②方便全村贫困户与非贫困户农业生产。",null,"省第二批沅振发〔2022〕9号",5,"沅财农指〔2022〕13号"]
[6,"乡村建设","农村人居环境整治","村容村貌提升","泗湖山镇","华红村","2022年泗湖山镇华红村-基础设施-华红村洞庭红片4-11组人居环境整治","新建","华红村洞庭红片4-11组","2022-08-01","2022-10-01","乡村振兴局","人居环境整治，洞庭红片4-11组",{"$f":"O121+P121+Q121+R121","v":10},10,null,null,0,1,30,80,0,0,0,"受益群众满意度≥95%","①完善基础设施建设提高群众生活水平；②改善人居环境。",null,"省第二批沅振发〔2022〕9号",10,"沅财农指〔2022〕13号"]
[7,"乡村建设","农村基础设施","农村道路建设（通村、通户路）","泗湖山镇","华红村","2022年泗湖山镇华红村-基础设施-华红村文林片12组公路硬化","新建","华红村文林片12组","2022-08-01","2022-09-01","乡村振兴局","新建公路427米",20,20,null,null,0,1,8,20,0,0,0,"受益群众满意度≥95%","①完善基础设施建设提高群众生产生活水平；②方便群众产品运输。",null,"市第一批",20,"沅财农指〔2022〕16号"]
[8,"产业发展","生产项目","种养业\n基地","泗湖山镇","北港村","2021泗湖山镇北港村-产业发展-沅江市华光种养专业合作社","扩建","北港村","2022-08-01","2022-10-01","乡村振兴局","投放投入白鲢鱼134000尾、大头鱼鱼苗23000尾及人工管理",20,20,null,null,0,1,21,30,0,0,0,"特色产业带动增加脱贫户人均收入≥200元","①与五类人员采取委托帮扶的模式形成利益联结机制②发展壮大村集体经济，入股分红提高村集体经济收入，增加全村监测户收入。",null,"中央第二批沅振发〔2022〕5号",20,"沅财农指〔2022〕8号"]
[9,"产业发展","加工流通项目","展销平台","泗湖山镇","北港村","泗湖山镇北港村-产业项目-沅江市华光农产品贸易公司","新建","北港村1组","2022-08-01","2022-10-01","乡村振兴局","1个",30,30,null,null,0,1,30,68,0,8,20,"受益脱贫人口满意度≥98%","①与五类人员采取委托帮扶的模式形成利益联结机制②发展壮大村集体经济，入股分红提高村集体经济收入，增加全村监测户收入。",null,"省第二批沅振发〔2022〕9号",30,"沅财农指〔2022〕13号"]
[10,"产业发展","生产项目","种植业基地","泗湖山镇","华红村","2022年泗湖山镇华红村-产业发展-泗水砂石建材销售中心","新建","华红村洞庭红片4组","2022-07-01","2022-08-01","农业局","新建一个砂石场",30,30,null,null,0,1,6,23,0,0,0,"受益群众满意度≥95%","①与五类人员采取委托帮扶的模式形成利益联结机制②发展壮大村集体经济，入股分红提高村集体经济收入，增加全村监测户收入。",null,"市第一批",30,"沅财农指〔2022〕16号"]
[11,"产业发展","生产项目","种植业基地","泗湖山镇","华红村","2022年泗湖山镇华红村-产业发展-华安水稻种植专业合作社","新建","华红村长安片","2022-10-01","2023-10-01","农业局","1.引进优质香稻建设200亩有机稻示范田2.品牌打造",66,30,null,null,36,1,60,100,0,0,0,"受益群众满意度≥95%","①与五类人员采取委托帮扶的模式形成利益联结机制；②直接帮扶42户脱贫户和监测户参与发展产业，带动近50人就地务工，项目建成后每亩增加收入3000元，预计可为脱贫户及监测户60人增收。人均增收将达15000元"]
[12,"产业发展","生产项目","种养业基地","泗湖山镇","华红村","2022年泗湖山镇华红村-产业发展-鑫淼稻虾种养合作社","新建","华红村重华片","2022-10-01","2023-03-01","农业局","1.建设稻虾共作面积800亩;2.销售平台",80,30,null,null,50,1,20,36,0,0,0,"受益群众满意度≥95%","①与五类人员采取委托帮扶的模式形成利益联结机制；②带领周边群众持续增收，建立稳定销售平台、受益脱贫户及监测户人数36人"]
[13,"乡村建设","农村基础设施","农村道路建设（通村、通户路）","泗湖山镇","北港村","泗湖山镇两鲜村-基础设施-北港村村部排水渠道硬化及电排渠新建桥梁","新建","北港四组","2022-09-25","2022-10-25","乡村振兴局","渠道硬化\n长98米*2边2.2米/边*底宽1.5米\n新建桥梁\n 宽6米*长14米*高4.5米*厚50CM",20,20,null,null,0,1,10,26,0,0,0,"受益脱贫人口满意度≧98%","①完善村级基础设施，提高群众生产生活水平；\n②方便全村贫困户与非贫困户农业生产。",null,"省第二批沅振发〔2022〕9号",20,"沅财农指〔2022〕21号"]
[1,"产业发展","生产项目","种植业基地","茶盘洲镇","幸福村","沅江市茶盘洲镇幸福村经济合作社产业发展项目","新建","幸福村","2022-06-01","2022-11-01","乡村振兴局","建设生态实验田200亩",80,80,{"$nulls":3},1,77,175,1,77,175,"建设生态实验田200亩，由沅江市茶盘洲镇幸福村负责督促实施，实验田实行生物防治、物理驱虫保证水稻在生产周期内不打农药、不施化肥，保证完全绿色生态，完成周边必要的配套设施建设。项目建设完成后能够为幸福村的集体经济提供更好的后续保障，对生态环境的美化和幸福村集体经济发展提供更好发展的平台。合作社每年按过渡期内不低于8%的年利率对幸福村77户175人脱贫户、监测户进行保底分红，连续分红五年。","按过渡期内不低于8%的年利率进行保底收益，连续分红五年，五年之后，所有权收归幸福村所有。并且生态水稻实验田的种植过程中聘请脱贫户和监测户进行务工，增加其务工收入。从而构筑好“幸福村经济合作社+幸福村+脱贫户”的帮扶形式。",null,"中央第二批沅振发〔2022〕5号",80,"沅财农指〔2022〕8号"]
[2,"产业发展","配套设施项目","产业园（区）","茶盘洲镇","茶盘洲镇","沅江市茶盘洲镇万亩生态产业示范园宣传牌及农产品包装设计","新建","茶盘洲镇","2022-06-01","2022-11-01","乡村振兴局","（1）字牌，规格：大小3米*3米，14个字(钢架）。（2）宣传牌，规格：6米*3.5米。（3）粮食、水果包装的设计、生产。",25,25,{"$nulls":3},2,159,248,1,77,175,"（1）字牌，规格：大小3米*3米，14个字(钢架）。（2）宣传牌，规格：6米*3.5米。（3）粮食、水果包装的设计、生产。","政府+合作社+农户",null,"贫困农场",25,"沅财农指〔2022〕12号"]
[3,"产业发展","配套设施项目","产业园（区）","茶盘洲镇","茶盘洲镇","沅江市茶盘洲镇万亩生态产业示范园生态实验田配套设施","新建","茶盘洲镇","2022-06-01","2022-11-01","乡村振兴局","（1）200亩生态实验田增加简易钢丝网与围网，约600米长*200米宽*1米高（配围网），留6个可以进出机械车的门，3-4米宽（门可提开），设柱子（钢管）。（2）引进适用于200亩数量的赤眼蜂虫。（3）实验田安装4个摄像头，120度广角，太阳能供电，5G网卡（网费计入），内存卡可存半个月，立杆需出地面3.5米。",26,26,{"$nulls":3},1,77,175,1,77,175,"（1）200亩生态实验田增加简易钢丝网与围网，约600米长*200米宽*1米高（配围网），留6个可以进出机械车的门，3-4米宽（门可提开），设柱子（钢管）。（2）引进适用于200亩数量的赤眼蜂虫。（3）实验田安装4个摄像头，120度广角，太阳能供电，5G网卡（网费计入），内存卡可存半个月，立杆需出地面3.5米。","政府+合作社+农户",null,"贫困农场",26,"沅财农指〔2022〕12号"]
[4,"产业发展","配套设施项目","产业园（区）","茶盘洲镇","茶盘洲镇","沅江市茶盘洲镇万亩生态产业示范园辅助性配套设施项目","新建","茶盘洲镇","2022-06-01","2022-11-01","乡村振兴局","（1）采摘园的钢丝网，300长*100宽，丝径6.0mm及以上，类似高速路上斜雨棚钢构，1.8米以上高度，2张门，宽6-8米(门可拉开)，（2）采摘园安装4个摄像头，1个头，120度广角，太阳能供电，5G网卡(网费计入)，内存卡可存半个月，立杆需出地面5米。（3）金银花基地28.35亩，钢丝网1.5米高，钢丝网，配柱子(钢管)，1张门，3米宽。",24,24,{"$nulls":3},2,150,256,0,35,58,"（1）采摘园的钢丝网，300长*100宽，丝径6.0mm及以上，类似高速路上斜雨棚钢构，1.8米以上高度，2张门，宽6-8米(门可拉开)，（2）采摘园安装4个摄像头，1个头，120度广角，太阳能供电，5G网卡(网费计入)，内存卡可存半个月，立杆需出地面5米。（3）金银花基地28.35亩，钢丝网1.5米高，钢丝网，配柱子(钢管)，1张门，3米宽。","政府+合作社+农户",null,"贫困农场",24,"沅财农指〔2022〕12号"]
[5,"产业发展","配套基础设施项目","产业园（区）","茶盘洲镇","幸福村","沅江市茶盘洲镇幸福村经济合作社产业发展项目","新建","幸福村","2022-08-01","2022-11-01","幸福村","建设生态实验田配套基础设施项目",10,10,{"$nulls":3},1,77,175,1,77,175,"硬化产业路一条260米","方便合作社农产品的运输，带动群众致富。",null,"省第二批沅振发〔2022〕9号",10,"沅财农指〔2022〕14号"]
[6,"产业发展","配套基础设施项目","产业园（区）","茶盘洲镇","幸福村","沅江市茶盘洲镇幸福村经济合作社产业发展项目","改建","幸福村","2022-08-01","2022-11-01","幸福村","建设生态实验田配套基础设施项目",10,10,{"$nulls":3},1,77,175,1,77,175,"渠道清淤3000米","确保农产品旱涝保收"]
[1,"乡村建设行动","农村基础设施","农村道路建设","南洞庭中心","东头嘴社区","美丽村庄配套基础设施建设","改扩建","东头嘴社区","2022-08-01","2022-09-01","乡村振兴局","支路衬砌1000米，道路平整200米，主干路北方护肩1200米，美丽乡村其他配套设施建设",30,30,{"$nulls":3},1,570,1417,0,53,138,"群众满意度100%","①提高群众生产生活水平②便利群众出行③解决53户（其中监测户4户）的农产品运输问题④加强基础设施建设",null,"省第二批沅振发〔2022〕9号",30,"沅财农指〔2022〕13号"]
[2,"乡村建设行动","农村基础设施","产业路建设","南洞庭中心","永胜社区","一队生产路平整修复","改扩建","永胜社区","2022-08-01","2022-09-01","乡村振兴局","530米",5,5,{"$nulls":3},1,740,2536,0,92,192,"群众满意度100%","①提高群众生产生活水平②便利群众发展生产③解决92户脱贫户（其中监测户3户）的农产品运输问题",null,"省第二批沅振发〔2022〕9号",5,"沅财农指〔2022〕13号"]
[3,"乡村建设行动","农村基础设施","产业路建设","南洞庭中心","澎湖潭社区","新垸子生产路平整修复","改扩建","澎湖潭社区","2022-08-01","2022-09-01","乡村振兴局","800米",3,3,{"$nulls":3},1,21,98,0,9,24,"群众满意度100%","①提高群众生产生活水平②便利群众发展生产③解决21户（其中贫困户9户）的农产品运输问题",null,"省第二批沅振发〔2022〕9号",3,"沅财农指〔2022〕13号"]
[4,"乡村建设行动","农村基础设施","产业路建设","南洞庭中心","东头嘴社区","东头嘴社区渔场公路建设","改扩建","东头嘴社区","2022-06-01","2022-06-01","乡村振兴局","3000米",20,20,{"$nulls":3},1,62,200,0,9,24,"社会效益指标","①提高群众生产生活水平②便利群众出行③解决62户（其中贫困户9户）的农产品运输问题",null,"省第二批沅振发〔2022〕9号",20,"沅财农指〔2022〕13号"]
[1,"产业发展","生产项目","种植业基地","漉湖中心","武岗洲社区","湖南林旺丰茂苗木专业合作社","新建","武岗洲社区","2022-01-01","2022-12-01","农业农村局","苗木种植100亩",150,100,null,null,50,3,50,180,1,68,158,"群众满意度达96%","脱贫户增收"]
[2,"产业发展","生产项目","种植业基地","漉湖中心","漉湖社区","沅江市辉雨农业综合开发农民专业合作社区","新建","漉湖社区","2022-01-01","2022-12-01","农业农村局","食用菌种植50亩",100,75,null,null,25,2,40,100,1,57,124,"群众满意度达97%","脱贫户增收"]
[3,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","漉湖中心","武岗洲社区","五队机耕道硬化","新建","武岗洲社区","2022-09-01","2022-11-01","乡村振兴局","600米机耕道硬化",30,30,{"$nulls":3},2,50,456,2,30,98,"提高群众满意度","提升群众生产生活条件"]
[4,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","漉湖中心","武岗洲社区","七队主渠道路硬化","新建","武岗洲社区","2022-10-01","2022-12-01","乡村振兴局","600米主渠道路硬化",22,22,{"$nulls":3},2,68,159,2,20,80,"群众满意度达96%","便利群众出行"]
[5,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","漉湖中心","漉湖社区","漉湖社区1.3.4.5.6.7.8.9队沟渠疏洗","农田水利","漉湖社区","2022-12-01","2023-06-01","乡村振兴局","4500米沟渠疏洗",25,25,{"$nulls":3},2,169,1200,2,57,124,"提高群众满意度","提升群众生产生活条件"]
[6,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","漉湖中心","漉湖社区","漉湖社区3-8队农田道路硬化","新建","漉湖社区","2022-10-01","2022-11-01","乡村振兴局","农田道路硬化1300米",48,48,{"$nulls":3},2,169,1200,2,57,124,"提高群众满意度","提升群众生产生活条件"]
[7,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","漉湖中心","渔业社区","渔业社区1.2.4.5.6队沟渠疏洗","农田水利","渔业社区六队","2022-09-01","2022-10-01","乡村振兴局","沟渠疏洗800米",12,12,{"$nulls":3},1,156,442,1,25,46,"提高群众满意度","提升群众生产生活条件"]
[8,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","漉湖中心","渔业社区","渔业社区1.5队公路硬化","新建","渔业社区","2022-06-01","2022-07-01","乡村振兴局","1至5队通村公路硬化1000米",5,5,{"$nulls":3},1,20,60,1,25,46,"提高群众满意度","提升群众生产生活条件，方便群众出行",null,"省第二批沅振发〔2022〕9号",5,"沅财农指〔2022〕13号"]
[9,"产业发展","生产项目","种植业基地","漉湖中心","合兴洲","合兴洲新盛生态农业专业合作社","扩建","合兴洲社区","2022-06-01","2022-06-01","农业农村局","生态产业园发展",50,50,{"$nulls":3},1,320,1693,1,119,336,"提高群众满意度","脱贫户增收",null,"中央第二批沅振发〔2022〕5号",50,"沅财农指〔2022〕8号"]
[10,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","漉湖中心","合兴洲","村组公路硬化拓宽及配套设施建设","新建","合兴洲社区","2022-06-01","2022-06-01","乡村振兴局","公路拓宽及附属设施建设80米宽，停车场320平方米",16,16,{"$nulls":3},1,320,1693,1,109,311,"提高群众满意度","提升群众生产生活条件，方便群众出行",null,"中央第二批沅振发〔2022〕5号",16,"沅财农指〔2022〕8号"]
[11,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","漉湖中心","合兴洲","合兴洲3、4队一排渠道路拓宽和配套设施建设","新建","合兴洲社区","2022-08-01","2022-09-01","乡村振兴局","合兴洲3、4队一排渠道路拓宽和配套设施建设700米",14,14,{"$nulls":3},1,320,1693,1,109,311,"提高群众满意度","提升群众生产生活条件，方便群众出行",null,"省第二批沅振发〔2022〕9号",14,"沅财农指〔2022〕13号"]
[12,"产业发展","生产项目","加工流通","漉湖中心","柴下洲社区","沅江市顺旺生态农业发展有限公司","新建","柴下洲社区五队","2022-11-01","2022-12-01","农业农村局","芦笋、藜蒿、芹菜加工，坛子菜加工700平方米",200,150,null,null,50,2,256,900,2,58,131,"提高群众满意度","脱贫户增收"]
[1,"乡村建设行动","农村基础设施","农村供水保障设施建设","南嘴镇","兴南村、百家沟村","南嘴镇兴南村、百家沟村-基础设施-南嘴镇农村自来水厂新增水源工程","新建","兴南村、百家沟村","2022-07-01","2022-12-01","水利局","新钻2口水源井及取水机电设备购安",41.6,41.6,{"$nulls":3},8,5954,20840,2,604,1292,"保障水厂用水户（包括脱贫户）的饮水安全。","群众参与"]
[2,"乡村建设行动","农村基础设施","农村供水保障设施建设","胭脂湖街道","赤塘村、海上社区、莲子塘村","胭脂湖街道赤塘村、海上社区、莲子塘村-基础设施-胭脂湖街道农村自来水厂新增水源工程","新建","赤塘村、海上社区、莲子塘村","2022-06-01","2022-08-01","水利局","新钻4口水源井及取水机电设备购安，其中海上社区的变压机增容（原50KVA增至100KVA)",103.7,103.7,{"$nulls":3},15,14560,50967,2,802,2004,"保障水厂用水户（包括脱贫户）的饮水安全。","群众参与"]
[3,"乡村建设行动","农村基础设施","农村供水保障设施建设","新湾镇","新湾村、老屋冲村","新湾镇新湾村、老屋冲村-基础设施-新湾镇农村自来水厂新增水源工程","新建","新湾村、老屋冲村","2022-07-01","2022-12-01","水利局","新钻2口水源井。其中1口水井出水量80吨/小时、深度95米，1口水井出水量70吨/小时、深度90米。",54.95,54.95,{"$nulls":3},7,6766,23679,1,442,1033,"保障水厂用水户（包括脱贫户）的饮水安全。","群众参与"]
[4,"乡村建设行动","农村基础设施","农村供水保障设施建设","草尾镇","新安村、长乐村","草尾镇新安-基础设施-留余堂水厂新增水源及长乐村管网改造工程","新建","新安村、长乐村","2022-08-01","2022-11-01","水利局","新钻1口水源井及取水机电设备购安，铺设铺设PE管网6.82千米。",78.8,78.8,{"$nulls":3},12,12531,43860,0,962,2412,"保障水厂用水户（包括脱贫户）的饮水安全。","群众参与"]
[5,"乡村建设行动","农村基础设施","农村供水保障设施建设","黄茅洲镇","肖家坝村","黄茅洲镇肖家坝村-基础设施-志成水厂新增水源工程","新建","肖家坝村","2022-07-01","2022-12-01","水利局","新钻1口水源井及取水机电设备购安",22,22,{"$nulls":3},6,9058,31705,0,606,1466,"保障水厂用水户（包括脱贫户）的饮水安全。","群众参与"]
[6,"乡村建设行动","农村基础设施","农村供水保障设施建设","泗湖山镇","朱冯村、净下洲村","泗湖山镇朱冯村、净下洲村-基础设施-泗湖山镇农村自来水厂新增水源工程","新建","朱冯村、净下洲村","2022-08-01","2022-12-01","水利局","新钻2口水源井及取水机电设备购安",41.6,41.6,{"$nulls":3},4,6723,16809,1,368,701,"保障水厂用水户（包括脱贫户）的饮水安全。","群众参与"]
[7,"乡村建设行动","农村基础设施","农村供水保障设施建设","南大膳镇","华胜村、同丰垸村","南大膳镇华胜村--基础设施-小波水厂新建清水池及同丰垸村管网改造工程","新建","华胜村、同丰垸村","2022-08-01","2022-12-01","水利局","新建一个清水池，铺设PE管网6.73千米。",129.3,129.3,{"$nulls":3},3,3820,10450,1,520,2000,"保障水厂用水户（包括脱贫户）的饮水安全。","群众参与"]
[8,"乡村建设行动","农村基础设施","农村供水保障设施建设","茶盘洲镇","社区、新华村","茶盘洲镇社区-基础设施-民生自来水厂新增水源工程及新华村管网改造工程","新建","社区、新华村","2022-08-01","2022-11-01","水利局","新钻1口水源井及取水机电设备购安，铺设铺设PE管网5.2千米。",66.5,66.5,{"$nulls":3},10,5420,27800,2,317,674,"保障水厂用水户（包括脱贫户）的饮水安全。","群众参与"]
[9,"乡村建设行动","农村基础设施","农村供水保障设施建设","琼湖街道","实竹社区、榨南村","琼湖街道实竹社区、榨南村-基础设施-琼湖街道农村自来水厂新增水源工程","新建","实竹社区、榨南村","2022-08-01","2022-12-01","水利局","新钻2口水源井及取水机电设备购安",38.5,38.5,{"$nulls":3},2,1342,4700,0,77,193,"保障水厂用水户（包括脱贫户）的饮水安全。","群众参与"]
[10,"乡村建设行动","农村基础设施","农村供水保障设施建设","四季红镇","长征村","四季红镇长征村-基础设施-四季红镇二水厂长征村管网改造工程","新建","长征村","2022-08-01","2022-12-01","水利局","铺设PE管网5.7千米。",40.84,40.84,{"$nulls":3},1,567,1986,0,35,94,"保障水厂用水户（包括脱贫户）的饮水安全。","群众参与"]
[11,"乡村建设行动","农村基础设施","农村供水保障设施建设","南大膳镇","牛洲村、北大村、同丰垸村、南渔口村、西福垸村、南大河村、大东口村、小康村","2022年小水源供水能力恢复建设","恢复","南大膳镇","2022-04-01","2022-12-01","水利局","对39处塘堰内淤泥、砂石和垃圾进行清除",218.79,78,null,null,140.79,8,39,137,{"$nulls":3},"增加蓄水容积，恢复供水能力","群众参与",null,400,78,"沅财农指〔2022〕20号"]
[12,"乡村建设行动","农村基础设施","农村供水保障设施建设","黄茅洲镇","群红村、黄粟塘村、新河口村、民心村、子母城村","2022年小水源供水能力恢复建设","恢复","黄茅洲镇","2022-04-01","2022-12-01","水利局","对19处塘堰内淤泥、砂石和垃圾进行清除",105.06,38,null,null,67.06,5,19,67,{"$nulls":3},"增加蓄水容积，恢复供水能力","群众参与",null,400,38,"沅财农指〔2022〕20号"]
[13,"乡村建设行动","农村基础设施","农村供水保障设施建设","草尾镇","人益村、东义村、立新村、熙福村","2022年小水源供水能力恢复建设","恢复","草尾镇","2022-04-01","2022-12-01","水利局","对15处塘堰内淤泥、砂石和垃圾进行清除",81.1,30,null,null,51.1,4,15,53,{"$nulls":3},"增加蓄水容积，恢复供水能力","群众参与",null,400,30,"沅财农指〔2022〕20号"]
[14,"乡村建设行动","农村基础设施","农村供水保障设施建设","阳罗洲镇","大中村、东新村、俩仪村、富安村","2022年小水源供水能力恢复建设","恢复","阳罗洲镇","2022-04-01","2022-12-01","水利局","对8处塘堰内淤泥、砂石和垃圾进行清除",43.43,16,null,null,27.43,4,8,28,{"$nulls":3},"增加蓄水容积，恢复供水能力","群众参与",null,400,16,"沅财农指〔2022〕20号"]
[15,"乡村建设行动","农村基础设施","农村供水保障设施建设","四季红镇","玉鹊村","2022年小水源供水能力恢复建设","恢复","四季红镇","2022-04-01","2022-12-01","水利局","对2处塘堰内淤泥、砂石和垃圾进行清除",12.44,4,null,null,8.44,1,2,7,{"$nulls":3},"增加蓄水容积，恢复供水能力","群众参与",null,400,4,"沅财农指〔2022〕20号"]
[16,"乡村建设行动","农村基础设施","农村供水保障设施建设","漉湖","渔业管区","2022年小水源供水能力恢复建设","恢复","漉湖","2022-04-01","2022-12-01","水利局","对2处塘堰内淤泥、砂石和垃圾进行清除",10.51,4,null,null,6.51,1,2,7,{"$nulls":3},"增加蓄水容积，恢复供水能力","群众参与",null,400,4,"沅财农指〔2022〕20号"]
[17,"乡村建设行动","农村基础设施","农村供水保障设施建设","南洞庭","东头咀村、南洞庭渔场","2022年小水源供水能力恢复建设","恢复","南洞庭","2022-04-01","2022-12-01","水利局","对3处塘堰内淤泥、砂石和垃圾进行清除",16.72,6,null,null,10.72,2,3,11,{"$nulls":3},"增加蓄水容积，恢复供水能力","群众参与",null,400,6,"沅财农指〔2022〕20号"]
[18,"乡村建设行动","农村基础设施","农村供水保障设施建设","泗湖山镇","东安垸村、坪头岭村、中和村、华红村","2022年小水源供水能力恢复建设","恢复","泗湖山镇","2022-04-01","2022-12-01","水利局","对15处塘堰内淤泥、砂石和垃圾进行清除",89.7,30,null,null,59.7,4,15,53,{"$nulls":3},"增加蓄水容积，恢复供水能力","群众参与",null,400,30,"沅财农指〔2022〕20号"]
[19,"乡村建设行动","农村基础设施","农村供水保障设施建设","共华镇","明月村","2022年小水源供水能力恢复建设","恢复","共华镇","2022-04-01","2022-12-01","水利局","对8处塘堰内淤泥、砂石和垃圾进行清除",41.99,16,null,null,25.99,1,8,28,{"$nulls":3},"增加蓄水容积，恢复供水能力","群众参与",null,400,16,"沅财农指〔2022〕20号"]
[20,"乡村建设行动","农村基础设施","农村供水保障设施建设","茶盘洲镇","玉竹村","2022年小水源供水能力恢复建设","恢复","茶盘洲镇","2022-04-01","2022-12-01","水利局","对3处塘堰内淤泥、砂石和垃圾进行清除",16,6,null,null,10,1,3,11,{"$nulls":3},"增加蓄水容积，恢复供水能力","群众参与",null,400,6,"沅财农指〔2022〕20号"]
[21,"乡村建设行动","农村基础设施","农村供水保障设施建设","胭脂湖街道","回龙山村、莲子塘村、洞兴村、南竹山村、三眼塘村、焦山咀村、先锋村","2022年小水源供水能力恢复建设","恢复","胭脂湖街道","2022-04-01","2022-12-01","水利局","对34处塘堰内淤泥、砂石和垃圾进行清除",187.5,68,null,null,119.5,7,34,119,{"$nulls":3},"增加蓄水容积，恢复供水能力","群众参与",null,400,68,"沅财农指〔2022〕20号"]
[22,"乡村建设行动","农村基础设施","农村供水保障设施建设","琼湖街道","保民村、杨泗桥、榨南村、九枳村、百乐村","2022年小水源供水能力恢复建设","恢复","琼湖街道","2022-04-01","2022-12-01","水利局","对17处塘堰内淤泥、砂石和垃圾进行清除",90.82,34,null,null,56.82,5,17,60,{"$nulls":3},"增加蓄水容积，恢复供水能力","群众参与",null,400,34,"沅财农指〔2022〕20号"]
[23,"乡村建设行动","农村基础设施","农村供水保障设施建设","新湾镇","莲花村、老屋冲村、桥北村、新湾村","2022年小水源供水能力恢复建设","恢复","新湾镇","2022-04-01","2022-12-01","水利局","对16处塘堰内淤泥、砂石和垃圾进行清除",84.07,32,null,null,52.07,4,16,56,{"$nulls":3},"增加蓄水容积，恢复供水能力","群众参与",null,400,32,"沅财农指〔2022〕20号"]
[24,"乡村建设行动","农村基础设施","农村供水保障设施建设","南嘴镇","百家沟村、南嘴村、蠡山村、兴南村、目南村","2022年小水源供水能力恢复建设","恢复","南嘴镇","2022-04-01","2022-12-01","水利局","对19处塘堰内淤泥、砂石和垃圾进行清除",103.19,38,null,null,65.19,5,19,67,{"$nulls":3},"增加蓄水容积，恢复供水能力","群众参与",null,400,38,"沅财农指〔2022〕20号"]
[1,"产业发展项目","生产项目","种植业基地","泗湖山镇","朱冯村","沅江市冯鑫农业开发有限公司\n优质稻初加工及稻虾生产基地建设项目","新建","泗湖山镇朱冯村","2022-09-01","2023-09-01","农业农村局","1、550亩优质稻品种改良2、购买农业生产机械设备。3、600m衬彻渠修整、600m二级田间道修建。4、4组30吨粮食烘干机组、80吨干谷钢板中转仓。5、立柱式广告宣传牌",129.6,100,null,null,29.6,1,111,142,null,43,74,"帮扶带动66人脱贫户和监测对象参与发展产业，带动30人就业务工，项目建成后增加优质稻烘干产能2000吨，优质稻增产275吨，提高销售收入102.5万元，预计可带动脱贫户及监测对象74人增收，其中带动监测户13人人均增收1500元。","务工就业发放工资报酬、提供种子种苗、提供生产技术服务、产品保底回收、生产托管固定收益、资产折股量化入股分红",null,"省重点产业",100,"沅财农指〔2022〕19号"]
[2,"产业发展项目","生产项目","种植业基地","新湾镇","老屋冲村","沅江市芦小妹食品有限公司\n沅江芦笋、芦菇培育研发标准化生产基地建设项目","新建","新湾镇老屋冲村","2022-09-01","2023-09-01","农业农村局","1.芦菇地窖恒温培育室及设施；2.室内多层芦菇培育架。3.一体式芦苇秸秆粉碎机、全自动喷淋系统。4.宣传册设计及制作 、广告投放等。",137.3,100,null,null,37.3,1,66,92,null,41,41,"直接帮扶26人脱贫户和监测对象参与发展产业，带动36人就业务工，项目建成后增加芦菇产量5吨，提高销售收入100万元，预计带动脱贫户及监测对象41人增收，可为监测户13人均增收3000元。","务工就业发放工资报酬、提供种子种苗、提供生产技术服务、产品保底回收、生产托管固定收益、资产折股量化入股分红",null,"省重点产业",100,"沅财农指〔2022〕19号"]
[3,"产业发展项目","生产项目","种植业基地","草尾镇","和平村","沅江市爱钦优质水稻种养专业合作社\n稻稻虾生态种养基地建设项目","新建","草尾镇和平村","2022-09-01","2023-09-01","农业农村局","1、小龙虾品种更新 ；                             2、稻虾田基地改建；\n3、农机添置：抛秧机一台\n4、修建200立方米冷库、小龙虾分拣厂房建设。",31,25,null,null,6,1,38,69,1,17,31,"直接帮扶26人脱贫户和监测对象参与发展产业，带动13人就业务工，项目建成后增加小龙虾产量15吨，优质稻80吨，提高销售收入55万元，预计带动脱贫户及监测对象31人增收，带动监测户10人均增收1500元。","务工就业发放工资报酬、提供种子种苗、提供生产技术服务、生产产品保底回收、生产托管固定收益、资产折股量化入股分红",null,"省重点产业",25,"沅财农指〔2022〕19号"]
[4,"产业发展项目","生产项目","种植业基地","草尾镇","四民村","沅江市草尾顺丰圆蔬菜种植专业合作社\n稻虾综合种养及销售平台建设项目","新建","草尾镇四民村","2022-09-01","2023-09-01","农业农村局","1、聘请专家进行稻虾养殖技术指导。2、优质稻、龙虾品种改良。3、新建稻虾生态养殖基地60亩。4、购买定制手工精准化挑选工作台8套.5、增加200立方米冻库一座。6、打造专属广告牌，打造品牌。7、拓展小龙虾排污体系，完善排污措施",32,25,null,null,7,1,57,65,null,17,25,"直接帮扶21人脱贫户和监测对象参与发展产业，带动20人就业务工，项目建成后增加成虾产量20吨，提高销售收入40万元，预计可为脱贫户及监测户25人增收，其中带动监测户10人人均增收3000元。","务工就业发放工资报酬、提供种子种苗、提供生产技术服务、产品保底回收、生产托管固定收益、资产折股量化入股分红",null,"省重点产业",25,"沅财农指〔2022〕19号"]
[5,"产业发展项目","生产项目","种植业基地","南大膳镇","众兴村","沅江市南大细刚稻虾种养专业合作社\n稻虾综合种养项目","新建","南大膳镇众兴村","2022-09-01","2023-09-01","农业农村局","1.水稻改良和龙虾优质品种改良。2、稻虾基地基础设施建设。3、基地供水设备。4、田间道路提质1000米。5、优质大米，小龙虾品牌打造。6、植保无人机",30,25,null,null,5,1,23,33,null,9,14,"直接帮扶11人脱贫户和监测对象参与发展产业，带动11人就业务工，项目建成后增加水稻产量40吨，龙虾增加产量15吨，提高销售收入42万元，预计可带动脱贫户及监测户14人增收，其中带动监测户3人人均增收2600元。","务工就业发放工资报酬、提供种子种苗、提供生产技术服务、产品保底回收、生产托管固定收益、资产折股量化入股分红",null,"省重点产业",25,"沅财农指〔2022〕19号"]
[6,"产业发展项目","生产项目","种植业基地","共华镇","新港村","沅江市迪科牧业养殖专业合作社\n稻虾渔综合种养项目","新建","共华镇新港村","2022-09-01","2023-09-01","农业农村局","1、小龙虾品种改良2、基地开挖、规格成箱，修整渠道、供水设施；                                                       \n3、智能化增氧机、稻虾苗种培育池；                                                 4、新建75平方米冷库。5、宣传广告牌",34.13,25,null,null,9.13,1,28,40,null,9,17,"直接帮扶带动15人脱贫户和监测对象参与发展产业，带动15人就业务工，项目建成后增加小龙虾产量15吨，优质稻75吨，提高销售收入50万元，预计可带动脱贫户或监测对象17人增收，其中监测户5人人均增收2550元。","务工就业发放工资报酬、提供种子种苗、提供生产技术服务、产品保底回收、生产托管固定收益、资产折股量化入股分红",null,"省重点产业",25,"沅财农指〔2022〕19号"]
[7,"产业发展项目","生产项目","养殖业基地","阳罗洲镇","跃进村","沅江市绿硒园特种水产养殖专业合作社\n优质稻+小龙虾（罗氏沼虾）养殖科技示范项目","新建","阳罗洲镇跃进村","2022-09-01","2023-09-01","农业农村局","1、优质种苗引进。2、虾苗培育示范塘建设、基地供电设备升级（安装专供电变压器）。3、实验塘增氧设备。4、产品销售直播平台及直播间建设。5、品牌宣传及产品推荐。6、基地道路提质",32,25,null,null,7,1,44,83,null,20,39,"直接帮扶36人脱贫户和监测对象参与发展产业，带动7人就业务工，项目建成后增加稻虾（小龙虾+罗氏沼虾）产量12吨，提高销售收入60万元，预计可带动脱贫户及监测户39人增收，其中监测户13人人均增收10000元。","务工就业发放工资报酬、提供种子种苗、提供生产技术服务、产品保底回收、生产托管固定收益、资产折股量化入股分红",null,"省重点产业",25,"沅财农指〔2022〕19号"]
[8,"产业发展项目","生产项目","种植业基地","共华镇","双阜村","沅江市长进水稻专业合作社\n菇稻菇基地建设项目","新建","共华镇双阜村","2022-09-01","2023-09-01","农业农村局","1、引进15亩菌种，聘请专家进行技术培训；2、新建30个大棚；3、大棚喷灌设施、电机+增压泵、简易机耕道维修。4、菇稻菇广告牌制作5、.完善排灌排污设施。",35,25,null,null,10,1,21,66,1,12,28,"直接帮扶 20个脱贫户和监测对象参与发展产业，带动20人就业务工，项目建成后增加芦菇产量22.5吨，优质稻62吨，提高销售收入65万元，预计可带动脱贫户或监测对象28人增收，其中监测户 6人，人均增收2800元。","务工就业发放工资报酬、提供种子种苗、提供生产技术服务、产品保底回收、生产托管固定收益、资产折股量化入股分红",null,"省重点产业",25,"沅财农指〔2022〕19号"]
[1,"产业发展项目","配套基础设施项目","小型农田水利设施建设","胭脂湖街道","南竹山村","渠道疏通","新建","南竹山村","2022-07-01","2022-09-01","民政局","1000米",7,7,{"$nulls":3},1,160,400,0,10,27,"促进农业经济发展，带动农户增收增产，公司积极发展生产，开拓市场，指导农户参与分享收益，带动乡村振兴和周边农民脱贫致富增收","1、解决积水，使农田增产增收\n 2、带动务工就业",null,"老区发展",7,"沅财农指〔2022〕7号"]
[2,"乡村建设行动","农村基础设施","其他","泗湖山镇","中和村","渠道疏浚","新建","中和村3-6组","2022-04-01","2022-04-01","民政局","渠道疏浚1300米",5,5,{"$nulls":3},1,30,51,0,4,11,"改善生产条件同，促进农业经济发展，带动农户增收增产","提高群众生产生活水平",null,"老区发展",5,"沅财农指〔2022〕7号"]
[3,"产业发展项目","生产项目","养殖业基地","阳罗洲镇","宝三村","特色养殖","品种改良","宝三村","2022-03-01","2022-04-01","民政局","品种改良200亩",100,5,null,null,95,1,7,22,1,3,7,"增加群众与村集体经济收入","1、增产增收\n2、带动务工就业",null,"老区发展",5,"沅财农指〔2022〕7号"]
[4,"乡村建设行动","农村基础设施建设","农村道路建设（通村、通户路）","新湾镇","新湾村","道路硬化","新建","新湾村新湾组","2022-05-01","2022-06-01","民政局","100米",6,5,null,null,1,1,39,87,0,8,20,"方便出行，改善生产条件促进农业经济发展，带动农户增收增产","1、提高群众生产生活水平\n2、便利群众出行",null,"老区发展",5,"沅财农指〔2022〕7号"]
[1,"乡村建设行动","农村基础设施","农村道路建设","草尾镇","熙福村","熙福村村级公路建设项目","新建","草尾镇熙福村","2022-05-01","2022-06-01","发改局","新建村组公路1公里",40,10,null,null,30,1,398,1563,0,133,378,"改善项目区生产条件，促进农业经济发展，带动农户增收增产","促进群众就地就近就业，并获得劳务报酬。",null,"以工代赈",10,"沅财农指〔2022〕10号"]
[2,"乡村建设行动","农村基础设施","农村道路建设","草尾镇","乐园村","乐园村村级公路建设项目","新建","草尾镇乐园村","2022-05-01","2022-06-01","发改局","新建村组公路0.5公里",23,10,null,null,13,1,210,712,0,6,16,"改善项目区生产条件，促进农业经济发展，带动农户增收增产","促进群众就地就近就业，并获得劳务报酬。",null,"以工代赈",10,"沅财农指〔2022〕10号"]
[3,"乡村建设行动","农村基础设施","农村道路建设","泗湖山镇","华星村","华星村村级公路建设项目","改建","泗湖山镇华星村","2022-05-01","2022-06-01","发改局","改建村组公路1.5公里",20,10,null,null,10,1,18,46,0,6,14,"改善项目区生产条件，促进农业经济发展，带动农户增收增产","促进群众就地就近就业，并获得劳务报酬。",null,"以工代赈",10,"沅财农指〔2022〕10号"]
[4,"乡村建设行动","农村基础设施","农村道路建设","南大膳镇","牛洲村","牛洲村村级公路建设项目","改扩建","南大膳镇牛洲村","2022-05-01","2022-06-01","发改局","改建村组公路2公里",6.2,5,null,null,1.2,1,63,215,0,12,28,"改善项目区生产条件，促进农业经济发展，带动农户增收增产","促进群众就地就近就业，并获得劳务报酬。",null,"以工代赈",5,"沅财农指〔2022〕10号"]
[5,"易地搬迁后扶","易地搬迁后扶","社区综合服务设施建设","草尾镇、琼湖街道等5镇","草尾镇镇区、榨南湖村等","易地搬迁集中安置区配套基础设施建设","新建","草尾、琼湖等镇（街道、中心）","2022-08-01","2022-09-01","发改局","新建电动自行车停车棚1个、3个电动自行车集中充电装置及安置点房屋维修等",21,21,{"$nulls":3},3,186,561,0,186,561,"完善安置点配套基础设施，提高搬迁群众满意度","为搬迁群众营造良好的生产生活氛围，促进搬迁群众社会融入",null,"沅振发〔2022〕5号",21,"沅财农指〔2022〕11号"]
[1,"乡村建设行动","农村基础设施","高标准农田建设","黄茅洲镇等10镇、街道","28个村","沅江市2022年高标准农田建设项目","续建","沅江市","2022-10-25","2023-03-30","沅江市农业农村局","建设高标准农田3.44万亩",330,330,{"$nulls":3},28,21392,51372,0,0,0,"项目区直接受益农民年纯收入增加100元","吸纳项目区劳动务工",null,568,330,"沅财农指〔2022〕18号"]
[2,"产业发展项目","金融保险配套项目","新型经营主体贷款贴息","沅江市","沅江市","2021年新型农业经营主体货款贴息项目","续建","沅江市","2022-10-25","2022-10-25","沅江市农业农村局","新型农业经营主体货款贴息",188,188,{"$nulls":3},0,102,0,0,0,0,"吸纳项目区劳动务工","吸纳项目区劳动务工",null,568,188,"沅财农指〔2022〕18号"]
[3,"产业发展项目","产业服务支撑项目","新型农业经营主体培育","沅江市","沅江市","百企培育","新建","沅江市","2022-10-25","2022-10-25","沅江市农业农村局","支持1个千企帮村企业、1个小升规培育企业",50,50,{"$nulls":3},"2个企业",0,0,0,0,0,"培育新型农业经营主体，推进乡村振兴。","吸纳项目区劳动务工",null,568,50,"沅财农指〔2022〕18号"]
[4,"乡村建设行动","人居环境整治","农村垃圾治理","14个镇（街道、中心）","178个村（社区）","农村生活垃圾治理服务外包项目1、2","新建","胭脂湖街道、琼湖街道、新湾镇、南嘴镇、草尾镇、黄茅洲镇、四季红镇、南大膳镇、漉湖事务中心、共华镇、泗湖山镇、茶盘洲镇、南洞庭事务中心共178个村（管区、社区）","2022-01-01","2022-10-01","农业农村局","农村生活垃圾治理项目建设",580,580,null,null,0,178,96337,289013,29,12208,28664,"农村生活垃圾处理率、保洁覆盖率均达100%。","群众参与",null,"人居环境",580,"沅财农指〔2022〕25号"]
[5,"乡村建设行动","人居环境整治","农村垃圾治理","14个镇（街道、中心）","169个行政村（社区\n）","农村生活垃圾治理服务外包项目1、2","新建","胭脂湖街道、琼湖街道、新湾镇、南嘴镇、草尾镇、黄茅洲镇、四季红镇、南大膳镇、漉湖事务中心、共华镇、泗湖山镇、茶盘洲镇、南洞庭事务中心","2022-01-01","2022-12-01","农业农村局","农村人居环境整治提质升级项目",300,300,null,null,0,169,96330,289013,29,12208,28664,"农村生活垃圾处理率、保洁覆盖率均达100%。","群众参与",null,"人居环境",300,"沅财农指〔2022〕24号"]
[6,"乡村建设行动","人居环境整治","农村垃圾治理","14个镇（街道、中心）","169个行政村（社区\n）","农村生活垃圾治理服务外包项目1、2","新建","胭脂湖街道、琼湖街道、新湾镇、南嘴镇、草尾镇、黄茅洲镇、四季红镇、南大膳镇、漉湖事务中心、共华镇、泗湖山镇、茶盘洲镇、南洞庭事务中心共169个村（社区）","2022-03-01","2022-12-01","农业农村局","农村人居环境整治提质升级项目",607,607,null,null,0,169,96330,289013,29,12208,28664,"农村生活垃圾处理率、保洁覆盖率均达100%。","群众受益",null,"人居环境",607]