{"text_format":"3","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"defined_names":3},"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":106,"n_cols":27,"rows_kept":106,"merged":[[0,0,0,1],[1,0,1,26],[3,0,3,26],[5,0,7,0],[5,1,5,3],[5,4,7,4],[5,5,7,5],[5,6,7,6],[5,7,7,7],[5,8,7,8],[5,9,5,10],[5,11,7,11],[5,12,7,12],[5,13,5,17],[5,18,5,23],[5,24,7,24],[5,25,7,25],[5,26,7,26],[6,1,7,1],[6,2,7,2],[6,3,7,3],[6,9,7,9],[6,10,7,10],[6,13,7,13],[6,14,6,17],[6,18,7,18],[6,19,7,19],[6,20,7,20],[6,21,6,23]]}
["附件2"]
["沅江市2023年度巩固拓展脱贫攻坚成果和乡村振兴项目库动态调整项目申报表"]
[]
["单位：（盖章）                                                                                                                                                                                                                      时间：20XX年X月X日"]
[]
["序号","项目类别",null,null,"乡","村","项目名称","建设性质","实施地点","时间进度",null,"责任单位","建设内容及规模","资金规模和筹资方式",{"$nulls":4},"受益对象",{"$nulls":5},"绩效目标","联农带农机制","备注"]
[null,"项目类型","二级项目类型","项目子类型",{"$nulls":5},"计划开工时间","计划完工时间",null,null,"项目预算总投资（万元）","其中",{"$nulls":3},"受益村数（个）","受益户数（户）","受益人口数（人）","其中"]
[{"$nulls":14},"财政衔接资金（万元）","除财政衔接资金外的统筹整资金（万元）","其他财政资金（万元）","其他筹措资金（万元）",{"$nulls":3},"受益脱贫村数（个）","受益脱贫户数及防止返贫监测对象户数（户）","受益脱贫人口数及防止返贫监测对象人口数（人）"]
[29,"产业发展","配套设施项目","配套设施项目","琼湖街道","小河咀村","琼湖街道2023年小河咀村生态养殖基地产业配套设施建设","新建","小河咀村","2023-04-01","2023-06-01","小河咀村","54亩鱼塘护坡清淤，基地产业配套建设",{"$f":"O9+P9+Q9+R9","v":30},30,null,null,0,1,38,90,0,27,58,"完成建设规划内容","提高群众生活水平"]
[30,"产业发展","配套设施项目","配套设施项目","琼湖街道","九只树村","琼湖街道2023年九只树村经济合作社产业园区配套设施建设","新建","九只树村","2023-03-01","2023-05-01","九只树村","产业园区配套建设",{"$f":"O10+P10+Q10+R10","v":50},50,null,null,0,1,63,142,1,53,124,"完成建设规划内容","通过产业分红和用工用劳"]
[31,"乡村建设行动","农村基础设施","小型农田水利设施","琼湖街道","保民村","琼湖街道2023年保民村渠道建设","新建","保民村","2023-11-01","2023-12-01","保民村","500米抗旱渠硬化建设",10,10,null,null,0,1,108,272,1,106,268,"完成既定目标","提高群众生活水平"]
[32,"乡村建设行动","农村基础设施","小型农田水利设施","琼湖街道","管竹山村","琼湖街道2023年管竹山村渠道疏浚","新建","管竹山村","2023-05-01","2023-08-01","管竹山村","南边五组迎宾桥至北边二组桥边1200米渠道疏浚",5,5,null,null,0,1,35,82,1,33,78,"完成既定目标","提高群众生活水平"]
[10,"产业发展","配套基础设施项目","小型农田水利设施建设","胭脂湖街道","赤塘村","梁家坝引水渠维修建设","改建","赤塘村15组","2023-03-10","2023-04-30","乡村振兴局","梁家坝引水渠提质改造",10,10,null,null,0,1,914,2644,0,56,142,"便于农业生产，农田灌溉，为群众增收","1、带动地方产业发展\n2、满足群众农业灌溉用水需求\n3、提高群众生产生活水平"]
[11,"产业发展","配套基础设施项目","小型农田水利设施建设","胭脂湖街道","南竹山村","南竹山村山塘改造","新建","南竹山村","2023-03-10","2023-04-30","乡村振兴局","南竹山村产业园山塘改造，清淤、护坡10亩",25,25,null,null,0,1,1061,3099,0,47,141,"山塘改造，便于蓄水抗旱，增产增收","1、带动地方产业发展\n2、新增就业岗位3、打造红色观光产业园"]
[12,"产业发展","生产项目","种植业基地","胭脂湖街道","南竹山村","柑桔品改","新建","南竹山村","2023-03-10","2023-04-20","乡村振兴局","南竹山村7组40亩柑桔品改",20,20,null,null,0,1,1061,3099,0,47,141,"改良品种，增产增收","1、带动地方产业发展\n2、新增就业岗位3、打造红色观光产业园"]
[13,"产业发展","配套基础设施项目","小型农田水利设施建设","胭脂湖街道","洞兴村","洞兴村山塘改造","改建","洞兴村","2023-03-01","2023-04-10","乡村振兴局","洞兴村山塘改造，清淤、护坡22亩",10,10,null,null,0,1,210,720,0,5,13,"山塘改造，便于蓄水抗旱，增产增收","1、带动地方产业发展\n2、满足群众农业灌溉用水需求\n3、提高群众生产生活水平"]
[14,"产业发展","配套基础设施项目","小型农田水利设施建设","胭脂湖街道","三眼塘村","三眼塘村后里冲山塘护坡","新建","三眼塘村1组","2023-02-20","2023-03-28","乡村振兴局","山塘护坡",5,5,null,null,0,1,73,219,0,5,10,"提高群众生产生活质量，便利群众灌溉。","受益73户219人，农田灌溉43亩。"]
[15,"乡村建设行动","农村基础设施","农村道路建设","胭脂湖街道","胭脂湖村","胭脂湖村路基拓宽项目","扩建","胭脂湖村5组","2023-03-01","2023-03-30","乡村振兴局","拓宽路基200米",8,8,null,null,0,1,120,650,0,60,151,"方便群众生产生活，达到增收致富","①提高群众生产生活水平\n②便利群众出行"]
[16,"乡村建设行动","农村基础设施","农村道路建设","胭脂湖街道","黄家湖村","黄家湖村公路路基拓宽","新建","黄家湖村","2023-02-20","2023-03-20","乡村振兴局","500米主干道拓宽2米",10,10,null,null,0,1,120,280,0,4,12,"项目（工程）验收合格率100%","①提高群众生产生活水平\n②便利群众出行"]
[17,"产业发展","生产项目","种植业基地","胭脂湖街道","先锋村","示范区采摘园建设","新建","先锋村十一组","2023-02-20","2023-03-10","乡村振兴局","培育杨梅树等15亩",30,30,null,null,0,1,520,3520,0,69,154,"发展村集体经济，带动更多的农户增收增产，开拓市场，帮助69户脱贫户每人每年增加收入300-500元","1、带动地方产业发展\n2、新增就业岗位"]
[18,"乡村建设行动","农村基础设施","农村道路建设","胭脂湖街道","莲子塘村","莲子塘村10组公路硬化","新建","莲子塘村10组","2023-03-01","2023-03-31","乡村振兴局","长210米，宽3米",8,8,null,null,0,1,60,180,0,3,8,"项目（工程）验收合格率100%","①提高群众生产生活水平\n②便利群众出行"]
[19,"产业发展","配套基础设施项目","小型农田水利设施建设","胭脂湖街道","十里坪村","十里坪村山塘改造","新建","台公塘十组","2023-03-01","2023-03-28","乡村振兴局","清淤硬化一口山塘",8,8,null,null,0,1,48,248,0,1,3,"项目（工程）验收\n合格率100%","1、提高群众生产生活水平\n2、带动农业发展"]
[20,"乡村建设行动","农村基础设施","农村道路建设","胭脂湖街道","永建村","公路\n硬化","新建","永建村","2023-02-20","2023-03-10","乡村振兴局","硬化270米",10,10,null,null,0,1,80,362,0,7,30,"项目（工程）验收合格率100%","①提高群众生产生活水平\n②便利群众出行"]
[21,"产业发展","生产项目","种植业基地","胭脂湖街道","杨梅山村","杨梅山村烤房建设","新建","杨梅山村","2023-03-01","2023-04-01","乡村振兴局","杨梅山村烤房建设新增烤箱1个、仓库1个",20,20,null,null,0,1,2200,6400,0,129,354,"增加烤房项目建设，便于村民橘子、枳壳销售，增加村集体经济收入。","1、带动地方产业发展\n2、新增就业岗位"]
[35,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","新湾镇","周公湖村","周公湖村烂泥组春初路公路硬化项目","基础设施建设","周公湖村烂泥组","2023-01-01","2023-03-01","周公湖村","烂泥组道路\n硬化长147米、宽3米",5,5,null,null,0,1,9,32,0,3,7,"项目带动脱贫人口直接受益7人","①提高群众生产生活水平②解决脱贫户3户7人的出行安全及发展经济问题"]
[36,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","新湾镇","杨阁老村","杨阁老村烈士路拓宽","改扩建","杨阁老村","2023-03-01","2023-10-01","乡村振兴局","烈士路约240米，拓宽2.5米",10,10,null,null,0,1,150,500,0,6,13,"项目带动脱贫人口直接受益13人","①提高群众生产生活水平②解决脱贫户6户13人的出行安全及发展经济问题"]
[37,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","新湾镇","龙虎山村","新湾镇龙虎山村-基础设施-七组公里维修项目","新建","龙虎山村七组","2023-01-01","2023-12-02","乡村振兴局","长1.5公里，宽3米道路拓宽维护",3,3,null,null,0,1,58,154,0,5,12,"项目带动脱贫人口直接受益12人","①提高群众生产生活水平②解决脱贫户5户12人的农副产品运输问题"]
[38,"产业发展项目","生产项目","种植业基地","新湾镇","新湾村","盛旺蠡山现代农业综合开发有限公司产业配套设施建设（喷滴灌）","新建","新湾村高子塘组","2023-05-01","2023-06-01","乡村振兴局","喷滴灌设施70亩",10,10,null,null,0,1,22,63,1,3,6,"项目带动脱贫人口直接受益6人","①提高群众生产生活水平和收入"]
[39,"产业发展项目","生产项目","种植业基地","新湾镇","桥北村","桥北村经济合作社-橘柚示范园建设","产业发展","桥北村东风组","2023-02-01","2023-12-01","桥北村","桥北村橘柚示范园基地管护",35,35,null,null,0,1,1220,2978,0,10,22,"项目带动脱贫人口直接受益22人","①提高群众生产生活水平 ②增加集体经济收入"]
[40,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","新湾镇","桥北村","桥北村葵花组道路拓宽硬化建设","基础设施","桥北村葵花组","2023-02-01","2023-12-01","桥北村","桥北村葵花组长700米道路拓宽硬化",25,25,null,null,0,1,100,261,0,4,7,"项目带动脱贫人口及防返贫监测对象直接受益7人","①提高群众生产生活水平②解决脱贫户4户7人的农副产品运输问题"]
[45,"产业发展","生产项目","种殖业基地","南嘴镇","蠡山村","南嘴镇2023年蠡山村经济合作社-产业基地建设","新建","蠡山村","2023-03-01","2023-11-01","乡村振兴局","开荒、道路平整，挖沟渠",10,10,null,null,0,1,15,42,0,5,12,"满意度指标、服务对象满意度指标、受益建档立卡贫困人口满意度>95%","1.完善村级基础设施，提高群众生产生活水平.2增加村集体经济，带动群众增收增产。"]
[46,"产业发展","生产项目","种植业基地","南嘴镇","兴南村","南嘴镇2023年兴南村柑橘品改","新建","兴南村","2023-02-01","2023-04-01","乡村振兴局","土地翻耕购买树苗，面积200亩",10,10,null,null,0,1,62,181,0,19,35,"满意度指标、服务对象满意度指标、受益建档立卡贫困人口满意度>96%","1.完善村级基础设施，提高群众生产生活水平.3增加村集体经济，带动群众增收增产。"]
[47,"乡村建设行动","农村基础设施建设","农村道路建设","南嘴镇","新南社区","南嘴镇2023年新南社区公路硬化","新建","新南社区","2023-03-01","2023-03-01","乡村振兴局","1公里",3,3,null,null,0,1,83,168,0,23,47,"满意度指标、服务对象满意度指标、受益建档立卡贫困人口满意度>97%","1.完善村级基础设施，提高群众生产生活水平.4增加村集体经济，带动群众增收增产。"]
[48,"乡村建设行动","农村基础设施建设","农村道路建设","南嘴镇","和谐村","南嘴镇2023年和谐村山塘整修","新建","和谐村","2023-09-01","2023-12-01","乡村振兴局","山塘整修及沟港清淤",8,8,null,null,0,1,963,2236,0,54,109,"满意度指标、服务对象满意度指标、受益建档立卡贫困人口满意度>98%","1.完善村级基础设施，提高群众生产生活水平.5增加村集体经济，带动群众增收增产。"]
[56,"乡村建设行动","人居环境整治","村容村貌提升","草尾镇","保安垸村","渠道疏浚","改扩建","7、4支渠、6、4横渠","2023-01-01","2023-12-31","乡村振兴局","渠道梳洗（6000米）",8,8,null,null,0,1,298,791,1,19,44,{"v":1,"d":"100%"},"提高群众生产生活水平"]
[57,"乡村建设行动","人居环境整治","村容村貌提升","草尾镇","草尾社区","渠道整修","改扩建","草尾社区","2023-01-01","2023-12-31","乡村振兴局","1000米",5,5,null,null,0,1,189,378,1,8,13,{"v":1,"d":"100%"},"提高群众生产生活水平"]
[58,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","大福村","路基维修","改扩建","大福村20组","2023-02-01","2023-03-01","乡村振兴局","路基整改，加高",3,3,null,null,0,1,54,168,1,11,36,{"v":1,"d":"100%"},"提高周边群众农用物质运输能力，提升渠道蓄水能力。"]
[59,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","大同闸村","道路维修","改扩建","11.12.13.22组","2023-01-01","2023-12-31","乡村振兴局","公路维修（300米）",3,3,null,null,0,1,310,820,1,18,55,{"v":1,"d":"100%"},"提高群众生产生活水平"]
[60,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","东红村","机耕道整修","改扩建","东红村","2023-01-01","2023-12-01","乡村振兴局","机耕道整修",10,10,null,null,0,1,30,92,1,6,17,{"v":1,"d":"100%"},"提高群众生产生活水平"]
[61,"产业发展项目","配套基础","小型农田水利设施建设","草尾镇","和平村","产业配套渠道疏浚及涵闸建设","改扩建","1、2、3、5组","2023-01-01","2023-12-31","乡村振兴局","14000米",44,44,null,null,0,1,220,1000,0,23,78,{"v":1,"d":"100%"},"提高群众生产生活水平"]
[62,"乡村建设行动","农村基础设施","产业路、资源路、旅游路建设","草尾镇","和平村","产业配套道路硬化","改扩建","1、2、3、5组","2023-01-01","2023-12-31","乡村振兴局","9000米",56,56,null,null,0,1,260,1200,0,23,78,{"v":1,"d":"100%"},"提高群众生产生活水平"]
[63,"乡村建设行动","农村基础设施","产业路、资源路、旅游路建设","草尾镇","和平村","和平村集体经济合作社产业配套设施建设","改扩建","1、2、3、5组","2023-01-01","2023-12-31","乡村振兴局","机耕道硬化",{"$f":"O42+P42+Q42+R42","v":20},20,null,null,0,1,110,545,0,23,78,{"v":1,"d":"100%"},"提高群众生产生活水平"]
[64,"乡村建设行动","人居环境整治","村容村貌提升","草尾镇","民主村","渠道疏浚","改扩建","1支渠和6支渠","2023-01-01","2023-12-31","乡村振兴局","渠道梳洗及扫障（3000米）",5,5,null,null,0,1,241,788,1,28,77,{"v":1,"d":"100%"},"提高群众生产生活水平"]
[65,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","上码头村","道路硬化","改扩建","上码头村","2023-01-01","2023-12-31","乡村振兴局","道路硬化",35,35,null,null,0,1,976,3241,1,65,157,{"v":1,"d":"100%"},"提高群众生产生活水平"]
[66,"乡村建设行动","人居环境整治","村容村貌提升","草尾镇","上码头村","渠道疏浚","改扩建","上码头村","2023-01-01","2023-12-31","乡村振兴局","渠道疏浚",15,15,null,null,0,1,420,1356,1,54,125,{"v":1,"d":"100%"},"提高群众生产生活水平"]
[67,"乡村建设行动","农村基础设施","产业路、资源路、旅游路建设","草尾镇","双东村","双东村集体经济合作社产业配套设施建设","改扩建","双东村","2023-01-01","2023-12-31","乡村振兴局","公路建设1200米，危桥改造2座",23,23,null,null,0,1,386,1680,1,25,76,{"v":1,"d":"100%"},"提高群众生产生活水平"]
[68,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","四民村","道路硬化","改扩建","四民村","2023-01-01","2023-12-31","乡村振兴局","3公里",10,10,null,null,0,1,30,87,1,6,15,{"v":1,"d":"100%"},"提高群众生产生活水平"]
[69,"乡村建设行动","人居环境整治","村容村貌提升","草尾镇","熙和村","渠道疏浚","改扩建","熙和村","2023-01-01","2023-12-31","乡村振兴局","1500米",3,3,null,null,0,1,78,267,1,22,61,{"v":1,"d":"100%"},"提高群众生产生活水平"]
[70,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","长乐村","道路硬化","改扩建","长乐村","2023-01-01","2023-12-31","乡村振兴局","3公里",10,10,null,null,0,1,35,96,1,8,25,{"v":1,"d":"100%"},"提高群众生产生活水平"]
[71,"乡村建设行动","人居环境整治","村容村貌提升","草尾镇","胜天村","渠道疏浚","改扩建","胜天村","2023-01-01","2023-12-31","乡村振兴局","渠道疏浚",6,6,null,null,0,1,280,1360,1,63,165,{"v":1,"d":"100%"},"提高群众生产生活水平"]
[32,"产业发展项目","生产项目","种植业基地","阳罗洲镇","胜利村","沅江市_产业项目_阳罗洲镇2023年胜利村宴府农业科技有限公司蔬菜种植","新建","阳罗洲镇胜利村","2023-02-01","2023-04-01","阳罗洲镇胜利村","产业发展",10,10,null,null,0,1,42,75,0,38,65,"带动脱贫户及监测户人均年增收800元","产业分红"]
[33,"产业发展项目","配套设施项目","小型农田水利设施建设","阳罗洲镇","吕丰村","沅江市_产业项目_阳罗洲镇2023年吕丰村闸门重建","新建","阳罗洲镇吕丰村","2023-02-01","2023-04-01","阳罗洲镇吕丰村","闸门一座",5,5,null,null,0,1,132,312,0,35,72,"带动脱贫户及监测户人均年增收300元","带动生产"]
[34,"产业发展项目","生产项目","种植业基地","阳罗洲镇","富安村","沅江市_产业项目_阳罗洲镇2023年富安村腰港生态农业专业合作社稻虾种养","新建","阳罗洲镇富安村","2023-02-01","2023-04-01","阳罗洲镇富安村","产业发展",9,9,null,null,0,1,92,285,0,88,268,"带动脱贫户及监测户人均年增收500元","产业分红"]
[35,"产业发展项目","生产项目","种植业基地","阳罗洲镇","候龙村","沅江市_产业项目_阳罗洲镇2023年候龙村俊熙稻虾种养专业合作社","新建","阳罗洲镇候龙村","2023-02-01","2023-04-01","阳罗洲镇候龙村","产业发展",20,20,null,null,0,1,102,354,1,96,325,"带动脱贫户及监测户人均年增收1000元","产业分红"]
[36,"产业发展项目","生产项目","种植业基地","阳罗洲镇","富民村","沅江市_产业项目_阳罗洲镇2023年富民村宏龙稻虾种养专业合作社","新建","阳罗洲镇富民村","2023-02-01","2023-04-01","阳罗洲镇富民村","产业发展",8,8,null,null,0,1,75,286,0,70,265,"带动脱贫户及监测户人均年增收500元","产业分红"]
[37,"产业发展项目","配套设施项目","小型农田水利设施建设","阳罗洲镇","复兴村","沅江市_产业项目_阳罗洲镇2023年复兴村新建电排","新建","阳罗洲镇复兴村","2023-02-01","2023-04-01","阳罗洲镇复兴村","新建电排1座",8,8,null,null,0,1,42,102,0,15,38,"带动脱贫户及监测户人均年增收300元","带动生产"]
[38,"产业发展项目","配套设施项目","小型农田水利设施建设","阳罗洲镇","永兴社区","沅江市_产业项目_阳罗洲镇2023年永兴社区沟渠梳洗","维修","阳罗洲镇永兴社区","2023-02-01","2023-04-01","阳罗洲镇永兴社区","沟渠梳洗1公里",5,5,null,null,0,1,52,135,0,0,0,"带动受益群众人均年增收300元","带动生产"]
[39,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","阳罗洲镇","七子浃村","沅江市_村基础设施_阳罗洲镇2023年七子浃村1组路基建设1公里","新建","阳罗洲镇七子浃村","2023-02-01","2023-04-01","阳罗洲镇七子浃村","路基建设1公里",10,10,null,null,0,1,68,175,0,34,75,"带动脱贫户及监测户人均年增收300元","带动生产"]
[40,"乡村建设行动","农村基础设施","产业路、资源路、旅游路建设","阳罗洲镇","大中村","沅江市_村基础设施_阳罗洲镇2023年大中村经济合作社产业路建设2公里","新建","阳罗洲镇大中村","2023-02-01","2023-04-01","阳罗洲镇大中村","产业路建设2公里",20,20,null,null,0,1,86,232,1,72,198,"带动脱贫户及监测户人均年增收800元","带动生产"]
[11,"产业发展","配套设施项目","大寨渠沿线休闲文旅配套设施建设","四季红镇","/","沅江市四季红镇大寨渠沿线休闲文旅配套设施建设","新建","四季红镇","2023-03-01","2023-06-01","四季红镇","腐乳产业配套；移民文化建设；乡村振兴示范镇建设等",100,100,null,null,0,8,378,1450,2,15,38,"增加群众收入","增加群众收入"]
[12,"产业发展","配套设施项目","食品加工厂配套设施建设","四季红镇","长征村","沅江市四季红镇长征村食品加工厂配套设施建设","新建","四季红镇","2023-03-01","2023-05-01","四季红镇","食品加工厂新建冷库1座",3,3,null,null,0,1,30,165,0,3,12,"增加群众收入","增加群众收入"]
[13,"乡村建设行动","农村基础设施","公路硬化","四季红镇","安心村","沅江市四季红镇安心村4-6组公路硬化","新建","四季红镇","2023-03-01","2023-05-01","四季红镇","C35混泥土新建公路硬化615m^2",8,8,null,null,0,1,23,112,0,3,10,"改善群众生活条件、群众满意度≥100%","改善群众生活条件"]
[14,"乡村建设行动","农村基础设施","公路扩宽","四季红镇","东红新村","沅江市四季红镇东红新村二斗渠公路扩宽","新建","四季红镇","2023-03-01","2023-05-01","四季红镇","C35混泥土公路扩建1.2km",8,8,null,null,0,1,30,198,0,3,8,"改善群众生活条件、群众满意度≥100%","改善群众生活条件"]
[15,"乡村建设行动","农村基础设施","公路扩宽","四季红镇","四季红村","沅江市四季红镇四季红村九组至十二组公路扩宽","新建","四季红镇","2023-03-01","2023-05-01","四季红镇","C35混泥土公路扩建2.5km（包括道路维护）",20,20,null,null,0,1,55,412,1,8,24,"改善群众生活条件、群众满意度≥100%","改善群众生活条件"]
[16,"乡村建设行动","农村基础设施","渠道硬化","四季红镇","阳雀洪村","沅江市四季红镇阳雀洪村稻虾渠道硬化","新建","四季红镇","2023-03-01","2023-05-01","四季红镇","渠道硬化清淤1.6km",10,10,null,null,0,1,22,187,1,5,14,"改善群众生活条件、群众满意度≥100%","改善群众生活条件"]
[17,"乡村建设行动","农村基础设施","公路维修","四季红镇","四季红社区","沅江市四季红镇四季红社区二斗渠公路维修","新建","四季红镇","2023-03-01","2023-05-01","四季红镇","C35混凝泥土加人工挖机维修道路50m^3",3,3,null,null,0,1,21,130,0,2,7,"改善群众生活条件、群众满意度≥100%","改善群众生活条件"]
[18,"乡村建设行动","人居环境整治","斗渠清淤工程","四季红镇","先锋村","四季红镇先锋村十斗渠清淤工程","新建","四季红镇","2023-03-01","2023-05-01","四季红镇","十斗渠清淤扫障200m^2",6,6,null,null,0,1,25,123,0,3,10,"改善群众生活条件、群众满意度≥100%","改善群众生活条件"]
[19,"乡村建设行动","农村基础设施","渠道硬化","四季红镇","玉鹊村","沅江市四季红镇玉鹊村六斗渠至八斗渠硬化","新建","四季红镇","2023-03-01","2023-05-01","四季红镇","渠道硬化6.8km",55,55,null,null,0,1,45,156,0,5,16,"改善群众生活条件、群众满意度≥100%","改善群众生活条件"]
[139,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","黄茅洲镇","柳树坪村","道路硬化","新建","柳树坪村","2023-03-01","2023-06-01","乡村振兴局","公路拓宽及\n白改黑880米",35,35,null,null,0,1,780,1245,1,32,65,"受益建档立卡贫困户满意度≥95％","方便群众\n出行"]
[140,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","黄茅洲镇","新丰村","路基拓宽","新建","新丰村","2023-01-01","2023-02-01","乡村振兴局","路基拓宽1.5m长500米",5,5,null,null,0,1,986,3096,1,20,35,"受益建档立卡贫困户满意度≥95％","方便群众\n出行"]
[141,"产业发展项目","生产项目","种植业基地","黄茅洲镇","柳树坪果业种植专业合作社","产业配套\n设施建设","新建","柳树坪果业种植专业合作社","2023-03-01","2023-06-01","乡村振兴局","公路白改黑900米",40,40,null,null,0,1,780,1245,1,25,132,"受益建档立卡贫困户满意度≥95％","增加集体\n经济收益"]
[142,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","黄茅洲镇","黄茅洲村","路基拓宽","新建","黄茅洲村","2023-01-01","2023-02-01","乡村振兴局","路基拓宽1.5m长300米",5,5,null,null,0,1,2075,5656,1,25,65,"受益建档立卡贫困户满意度≥95％","方便群众\n出行"]
[143,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","黄茅洲镇","红旗村","路基拓宽","新建","红旗村","2023-01-01","2023-02-01","乡村振兴局","路基拓宽2.5m1280米",7,7,null,null,0,1,852,2056,1,23,56,"受益建档立卡贫困户满意度≥95％","方便群众\n出行"]
[144,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","黄茅洲镇","洞庭滨村","路基拓宽","新建","洞庭滨村","2023-01-01","2023-01-01","农业农村局","向阳渠路基拓宽280米",{"$f":"O74+P74+Q74+R74","v":5},5,null,null,0,3,364,1280,1,36,78,"受益建档立卡贫困户满意度≥95％","方便群众\n出行"]
[145,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","黄茅洲镇","肖家坝村","机耕道整修","新建","肖家坝村","2023-02-01","2023-03-01","乡村振兴局","机耕道整修1500米",8,8,null,null,0,1,1758,5212,1,22,56,"受益建档立卡贫困户满意度≥95％","方便群众\n出行"]
[146,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","黄茅洲镇","黄栗塘村","道路维修","新建","黄栗塘村","2023-02-01","2023-03-01","乡村振兴局","道路维修40m",8,8,null,null,0,1,1595,2586,1,25,65,"受益建档立卡贫困户满意度≥95％","方便群众\n出行"]
[147,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","黄茅洲镇","群红村","机耕道整修","新建","群红村","2023-02-01","2023-03-01","乡村振兴局","机耕道整修700米",6,6,null,null,0,1,38,190,1,9,34,"受益建档立卡贫困户满意度≥95％","方便群众\n出行"]
[148,"乡村振兴行动","农村基础设施","农村道路建设(通村、通户路)","黄茅洲镇","志成垸村","道路拓宽","新建","志成垸村","2023-02-01","2023-02-01","乡村振兴局","道路拓宽600米",5,5,null,null,0,1,534,1455,1,27,34,"收益建档立卡贫困户满意度≥95％","方便群众出行"]
[149,"产业发展项目","生产项目","种植业基地","黄茅洲镇","民心村","产业配套\n设施建设","新建","民心村","2023-03-01","2023-06-01","乡村振兴局","机耕道整修2000米",22,22,null,null,0,1,780,1245,1,25,132,"受益建档立卡贫困户满意度≥95％","增加集体\n经济收益"]
[115,"乡村建设行动","农村基础设施","其他","南大膳镇","双螺村","南大膳镇双螺村渠道梳洗项目","维修","双螺村","2023-04-01","2023-06-01","乡村振兴局","渠道梳洗1000M",3,3,null,null,0,1,30,90,0,10,30,"提高群众满意度","提升群众生产生活条件"]
[100,"产业发展项目","生产项目","水产养殖业发展","共华镇","双阜村","共华镇-双阜村—产业发展-鑫德雷特种水产养殖专业合作社","新建","双阜村11组","2023-03-01","2023-12-01","乡村振兴局","养殖鱼塘改扩建180亩",20,20,null,null,0,1,30,50,1,2,6,"受益群众满意度≥100%","提高群众生产生活水平"]
[101,"产业发展项目","配套基础设施项目","小型农田水利设施建设","共华镇","和裕村","共华镇-和裕村—产业发展-禾裕农业专业合作社优质稻基地产业配套设施建设","新建","和裕村8组、9组","2023-03-01","2023-12-01","乡村振兴局","机耕道平整200米、沟渠硬化200米",15,15,null,null,0,1,50,100,0,6,17,"受益群众满意度≥100%","提高群众生产生活水平"]
[102,"产业发展项目","配套基础设施项目","小型农田水利设施建设","共华镇","谭家岭村","共华镇-谭家岭村-基础设施-机埠建设","新建","谭家岭村东成片7组","2023-03-02","2023-12-02","乡村振兴局","机埠1座",3,3,null,null,0,1,50,160,0,0,0,"受益群众满意度≥100%","提高群众生产生活水平"]
[103,"产业发展项目","配套基础设施项目","小型农田水利设施建设","共华镇","团湖洲村","共华镇-团湖洲村-基础设施-渠道建设","新建","团湖洲村东湖片","2023-03-03","2023-12-03","乡村振兴局","东湖片渠道梳洗新开800米",5,5,null,null,0,1,40,100,1,0,0,"受益群众满意度≥100%","提高群众生产生活水平"]
[104,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","共华镇","东合村","共华镇-东合村-基础设施-道路及附属设施建设","新建","东合村","2023-03-04","2023-12-04","乡村振兴局","道路及配套设施建设1千米",10,10,null,null,0,1,100,200,0,0,0,"受益群众满意度≥100%","提高群众生产生活水平"]
[105,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","共华镇","华兴村","共华镇-华兴村-基础设施-机耕道平整","新建","华兴村","2023-03-05","2023-12-05","乡村振兴局","机耕道平整500米",3,3,null,null,0,1,20,50,0,0,0,"受益群众满意度≥100%","提高群众生产生活水平"]
[106,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","共华镇","黄土包村","共华镇-黄土包村-基础设施-路基建设","新建","黄土包村足华洲片","2023-03-06","2023-12-06","乡村振兴局","路基平整800米",6,6,null,null,0,1,30,100,0,0,0,"受益群众满意度≥100%","提高群众生产生活水平"]
[107,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","共华镇","仁安村","共华镇-仁安村-基础设施-路基建设","新建","仁安村友谊渠","2023-03-07","2023-12-07","乡村振兴局","路基建设2千米",9,9,null,null,0,1,100,200,0,0,0,"受益群众满意度≥100%","提高群众生产生活水平"]
[108,"产业发展项目","配套基础设施项目","小型农田水利设施建设","共华镇","紫红洲村","共华镇-紫红洲村-基础设施-渠道疏浚","新建","紫红洲村均利片","2023-03-08","2023-12-08","乡村振兴局","渠道梳洗800米",5,5,null,null,0,1,30,100,0,0,0,"受益群众满意度≥100%","提高群众生产生活水平"]
[109,"产业发展项目","生产项目","水产养殖业发展","共华镇","八形汊村","八形汊村鳖福健生态甲鱼养殖农民专业合作社","新建","八形汊村","2023-03-09","2023-12-09","乡村振兴局","甲鱼养殖",20,20,null,null,0,1,40,100,0,0,0,"受益群众满意度≥100%","提高群众生产生活水平"]
[110,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","共华镇","八形汊村","共华镇-八形汊村-基础设施-道路及附属设施建设","新建","八形汊村","2023-03-10","2023-12-10","乡村振兴局","道路及附属设施建设",25,25,null,null,0,1,50,130,0,0,0,"受益群众满意度≥100%","提高群众生产生活水平"]
[135,"乡村建设行动","农村基础设施","农村道路建设（通村、通路）","泗湖山镇","华星村","2023年泗湖山镇华星村-基础设施-星台片道路硬化","新建","华星村星台片","2023-02-01","2023-04-01","乡村振兴局","175米",7,7,null,null,0,1,8,28,1,2,5,"受益脱贫人口满意度≥98%","①完善村级基础设施，提高群众生产生活水平；\n②方便全村贫困户与非贫困户农业生产。"]
[136,"乡村建设行动","农村基础设施","其他","泗湖山镇","净下洲村","2023泗湖山镇净下洲村-乡村建设行动-中心渠、净北渠、永乐渠段渠道疏洗","改修建","净下洲村","2023-01-01","2023-12-01","乡村振兴局","中心渠共计650米；净北渠共计400米；永乐渠共计450米；",4,4,null,null,0,1,22,35,0,1,4,"受益脱贫人口满意度≥98%","①完善村级基础设施，提高群众生产生活水平；\n②方便全村贫困户与非贫困户农业生产。"]
[137,"产业发展","生产\n项目","种植业\n基地","泗湖山镇","东安垸村","2023年泗湖山镇-产业发展-东安垸村万良种养专业合作社基础设施建设","基地建设","东安垸村东红片1-2组","2023-04-01","2023-06-01","东安垸村","803亩脐橙基地水肥一体基础设施建设",35,35,null,null,0,1,5,13,1,128,274,"受益脱贫人口满意度≥95%","①完善村级基础设施，提高群众生产生活水平；\n②方便全村贫困户与非贫困户农业生产。"]
[138,"乡村建设行动","农村基础设施","农村道路建设（通村、通路）","泗湖山镇","光复垸村","2023泗湖山镇光复垸村-乡村建设行动-群益2组-3组道路加宽","道路加宽","群益片","2023-03-01","2023-04-01","乡村振兴局","道路加宽0.5千米",10,10,null,null,0,1,60,200,1,4,8,"受益脱贫人口满意度≥98%","完善村级基础设施，提高群众生产生活水平"]
[139,"产业发展","加工流通项目","产地初加工和精深加工","泗湖山镇","光复垸村","2023泗湖山镇光复垸村-产业发展-秸秆综合回收利用","厂房新建","光复垸村","2023-03-01","2024-03-01","乡村振兴局","厂房新建1200平方",150,50,null,null,100,1,136,302,1,126,271,"受益脱贫人口满意度≥99%","改善农村环境，提高群众生产生活水平"]
[140,"乡村建设行动","农村基础设施","农村道路建设（通村、通路）","泗湖山镇","北港村","2023泗湖山镇北港村-乡村建设行动-通户公路硬化","基础设施","通户公路","2023-01-01","2023-12-01","北港村","入户路路基铺设和通户路硬化",20,20,null,null,0,1,10,24,1,3,8,"受益脱贫人口满意度≥95%","①完善村级基础设施，提高群众生产生活水平；\n②方便全村贫困户与非贫困户农业生产。"]
[141,"乡村建设行动","农村基础设施","其他","泗湖山镇","北港村","2023泗湖山镇北港村-乡村建设行动-渠道疏浚","基础设施","渠道疏浚","2023-01-01","2023-12-01","北港村","S507沿河路和光华片围湖渠",10,10,null,null,0,1,12,25,1,4,10,"受益脱贫人口满意度≥95%","①完善村级基础设施，提高群众生产生活水平；\n②方便全村贫困户与非贫困户农业生产。"]
[142,"乡村建设行动","农村基础设施","农村道路建设（通村、通路）","泗湖山镇","华红村","2023泗湖山镇华红村-乡村建设行动-机耕道硬化","新建","华红村重华片3组","2023-02-13","2023-03-01","华红村","新建公路280米",10,10,null,null,0,1,8,23,0,1,2,"完善基础设施建设方便群众产品运输","①完善村级基础设施，提高群众生产生活水平；\n②方便全村贫困户与非贫困户农业生产。"]
[143,"乡村建设行动","农村基础设施","其他","泗湖山镇","坪塘岭村","2023年泗湖山镇坪塘岭村-基础设施-双洲片2组渠道疏浚","新建","双洲片2组","2023-01-01","2023-12-01","坪塘岭村","坪塘岭村双洲片2组渠道疏浚500米",3,3,null,null,0,1,29,92,1,1,2,"受益脱贫人口满意度≥98%","①完善村级基础设施，提高群众生产生活水平；\n②方便全村贫困户与非贫困户农业生产。"]
[43,"乡村建设行动","农村基础设施","其他","茶盘洲镇","新华村","2023年茶盘洲镇新华村中排沟渠清淤项目","新建","新华村中排渠","2023-03-01","2023-04-08","新华村","新华村中排渠清淤",5,5,null,null,0,1,220,806,0,16,44,"沟渠清淤2.8千米","确保农田旱涝保收"]
[44,"乡村建设行动","农村基础设施","其他","茶盘洲镇","六合村","2023年茶盘洲镇茶盘洲镇六合村永丰中心渠道清淤项目","新建","六合村","2023-02-18","2023-04-09","六合村","茶盘洲镇六合村永丰中心渠道清淤1400米",3,3,null,null,0,1,73,158,0,28,51,"渠道清淤1.4公里","确保农田旱涝保收"]
[45,"乡村建设行动","农村基础设施","其他","茶盘洲镇","玉竹村","2023年茶盘洲镇玉竹村四组高标准农田机耕道拓宽项目","拓建","玉竹村","2023-02-18","2023-04-08","玉竹村","玉竹村四组高标准农田机耕道拓宽项目",3,3,null,null,0,1,150,300,0,10,20,"路基拓宽0.5米，路长1000米","方便群众出行和产品的运输，带动群众致富"]
[46,"乡村建设行动","农村基础设施","其他","茶盘洲镇","幸福村","2023年茶盘洲镇茶盘洲镇幸福村幸平路路基拓宽项目","拓建","幸福村","2023-02-01","2023-05-19","幸福村","幸福村幸平路路基拓宽",20,20,null,null,0,1,900,2800,1,77,173,"路基拓宽2000米","方便群众出行和产品的运输，带动群众致富。"]
[47,"产业发展","生产项目","产业园（区）","茶盘洲镇","幸福村","2023年茶盘洲镇茶盘洲镇幸福村经济合作社产业发展项目","拓建","幸福村","2023-02-18","2023-04-09","幸福村","用于幸福村经济合作社的发展",25,25,null,null,0,1,84,194,1,84,194,"提升集体经济合作社的致富能力","提升集体经济合作社的创收能力"]
[48,"乡村建设行动","农村基础设施","其他","茶盘洲镇","柴洲包村","2023年茶盘洲镇柴洲包村南排渠清淤工程","新建","柴洲包村","2023-02-17","2023-04-09","柴洲包村","沟渠清淤2000米",5,5,null,null,0,1,90,320,0,12,28,"沟渠清淤2000米","便于农田灌溉于排渍"]