{"text_format":"3","workbook":"xlsx","n_sheets":2,"sheets":["汇总表","明细表"],"not_rendered":{"defined_names":3},"read":"whole","date_system":"1900"}

{"sheet":"汇总表","index":0,"n_rows":37,"n_cols":15,"rows_kept":37,"merged":[[0,0,0,14],[1,0,1,14],[3,0,5,0],[3,1,5,1],[3,2,5,2],[3,3,3,7],[3,8,3,13],[3,14,5,14],[4,3,5,3],[4,4,4,7],[4,8,5,8],[4,9,5,9],[4,10,5,10],[4,11,4,13]]}
["沅江市2023年度巩固拓展脱贫攻坚成果和乡村振兴项目库汇总表"]
["单位（盖章）：                                                                                                         单位：万元、个、人"]
[]
["序号","项目类型","项目个数","资金规模和筹资方式",{"$nulls":4},"受益对象",{"$nulls":5},"备注"]
[{"$nulls":3},"项目预算总投资","其中",{"$nulls":3},"受益村（个）","受益户数（户）","受益人口数（人）","其中"]
[{"$nulls":4},"财政衔接资金","除财政衔接资金外的统筹整合资金","其他财政资金","其他筹措资金",{"$nulls":3},"受益脱贫村数（个）","受益脱贫户数及防止返贫监测对象户数（户）","受益脱贫人口数及防止返贫监测对象人口数（人）"]
[null,"总  计",{"$f":"C8+C20+C24+C25+C34","v":0},0,0,0,0,0,0,0,0,0,0,0]
[null,"一、产业发展",{"$f":"C9+C10+C11+C12+C13","v":0},0,0,0,0,0,0,0,0,0,0,0]
[null,"1.生产项目"]
[null,"2.加工流通项目"]
[null,"3.配套设施项目"]
[null,"4.产业服务支撑项目"]
[null,"5.金融保险配套项目"]
[null,"二、就业项目"]
[null,"1.务工补助"]
[null,"2.就业培训"]
[null,"3.创业"]
[null,"4.乡村工匠"]
[null,"5.公益性岗位"]
[null,"三、乡村建设行动",{"$f":"C21+C22+C23","v":0},0,0,0,0,0,0,0,0,0,0,0]
[null,"1.农村基础设施"]
[null,"2.人居环境整治"]
[null,"3.农村公共服务"]
[null,"四、易地搬迁后扶"]
[null,"五、巩固三保障成果",{"$f":"C26+C27+C28+C29","v":0},0,0,0,0,0,0,0,0,0,0,0]
[null,"1.住房"]
[null,"2.教育"]
[null,"3.健康"]
[null,"4.综合保障"]
[null,"六、乡村治理和精神文明建设"]
[null,"1.乡村治理"]
[null,"2.农村精神文明建设"]
[null,"七、项目管理费"]
[null,"八、其他",{"$f":"C35+C36+C37","v":0},0,0,0,0,0,0,0,0,0,0,0]
[null,"1.少数民族特色村寨建设项"]
[null,"2.困难群众饮用低氟茶"]
[null,"……"]

{"sheet":"明细表","index":1,"n_rows":90,"n_cols":30,"rows_kept":90,"merged":[[0,0,0,26],[2,0,2,26],[4,0,6,0],[4,1,4,3],[4,4,6,4],[4,5,6,5],[4,6,6,6],[4,7,6,7],[4,8,6,8],[4,9,4,10],[4,11,6,11],[4,12,6,12],[4,13,4,17],[4,18,4,23],[4,24,6,24],[4,25,6,25],[4,26,6,26],[5,1,6,1],[5,2,6,2],[5,3,6,3],[5,9,6,9],[5,10,6,10],[5,13,6,13],[5,14,5,17],[5,18,6,18],[5,19,6,19],[5,20,6,20],[5,21,5,23]]}
["沅江市2023年度巩固拓展脱贫攻坚成果和乡村振兴项目库申报表"]
[]
["单位：（盖章）                                                                                                                                                                                                      时间：2023年8月"]
[]
["序号","项目类别",null,null,"乡","村","项目名称","建设性质","实施地点","时间进度",null,"责任单位","建设内容及规模","资金规模和筹资方式",{"$nulls":4},"受益对象",{"$nulls":5},"绩效目标","联农带农机制","备注"]
[null,"项目类型","二级项目类型","项目子类型",{"$nulls":5},"计划开工时间","计划完工时间",null,null,"项目预算总投资（万元）","其中",{"$nulls":3},"受益村数（个）","受益户数（户）","受益人口数（人）","其中"]
[{"$nulls":14},"财政衔接资金（万元）","除财政衔接资金外的统筹整资金（万元）","其他财政资金（万元）","其他筹措资金（万元）",{"$nulls":3},"受益脱贫村数（个）","受益脱贫户数及防止返贫监测对象户数（户）","受益脱贫人口数及防止返贫监测对象人口数（人）"]
[1,"乡村建设行动","人居环境整治","农村垃圾治理","14个镇（街道、中心）","169个行政村（社区\n）","农村生活垃圾治理服务外包项目1、2","新建","胭脂湖街道、琼湖街道、新湾镇、南嘴镇、草尾镇、黄茅洲镇、四季红镇、南大膳镇、漉湖事务中心、共华镇、泗湖山镇、茶盘洲镇、南洞庭事务中心共169个村（社区）","2023-01-25","2023-12-01","农业农村局","农村人居环境整治提质升级项目",{"$f":"O8+P8+Q8+R8","v":1431.94},1431.94,0,0,0,169,96330,289013,29,12208,28664,"农村生活垃圾处理率、保洁覆盖率均达100%。","解决了贫困户就业岗位63个，残疾人就业岗位52个。",null,"县级+","588.94+843","沅财农指〔2023〕6号"]
[2,"产业发展项目","加工流通项目","产地初加工和精深加工","阳罗洲镇","七子浃村","沅江市粮晟农业开发有限公司","新建","阳罗洲镇七子浃村","2023-08-01","2024-08-01","农业农村局","长粒型优质香稻加工线建设项目长颗粒香稻大米加工设备1套",100,100,0,0,0,2,38,38,1,38,38,"帮扶带动 30人脱贫户和监测对象参与发展产业，人均增收1150元，带动 8人就业务工，项目建成后增加长粒型优质香稻加工5000 吨，提高销售收入1000万元，提升我市北部湖区优质稻加工流通产能。","务工就业发放工资报酬、提供生产技术服务、产品保底回收、生产托管固定收益、入股分红",null,"重点产业330",100,"沅财农指〔2023〕12号"]
[3,"产业发展项目","加工流通项目","农产品仓储保鲜冷链基础设施建设","黄茅洲镇","黄茅洲村","湖南泰源农业科技开发有限公司","新建","沅江市高新区","2023-08-01","2024-08-01","农业农村局","小龙虾集采集配中心项目1000立方",100,100,0,0,0,1,20,20,0,20,20,"帮扶带动 8人脱贫户和监测对象参与发展产业，人均增收1240元，带动12人就业务工，项目建成后增加小龙虾集采集配交易150吨，提高销售收入 300万元，提升小龙虾交易流通能力，保障销售环节通畅。","务工就业发放工资报酬、提供生产技术服务、产品保底回收、生产托管固定收益、入股分红",null,"重点产业330",100,"沅财农指〔2023〕12号"]
[4,"产业发展项目","加工流通项目","产地初加工和精深加工","南大膳镇","华丰垸村","沅江市金江水产品有限公司","新建","沅江市高新区","2023-08-01","2024-08-01","农业农村局","小龙虾精深加工建设项目生产线2条",100,100,0,0,0,1,35,35,0,35,35,"帮扶带动 20人脱贫户和监测对象参与发展产业，人均增收1500元，带动 15人就业务工，项目建成后增加400吨虾粉产能，提高销售收入 800 万元，提升小龙虾深加工能力。","务工就业发放工资报酬、提供生产技术服务、产品保底回收、生产托管固定收益、入股分红",null,"重点产业330",100,"沅财农指〔2023〕12号"]
[5,"产业发展项目","生产项目","种植业基地","草尾镇","民主村","沅江市国芳生态农业种养专业合作社","新建","民主村","2023-08-01","2024-08-01","农业农村局","180亩稻虾综合种养",30,30,0,0,0,1,10,10,0,10,10,"帮扶带动6人脱贫户和监测对象参与发展产业，人均增收1500元，带动4人就业务工，项目建成后增加优质小龙虾产品20吨，提高销售收入39.6万元，同时带头推进立体循环农业示范，提升小龙虾及稻虾米品质。","务工就业发放工资报酬、提供生产技术服务、产品保底回收、生产托管固定收益",null,"重点产业330",30,"沅财农指〔2023〕12号"]
[6,"产业发展项目","生产项目","种植业基地","共华镇","双阜村","长进水稻专业合作社","新建","双阜村","2023-01-01","2023-03-01","农业农村局","基地配套设施建设产业基地建设",22,22,0,0,0,1,5,10,0,5,10,"打造长进专业水稻合作社产业示范基地，制作乡村振兴展板8块，完成产业园内环境整治、渠道清淤，建设6个示范菜园。","务工就业发放工资报酬、提供生产技术服务、产品保底回收、生产托管固定收益",null,"县级\n200",22,"沅财农指〔2023〕5号"]
[7,"乡村建设行动","人居环境整治","农村垃圾治理","琼湖街道","小河咀村","生活垃圾分类","新建","小河咀村","2023-09-01","2023-12-01","农业农村局","垃圾分类收集设施配置，开展再收资源回收利用、生活垃圾分类、垃圾源头减量宣传引导。",20,20,0,0,0,1,320,1728,1,58,58,"全村区域垃\n圾分类收集设施配置；\n开展再收资源回收利用、生\n活垃圾分类、垃圾源","对脱贫人口、易返贫致贫、低收入人群等监测对象进行带动帮扶",null,"中央\n368",20,"沅财农指〔2023〕17号"]
[8,"乡村建设行动","人居环境整治","村容村貌提升","胭脂湖街道、四季红镇、草尾镇、阳罗洲镇、泗湖山镇","南竹山村、玉鹊村、长乐村、七子浃村、东安垸村","美丽庭院与美丽屋场","新建","南竹山村、玉鹊村、长乐村、七子浃村、东安垸村","2023-09-01","2023-12-01","农业农村局","美丽庭院建设。",100,100,0,0,0,5,7916,21118,5,330,330,"5个村人居环境整治，村容村貌提升。","对脱贫人口、易返贫致贫、低收入人群等监测对象进行带动帮扶",null,"中央\n368",100,"沅财农指〔2023〕17号"]
[9,"产业发展项目","生产项目","种植业基地","沅江市","沅江市","产业发展","新建","沅江市","2023-09-01","2023-12-01","农业农村局","基地基础设施提升",248,248,0,0,0,47,55412,147826,47,2136,2136,"产地初加工、精深加工、与副产物综合利用、农旅融合发展经营服务、主体培育培育、预制菜产业品等基地建设","对脱贫人口、易返贫致贫、低收入人群等监测对象进行带动帮扶",null,"中央\n368",248,"沅财农指〔2023〕17号"]
[10,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","新湾镇、南嘴镇、草尾镇、共华镇、茶盘洲镇、四季红镇","目南村、和平村、双阜村、幸福村、四季红村、百家沟村","沅江市2022年资源产业旅游公路第三期","改建","沅江市区各乡镇、街道","2023-03-01","2023-09-01","交通运输局","共建设8条路，改造阁老墓景区道路1.933km,路面宽度5m；南嘴镇甘桔品改产业公路5.301km,路面宽度5m；百家沟产业园道路1.57km,路面宽度5.5m；美丽乡村和平村公路1.213km,路面宽度5m；东合村产业园公路2.148km,宽度路面4.5m；双阜村产业园公2.236km,面宽度4.5m；幸福村产业园公路2.148km，路面宽度5m；长征村至四季红公路5.705 km，路面宽度4.5m。全长共计  22.254km。",237.15,237.15,0,0,0,6,3408,13652,3,342,1127,"对经济发展的促进作用明显，基本公共服务水平和公路安全水平提升，适用未来一定时期内交通需求率100%","对脱贫人口、易返贫致贫、低收入人群等监测对象进行带动帮扶",null,"县级\n1000",237.15,"沅财农指〔2023〕10号"]
[11,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","琼湖街道办事处、共华镇、泗湖山镇","保民垸村、黄土包村、朱冯村、光华垸村","沅江市2022年资源产业旅游公路第一期","改建","沅江市区各乡镇、街道","2022-08-01","2023-02-01","交通运输局","保民大道(琼湖街道），0.802km；共华村至谭家岭公路（共华镇），1.619km；朱冯村农业特色产业园公路（泗湖山镇）2.345km；3条线路，总长4.775公里。",149.29,149.29,0,0,0,4,2272,8912,1,126,382,"对经济发展的促进作用明显，基本公共服务水平和公路安全水平提升，适用未来一定时期内交通需求率100%","对脱贫人口、易返贫致贫、低收入人群等监测对象进行带动帮扶",null,"县级\n1000",149.29,"沅财农指〔2023〕10号"]
[12,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","黄茅洲镇、新湾镇","大成村、谢家村","沅江市2021年资源产业旅游公路建设项目","改建","沅江市区各乡镇、街道","2022-03-01","2022-09-01","交通运输局","阳罗至子母城公路，4.897公里；谢家至回龙公路（新湾镇），2.634公里。",113.56,113.56,0,0,0,2,1126,4116,0,0,0,"对经济发展的促进作用明显，基本公共服务水平和公路安全水平提升，适用未来一定时期内交通需求率100%","对脱贫人口、易返贫致贫、低收入人群等监测对象进行带动帮扶",null,"县级\n1000",113.56,"沅财农指〔2023〕10号"]
[13,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","14个镇（街道、中心）","169个行政村（社区\n）","沅江市2020-2022农村公路提质改造工程","改建","沅江市区各乡镇、街道","2020-03-01","2022-12-20","交通运输局","沅江市2020-2022各乡镇、街道农村公路提质改造工程，共计426.6",500,500,0,0,0,180,360000,360000,11,1216,3720,"对经济发展的促进作用明显，基本公共服务水平和公路安全水平提升，适用未来一定时期内交通需求率100%","对脱贫人口、易返贫致贫、低收入人群等监测对象进行带动帮扶",null,"县级\n1000",500,"沅财农指〔2023〕10号"]
[14,"乡村建设行动","农村基础建设","农村道路建设","四季红镇","东红新村","农村道路建设","新建","四季红镇东红新村","2023-02-08","2023-03-10","民政局","公路扩宽300平方",{"$f":"O21+P21+Q21+R21","v":5},5,0,0,0,1,46,98,0,15,44,"帮扶带动12人脱贫户和检测户参与其中，人均增收1000多元，项目建成后全村都得到了受益","确保了村民出行条件，改善了农村生活环境",null,"民政",5]
[15,"乡村建设行动","农村基础建设","农村道路建设","四季红镇","阳雀洪村","道路提质升级","新建","四季红镇阳雀洪村","2023-07-20","2023-07-30","民政局","六组、九组机耕道新建",5,5,0,0,0,1,15,93,1,17,35,"保障农村安全生产，促进农村生产效率，改善农村居住条件","保证农村生产效率，使乡村更加宜居",null,"民政",5]
[16,"乡村建设行动","农村基础建设","农村道路建设","草尾镇","东红村","农村道路建设","新建","草尾镇东红村","2023-05-06","2023-05-16","民政局","公路硬化200米",5,5,0,0,0,1,20,56,0,10,32,"方便村民出行，保障安全生产，改善居住条件","改善了村民出行条件，使村民出行更加便利",null,"民政",5]
[17,"产业发展项目","配套基础设施项目","小型农田水利设施建设","草尾镇","三码头村","人居环境整治","新建","草尾镇三码头村","2023-04-25","2023-05-06","民政局","渠道疏通、清淤2200米",5,5,0,0,0,1,132,450,1,25,85,"改善了农村人居环境，解决了周边5个村民小组大部分稻虾养殖户的用水需求。提升了养殖户的养殖效益","是村民养殖户用水得到了很大的提升，提升了村民收益",null,"民政",5]
[18,"乡村建设行动","农村基础建设","农村道路建设","琼湖街道","山巷口社区","人居环境整治","新建","琼湖办事处山巷口社区","2023-07-20","2023-08-30","民政局","道路提质改造",5,5,0,0,0,1,60,158,0,20,40,"更精准、彻底的治理乱停车问题、确保道路的整洁有序。为居民创造更加文明和谐的交通环境满足居民对生活环境提升的期待","提高了社区居民生活环境，提供了更多的车位，使社区的生活更加整洁",null,"民政",5]
[19,"产业发展项目","配套基础设施项目","产业园（区）","琼湖街道","九只树村","九只树村四季果园产业基地改扩建60亩","改扩建","九只树村","2023-09-01","2023-10-01","组织部","品种改良48亩，亲子乐园、排水渠道、滴灌设施，灌溉水井、大棚、物资仓库等共约70亩",50,50,0,0,0,1,62,142,1,11,23,"群众人口满意度百分之百","增加村民收益",null,"中央、省",50,"沅财农指〔2023〕15号"]
[20,"乡村建设行动","人居环境整治","农村垃圾治理","琼湖街道","万子湖村","万子湖村人居环境整治","新建","万子湖村新村大道旁","2023-09-02","2023-10-01","乡村振兴局","33户房前屋后垃圾清运等环境整治；400米",50,50,0,0,0,1,33,85,0,19,35,"群众人口满意度百分之百","优化人居环境",null,"沅振发〔2023〕8号",50,"沅财农指〔2023〕14号"]
[21,"产业发展项目","配套基础设施项目","小型农田水利设施建设","琼湖街道","榨南湖村","榨南湖村长安组渠道疏浚","新建","榨南湖村长安组","2023-09-03","2023-10-01","乡村振兴局","900米渠道疏浚",10,10,0,0,0,1,65,180,0,58,159,"群众人口满意度百分之百","完善村级基础设施，提高群众生产生活水平",null,"沅振发〔2023〕8号",10,"沅财农指〔2023〕14号"]
[22,"产业发展项目","配套基础设施项目","产业园（区）","琼湖街道","小河咀村","小河咀村禾堂文化产业配套设施建设","新建","小河咀村","2023-09-04","2023-10-01","乡村振兴局","配套设施建设共约8亩",5,5,0,0,0,1,38,90,0,27,58,"群众人口满意度百分之百","提高群众生活水平",null,"沅振发〔2023〕8号",5,"沅财农指〔2023〕14号"]
[23,"乡村建设行动","农村基础设施","农村道路建设","胭脂湖街道","胭脂湖村","胭脂湖村道路配套设施建设项目","扩建","胭脂湖村5组、8组、9组、10组","2023-10-15","2023-11-25","乡村振兴局","拓宽硬化道路1000米",30,30,0,0,0,1,850,2778,0,60,149,"方便群众生产生活，达到增收致富","①提高群众生产生活水平\n②便利群众出行",null,"沅振发〔2023〕8号",30,"沅财农指〔2023〕14号"]
[24,"乡村建设行动","农村基础设施","农村道路建设","胭脂湖街道","南竹山村","南竹山村路基配套设施建设","新建","南竹山村","2023-10-15","2023-11-25","乡村振兴局","道路挡土墙建设260米",8,8,0,0,0,1,160,400,0,10,15,"方便群众生产生活，达到增收致富","①提高群众生产生活水平\n②便利群众出行",null,"沅振发〔2023〕8号",8,"沅财农指〔2023〕14号"]
[25,"乡村建设行动","农村基础设施","农村道路建设","胭脂湖街道","赤塘村","赤塘村道路配套设施建设","新建","赤塘村9、10组","2023-10-15","2023-11-25","乡村振兴局","9、10组基础设施建设",30,30,0,0,0,1,889,2588,0,56,140,"方便群众生产生活，达到增收致富","①提高群众生产生活水平\n②便利群众出行",null,"沅振发〔2023〕8号",30,"沅财农指〔2023〕14号"]
[26,"乡村建设行动","农村基础设施","农村道路建设","胭脂湖街道","荷花村","荷花村主干道公路附属基础设施","新建","荷花村七、八、四、三五组","2023-10-16","2023-11-26","乡村振兴局","沿线2.3公里绿化带挡土墙建设",5,5,0,0,0,1,780,2280,1,20,58,"方便群众生产生活，达到增收致富","①提高群众生产生活水平\n②便利群众出行",null,"沅振发〔2023〕8号",5,"沅财农指〔2023〕14号"]
[27,"产业发展","生产项目","种植业基地","新湾镇","新湾村","蠡山三农农业综合开发有限性公司蔬菜种植","产业发展","新湾村","2023-11-01","2028-11-01","乡村振兴局","蔬菜种植\n100亩",20,10,0,0,10,1,20,60,1,12,36,"项目带动脱贫人口直接受益36人","①提高群众\n生产生活水平和收入",null,"沅振发〔2023〕8号",10,"沅财农指〔2023〕14号"]
[28,"乡村建设行动","农村基础设施","农村道路建设","新湾镇","老屋冲村","桂枝园组至关王组115米道路硬化","新建","老屋冲村","2023-09-01","2023-11-01","乡村振兴局","115米道路硬化",8,5,0,0,3,1,5,20,1,3,10,"项目带动脱贫人口直接受益10人","①提高群众\n生产生活水平和收入②解决脱贫户3户10人的出行和农副产品运输",null,"益阳",5,"沅财农指〔2023〕13号"]
[29,"乡村建设行动","农村基础设施","农村道路建设","新湾镇","杨阁老村","阁老路1933米道路维修","维修","杨阁老村","2023-09-01","2023-11-01","乡村振兴局","阁老路1933米道路维修",35,30,0,0,5,1,150,460,1,5,20,"项目带动脱贫人口直接受益20人","①提高群众\n生产生活水平和收入②解决脱贫户5户20人的出行和农副产品运输",null,"沅振发〔2023〕8号",30,"沅财农指〔2023〕14号"]
[30,"产业发展","生产项目","种殖业基地","南嘴镇","百家沟村","南嘴镇2023年百家沟村红薯深加工集体经济项目","新建","百家沟村","2023-09-01","2024-12-01","组织部","流转、建设2000亩红薯种植基地",50,50,0,0,0,1,1488,4247,1,113,269,"满意度指标、服务对象满意度指标、受益建档立卡贫困人口满意度≥95%","①完善村级基础设施，提高群众生产生活水平；\n②增加村集体经济，带动群众增收增产。",null,"中央、省",50,"沅财农指〔2023〕15号"]
[31,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","南嘴镇","兴南村","南嘴镇2023年兴南村道路配套设施建设项目","新建","兴南村","2023-09-01","2023-10-31","乡村振兴局","张家村片2.1公里道路配套设施建设",31,30,0,0,1,1,402,1081,0,18,36,"满意度指标、服务对象满意度指标、受益建档立卡贫困人口满意度≥95%","完善村级基础设施，提高群众生产生活水平",null,"沅振发〔2023〕8号",30,"沅财农指〔2023〕14号"]
[32,"乡村建设行动","人居环境整治","村容村貌提升","草尾镇","四民村","渠道疏浚","改扩建","四民村四斗渠","2023-08-26","2023-12-31","乡村振兴局","渠道清淤及两边扫障",{"$f":"O39+P39+Q39+R39","v":10},10,0,0,0,1,126,458,0,12,35,{"v":1,"d":"100%"},"提高群众生产生活水平",null,"沅振发〔2023〕8号",10,"沅财农指〔2023〕14号"]
[33,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","四民村","道路硬化","改扩建","四民村四斗渠","2023-09-10","2023-12-31","乡村振兴局","公路硬化",20,20,0,0,0,1,126,458,0,12,35,{"v":1,"d":"100%"},"提高群众生产生活水平",null,"沅振发〔2023〕8号",20,"沅财农指〔2023〕14号"]
[34,"乡村建设行动","人居环境整治","村容村貌提升","草尾镇","双东村","渠道疏浚","改扩建","双东村六支渠","2023-09-10","2023-12-31","乡村振兴局","2公里",4,4,0,0,0,1,120,420,0,11,32,{"v":1,"d":"100%"},"提高群众生产生活水平",null,"沅振发〔2023〕8号",4,"沅财农指〔2023〕14号"]
[35,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","大福村","路基建设","改扩建","大福15组","2023-09-01","2023-12-31","乡村振兴局","居民线机耕道路长1250米",5,5,0,0,0,1,78,245,0,3,9,{"v":1,"d":"100%"},"提高群众生产生活水平",null,"沅振发〔2023〕8号",5,"沅财农指〔2023〕14号"]
[36,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","三码头村","危桥改造","改扩建","三码头村三组","2023-01-31","2023-12-31","乡村振兴局","1座",5,5,0,0,0,1,92,415,0,15,42,{"v":1,"d":"100%"},"提高群众生产生活水平",null,"沅振发〔2023〕8号",5,"沅财农指〔2023〕14号"]
[37,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","民主村","道路维修","改扩建","三支渠18组路段","2023-08-31","2023-12-31","乡村振兴局","400米",5,5,0,0,0,1,85,345,0,5,16,{"v":1,"d":"100%"},"提高群众生产生活水平",null,"沅振发〔2023〕8号",5,"沅财农指〔2023〕14号"]
[38,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","长乐村","道路硬化","改扩建","七组、十二组","2023-08-31","2023-12-31","乡村振兴局","两处",10,10,0,0,0,1,90,360,0,10,29,{"v":1,"d":"100%"},"提高群众生产生活水平",null,"沅振发〔2023〕8号",10,"沅财农指〔2023〕14号"]
[39,"乡村建设行动","人居环境整治","村容村貌提升","草尾镇","长乐村","渠道疏浚","改扩建","七组、十二组","2023-08-31","2023-12-31","乡村振兴局","两处",20,20,0,0,0,1,90,360,0,10,29,{"v":1,"d":"100%"},"提高群众生产生活水平",null,"沅振发〔2023〕8号",20,"沅财农指〔2023〕14号"]
[40,"乡村建设行动","人居环境整治","村容村貌提升","草尾镇","人益村","渠道疏浚","改扩建","民兵渠","2023-08-31","2023-12-31","乡村振兴局","2.2公里",5,5,0,0,0,1,105,409,0,10,28,{"v":1,"d":"100%"},"提高群众生产生活水平",null,"益阳",5,"沅财农指〔2023〕13号"]
[41,"产业发展","新型农村集体经济发展项目","新型农村集体经济发展项目","草尾镇","新安村","沅江市新安制衣有限公司","改扩建","新安小区原礼堂","2023-08-31","2023-12-31","组织部","500平方米",50,50,0,0,0,1,200,800,0,20,68,{"v":1,"d":"100%"},"提高群众生产生活水平",null,"中央、省",50,"沅财农指〔2023〕15号"]
[42,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","阳罗洲镇","跃进村","沅江市_村基础设施_阳罗洲镇2023年跃进村胜利渠公路维修","维修","阳罗洲镇跃进村","2023-10-22","2023-11-05","乡村振兴局","公路维修1公里",5,5,0,0,0,1,128,376,0,45,102,"受益农户人均年增收400元","带动生产",null,"益阳",5,"沅财农指〔2023〕13号"]
[43,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","阳罗洲镇","七子浃村","沅江市_村基础设施_阳罗洲镇2023年七子浃村10组8斗渠公路建设","新建","阳罗洲镇七子浃村","2023-09-01","2023-09-16","乡村振兴局","公路建设750米",{"$f":"O50+P50+Q50+R50","v":30},30,0,0,0,1,104,382,0,37,89,"受益农户人均年增收400元","带动生产",null,"沅振发〔2023〕8号",30,"沅财农指〔2023〕14号"]
[44,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","阳罗洲镇","候龙村","沅江市_村基础设施_阳罗洲镇2023年候龙村十一斗渠公路建设","新建","阳罗洲镇候龙村","2023-08-01","2023-08-16","乡村振兴局","公路维修400米",30,30,0,0,0,1,108,212,1,2,46,"受益农户人均年增收200元","方便农副产品运输",null,"沅振发〔2023〕8号",30,"沅财农指〔2023〕14号"]
[45,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","阳罗洲镇","吕丰村","沅江市_村基础设施_阳罗洲镇2023年吕丰村11支13斗-14斗公路硬化","维修","阳罗洲镇吕丰村","2023-11-08","2023-11-23","乡村振兴局","公路硬化400米",10,10,0,0,0,1,136,363,0,9,22,"受益农户人均年增收400元","带动生产",null,"沅振发〔2023〕8号",10,"沅财农指〔2023〕14号"]
[46,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","阳罗洲镇","宝三村","沅江市_村基础设施_阳罗洲镇2023年宝三村渔场育苗基地公路路基建设","新建","阳罗洲镇宝三村","2023-09-20","2023-09-28","乡村振兴局","公路路基建设650米",5,5,0,0,0,1,36,105,0,6,16,"受益农户人均年增收600元","带动生产",null,"沅振发〔2023〕8号",5,"沅财农指〔2023〕14号"]
[47,"产业发展","加工流通项目","加工业","阳罗洲镇","宝三村","沅江市_产业发展_阳罗洲镇2023年宝三村沅江市三辉电子有限公司","新建","阳罗洲镇宝三村","2023-10-20","2023-12-20","组织部","产业发展",50,50,0,0,0,1,112,213,0,90,201,"村集体经济收入每年增加6.8万、脱贫户及监测对象人均增收400元","就业务工、收益分红",null,"中央、省",50,"沅财农指〔2023〕15号"]
[48,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","四季红镇","玉鹊村","沅江市四季红镇玉鹊村七斗渠公路拓宽","扩建","玉鹊村","2023-06-27","2023-07-15","乡村振兴局","公路拓宽1米，长1220米",10,10,0,0,0,1,150,600,0,6,12,"改善群众生产生活条件、群众满意度≥100%","改善群众生产生活条件",null,"益阳",10,"沅财农指〔2023〕13号"]
[49,"产业发展","配套基础设施项目","小型农田水利设施建设","四季红镇","四季红村","沅江市四季红镇四季红村二组、四组菜园渠道建设","新建","四季红村","2023-10-12","2023-10-30","乡村振兴局","渠道建设600米",10,10,0,0,0,1,153,435,1,10,25,"改善群众生产生活条件、群众满意度≥100%","改善群众生产生活条件",null,"沅振发〔2023〕8号",10,"沅财农指〔2023〕14号"]
[50,"产业发展","配套基础设施项目","小型农田水利设施建设","四季红镇","四季红社区","沅江市四季红镇四季红社区七组沟渠建设","新建","社区七组","2023-10-10","2023-11-30","乡村振兴局","沟渠建设350米",15,10,0,0,5,1,36,176,0,2,4,"改善群众生产生活条件、群众满意度≥100%","改善群众生产生活条件",null,"沅振发〔2023〕8号",10,"沅财农指〔2023〕14号"]
[51,"产业发展","配套基础设施项目","小型农田水利设施建设","四季红镇","先锋村","沅江市四季红镇先锋村十四斗渠、十斗渠渠道疏浚","新建","先锋村","2023-09-02","2023-09-28","乡村振兴局","渠道疏浚2970米、土方工程",30,30,0,0,0,1,301,854,0,15,51,"改善群众生产生活条件、群众满意度≥100%","改善群众生产生活条件",null,"沅振发〔2023〕8号",30,"沅财农指〔2023〕14号"]
[52,"乡村建设行动","农村基础设施","农村道路建设","黄茅洲镇","黄茅洲村","路基拓宽","新建","黄茅洲村","2023-09-01","2023-10-01","乡村振兴局","路基拓宽300米",5,5,0,0,0,2,3511,10284,1,139,359,"受益建档立卡贫困人口满意度≥90%","方便群众出行",null,"沅振发〔2023〕8号",5,"沅财农指〔2023〕14号"]
[53,"乡村建设行动","农村基础设施","农村供水保障设施建设","黄茅洲镇","晒袍社区","新建机埠","新建","晒袍社区","2023-09-01","2023-12-01","乡村振兴局","1座",5,5,0,0,0,1,87,195,0,118,259,"受益建档立卡贫困人口满意度≥90%","方便群众灌溉",null,"沅振发〔2023〕8号",5,"沅财农指〔2023〕14号"]
[54,"乡村建设行动","农村基础设施","农村道路建设","黄茅洲镇","黄栗塘村","安南9组新建公路500米","新建","黄栗塘村","2023-10-01","2024-01-01","乡村振兴局","新建公路500米",5,5,0,0,0,2,1864,7949,0,116,282,"受益建档立卡贫困人口满意度≥95%","方便群众出行",null,"沅振发〔2023〕8号",5,"沅财农指〔2023〕14号"]
[55,"乡村建设行动","农村基础设施","农村道路建设","黄茅洲镇","志成垸村","公路加宽铺砾石至南堤","维修","志成垸村","2023-10-01","2023-12-01","乡村振兴局","填土铺砾石1200米",5,5,0,0,0,1,389,1521,0,138,378,"受益建档立卡贫困人口满意度≥90%","方便群众出行",null,"沅振发〔2023〕8号",5,"沅财农指〔2023〕14号"]
[56,"乡村建设行动","农村基础设施","农村道路建设","黄茅洲镇","肖家坝村","基础设施建设","新建","肖家坝村","2023-09-01","2023-10-01","乡村振兴局","道路配套设施建设",30,30,0,0,0,2,2847,5726,0,160,341,"受益建档立卡贫困人口满意度≥90%","方便群众出行",null,"沅振发〔2023〕8号",30,"沅财农指〔2023〕14号"]
[57,"产业发展项目","加工流通项目","冷农产品仓储保鲜冷链基础设施建设链库\n建设","黄茅洲镇","柳树坪村","冷链库建设","新建","柳树坪村\n二组","2023-10-01","2023-12-01","组织部","一个冷链库",50,50,0,0,0,1,1102,3088,0,63,131,"受益建档立卡贫困户满意度≥95％","增加集体\n经济收入",null,"中央、省",50,"沅财农指〔2023〕15号"]
[58,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","南大膳镇","华胜村","2023年南大膳镇华胜村明北渠公路硬化项目","新建","华胜村","2023-10-20","2023-11-20","乡村振兴局","新建公路130m",{"$f":"O65+P65+Q65+R65","v":5},5,0,0,0,1,62,174,0,18,42,"提高群众满意度","便利群众出行",null,"沅振发〔2023〕8号",5,"沅财农指〔2023〕14号"]
[59,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","南大膳镇","牛洲村","2023年南大膳镇牛洲村牛洲排渠南侧5-9组公路硬化及附属设施建设项目","新建","牛洲村","2023-10-20","2023-10-31","乡村振兴局","新建公路1000米及过道涵管、涵闸、护坡建设",52,52,0,0,0,1,127,412,0,30,90,"提高群众满意度","便利群众出行",null,"沅振发〔2023〕8号",52,"沅财农指〔2023〕14号"]
[60,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","南大膳镇","牛洲村","2023年南大膳镇牛洲村牛洲排渠南侧4组公路硬化及附属设施建设项目","新建","牛洲村","2023-10-20","2023-10-31","乡村振兴局","新建公路300米及路基处理，过道涵管、涵闸、护坡建设",16,16,0,0,0,1,33,102,0,10,30,"提高群众满意度","便利群众出行",null,"沅振发〔2023〕8号",16,"沅财农指〔2023〕14号"]
[61,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","南大膳镇","牛洲村","2023年南大膳镇牛洲村漉乐线北侧公路硬化及附属设施建设项目","新建","牛洲村","2023-10-19","2023-11-22","乡村振兴局","新建公路90米及附属设施",20,20,0,0,0,1,24,68,0,10,30,"提高群众满意度","便利群众出行",null,"沅振发〔2023〕8号",20,"沅财农指〔2023〕14号"]
[62,"乡村建设行动","人居环境整治","村容村貌提升","南大膳镇","牛洲村","2023年南大膳镇牛洲村人居环境提质改造项目","人居环境整治","牛洲村","2023-10-10","2023-10-31","乡村振兴局","水葫芦打捞、堵塞渠道清淤、杂草清理",30,30,0,0,0,1,425,1422,0,40,120,"提高群众满意度","人居环境整治建设，提升群众生活环境",null,"沅振发〔2023〕8号",30,"沅财农指〔2023〕14号"]
[63,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","南大膳镇","牛洲村","2023年南大膳镇牛洲村牛洲排渠桥梁建设项目","新建","牛洲村","2023-09-25","2023-10-22","乡村振兴局","新建5M宽桥梁一座",12,12,0,0,0,1,125,622,0,40,120,"提高群众满意度","便利群众出行",null,"沅振发〔2023〕8号",12,"沅财农指〔2023〕14号"]
[64,"产业发展项目","配套基础设施项目","产业园（区）","南大膳镇","众兴村","2023年沅江伦慧种粮合作社稻谷烘干厂扩建项目","扩建","众兴村","2023-10-20","2023-12-31","组织部","烘干机一台、稻谷输道带、提升机及厂房建设",50,50,0,0,0,1,70,210,0,20,60,"提高群众满意度","提高生产生活条件",null,"中央、省",50,"沅财农指〔2023〕15号"]
[65,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","共华镇","仁安村","共华镇-仁安村-基础设施-2023年仁安村仁东友谊渠公路路基建设","新建","仁安村仁东片","2023-10-01","2023-12-01","乡村振兴局","仁东友谊渠公路路基平整2100米",5,5,0,0,0,1,205,804,0,12,35,"受益群众满意度≥100%","提高群众生产生活水平",null,"沅振发〔2023〕8号",5,"沅财农指〔2023〕14号"]
[66,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","共华镇","双阜村","共华镇-双阜村-基础设施-2023年共华镇双阜村道路及附属设施建设","新建","双阜村","2023-10-01","2023-12-01","乡村振兴局","道路及配套设施建设",40,40,0,0,0,1,100,260,1,30,70,"受益群众满意度≥100%","提高群众生产生活水平",null,"县级\n200",40,"沅财农指〔2023〕5号"]
[67,"产业发展项目","配套基础设施项目","小型农田水利设施建设","共华镇","双阜村","共华镇-双阜村-基础设施-2023年共华镇双阜村农业基础设施建设","新建","双阜村","2023-10-01","2023-12-01","乡村振兴局","农业基础设施建设",30,30,0,0,0,1,100,260,1,30,70,"受益群众满意度≥100%","提高群众生产生活水平",null,"县级\n200",30,"沅财农指〔2023〕5号"]
[68,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","泗湖山镇","光复垸村","2023年泗湖山镇光复垸村-基础设施-光复垸村群益2组道路加宽","改建","群益片","2023-10-01","2023-11-01","乡村振兴局","道路加宽0.5千米",6,6,0,0,0,1,30,100,1,2,4,"受益脱贫人口满意度≥98%","完善村级基础设施，提高群众生产生活水平",null,"沅振发〔2023〕8号",6,"沅财农指〔2023〕14号"]
[69,"产业发展项目","生产项目","种植业基地","泗湖山镇","东安垸村","2023年泗湖山镇东安垸村-基础设施-泗湖山镇东安垸村万良种养专业合作社","新建","东安垸村","2023-09-01","2023-11-01","乡村振兴局","产业基地提质改造建设-安装广告牌、打药机房建设",{"$f":"O76+P76+Q76+R76","v":30},30,0,0,0,1,12,36,0,128,275,"受益脱贫人口满意度≥95%","①完善村级基础设施，提高群众生产生活水平；\n②方便全村贫困户与非贫困户农业生产。",null,"沅振发〔2023〕8号",30,"沅财农指〔2023〕14号"]
[70,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","泗湖山镇","坪塘岭村","2023年泗湖山镇坪塘岭村-基础设施-双洲片七组路基拓宽","新建","双洲片七组","2023-06-02","2023-10-02","乡村振兴局","路基拓宽1.5米",5,5,0,0,0,1,67,205,0,7,16,"受益脱贫人口满意度≥98%","①完善村级基础设施，提高群众生产生活水平；\n②方便全村贫困户与非贫困户农业生产。",null,"沅振发〔2023〕8号",5,"沅财农指〔2023〕14号"]
[71,"产业发展项目","配套基础设施项目","小型农田水利设施建设","泗湖山镇","泗湖山社区","2023年泗湖山镇泗湖山社区-产业发展-泗湖山村10组过水涵洞建设","新建","泗湖山村10组","2023-09-01","2023-11-01","乡村振兴局","涵洞长度20米，内宽0.8米，高1.2米，采用混凝土浇筑",5,5,0,0,0,1,22,35,1,1,2,"受益脱贫人口满意度≥98%","完善村级基础设施，提高群众生产生活水平"]
[72,"产业发展项目","生产项目","种植业基地","泗湖山镇","中和村","2023年泗湖山镇中和村-产业发展-沅江市兴胜特种养殖专业合作社","改建","中和村","2023-09-01","2028-09-01","组织部","种植水稻445亩",50,50,0,0,0,1,11,20,0,1,2,"受益脱贫人口满意度≥98%","①完善村级基础设施，提高群众生产生活水平；\n②壮大村级集体经济",null,"中央、省",50,"沅财农指〔2023〕16号"]
[73,"产业发展项目","生产项目","养殖业基地","茶盘洲镇","花果山村","茶盘洲镇六合河渔业发展配套设施建设","改建","花果山村","2023-06-22","2023-12-20","茶盘洲镇","生态养殖\n渔塘150亩",10,10,0,0,0,1,58,182,0,10,28,"渔塘护坡\n800米","确保生态\n养殖发展",null,"中央81",10,"沅财农指〔2023〕11号"]
[74,"产业发展项目","生产项目","种植业基地","茶盘洲镇","幸福港社区","茶盘洲镇采摘园配套设施建设项目","改建","茶盘洲镇采摘园","2023-03-10","2023-10-30","茶盘洲镇","采摘园配套设施改建、加固、添置",30,30,0,0,0,1,2608,4005,0,0,0,"50亩采摘园配套设施改建、加固、添置","确保农产品旱涝保收,提升居民再就业",null,"中央81",30]
[75,"产业发展项目","生产项目","种植业基地","茶盘洲镇","六合村","茶盘洲镇六合村蔬菜基地配套设施建设项目","新建","六合村","2023-04-10","2023-07-01","茶盘洲镇","茶盘洲镇六合村蔬菜基地配套设施建设项目",25,25,0,0,0,1,24,68,1,7,16,"基地地质提升及周边道路、渠道维修。","方便群众出行和产品的运输，带动群众致富。",null,"中央81",25,"沅财农指〔2023〕11号"]
[76,"产业发展项目","生产项目","水产养殖业发展","茶盘洲镇","南洲街社区（天心渔村）","茶盘洲镇场部河渔业发展配套设施建设项目","改建","天心渔村","2023-03-10","2023-10-30","茶盘洲镇","场部河配套设施改建、加固、添置",16,16,0,0,0,1,455,854,0,13,23,"场部河配套设施改建、加固、添置","带动经济发展",null,"中央81",16,"沅财农指〔2023〕11号"]
[77,"产业发展项目","配套基础设施项目","小型农田水利设施建设","茶盘洲镇","柴洲包村","茶盘洲镇柴洲包村南公路排渠疏浚工程","新建","柴洲包村1.2.5组南公路排渠","2023-10-15","2023-12-20","乡村振兴局","捞杂草、清淤3000米",5.2,5,0,0,0.2,1,308,1202,0,12,43,"便于南公路排渠两旁3200亩耕地灌溉","其他",null,"沅振发〔2023〕8号",5,"沅财农指〔2023〕14号"]
[78,"产业发展项目","生产项目","种植业基地","南洞庭湿地保护与发展事务中心","东头嘴社区","东头嘴社区农村基础设施-产业项目建设","新建","东头嘴社区","2023-01-01","2023-12-31","乡村振兴局","稻虾共作350亩",{"$f":"O85+P85+Q85+R85","v":14},14,0,0,0,1,570,1417,0,53,137,"群众满意度100%","1.增加村集体经济收入；2.提供就业岗位，增加群众收入；3.监测户能享受保底分红。",null,"沅振发〔2022〕16号",14,"沅财农指〔2023〕1号"]
[79,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","南洞庭湿地保护与发展事务中心","东头嘴社区","东头嘴社区农村基础设施-农村道路建设","新建","东头嘴社区","2023-01-01","2023-12-31","乡村振兴局","道路硬化一公里",40,40,0,0,0,1,570,1417,0,53,137,"群众满意度100%","①提高群众生产生活水平②便利群众出行③解决53户脱贫户（其中监测户5户）的农产品运输问题",null,"沅振发〔2022〕16号",40,"沅财农指〔2023〕1号"]
[80,"产业发展项目","生产项目","水产养殖业发展","南洞庭湿地保护与发展事务中心","五花洲社区","五花洲社区农村产业项目-五花洲社区特种水产高密度养殖项目","新建","五花洲社区徐家岭四队","2023-01-29","2023-05-31","乡村振兴局","高密度养鱼，面积28亩",16,16,0,0,0,1,1439,3468,1,114,284,"群众满意度100%","1.增加村集体经济收入；2.提供就业岗位，增加群众收入；3.监测户能享受保底分红",null,"沅振发〔2022〕16号",16,"沅财农指〔2023〕1号"]
[81,"产业发展项目","加工流通项目","农产品仓储保鲜冷链基础设施建设","南洞庭湿地保护与发展事务中心","大码头村","大码头村农村基础设施-农产品冷链物流建设","新建","大码头村","2023-09-01","2023-12-31","组织部","农产品冷链物流建设项目",50,50,0,0,0,1,520,2068,0,58,164,"群众满意度100%","1.增加村集体经济收入；2.提供就业岗位，增加群众收入；3.监测户能享受保底分红。",null,"中央、省",50,"沅财农指〔2023〕16号"]
[82,"产业发展项目","配套基础设施项目","小型农田水利设施建设","南洞庭湿地保护与发展事务中心","东头嘴社区","东头嘴社区产业发展项目-出水沟护坡、拓宽","新建","东头嘴社区","2023-09-01","2023-12-31","乡村振兴局","东头嘴社区出水沟护坡、拓宽",10,10,0,0,0,1,570,1417,1,54,137,"群众满意度100%","①提高群众生产生活水平②便利群众出行③解决53户脱贫户（其中监测户5户）的农产品运输问题",null,"沅振发〔2023〕8号",10,"沅财农指〔2023〕14号"]
[82,"合计",{"$nulls":11},4510.14,{"$f":"SUM(O8:O89)","v":4485.94},{"$f":"SUM(P8:P89)","v":0},{"$f":"SUM(Q8:Q89)","v":0},{"$f":"SUM(R8:R89)","v":24.2}]