{"text_format":"3","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"defined_names":3},"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":206,"n_cols":27,"rows_kept":206,"merged":[[1,0,1,26],[3,0,3,26],[5,0,7,0],[5,1,5,3],[5,4,7,4],[5,5,7,5],[5,6,7,6],[5,7,7,7],[5,8,7,8],[5,9,5,10],[5,11,7,11],[5,12,7,12],[5,13,5,17],[5,18,5,23],[5,24,7,24],[5,25,7,25],[5,26,7,26],[6,1,7,1],[6,2,7,2],[6,3,7,3],[6,9,7,9],[6,10,7,10],[6,13,7,13],[6,14,6,17],[6,18,7,18],[6,19,7,19],[6,20,7,20],[6,21,6,23],[205,0,205,26]]}
["附件2"]
["沅江市2024年度巩固拓展脱贫攻坚成果和乡村振兴项目库储备项目申报表（新增入库）"]
[]
["单位：（盖章）                                                                                                                                                                                                                      时间：2023年11月"]
[]
["序号","项目类别",null,null,"乡","村","项目名称","建设性质","实施地点","时间进度",null,"责任单位","建设内容及规模","资金规模和筹资方式",{"$nulls":4},"受益对象",{"$nulls":5},"绩效目标","联农带农机制","备注"]
[null,"项目类型","二级项目类型","项目子类型",{"$nulls":5},"计划开工时间","计划完工时间",null,null,"项目预算总投资（万元）","其中",{"$nulls":3},"受益村数（个）","受益户数（户）","受益人口数（人）","其中"]
[{"$nulls":14},"财政衔接资金（万元）","除财政衔接资金外的统筹整资金（万元）","其他财政资金（万元）","其他筹措资金（万元）",{"$nulls":3},"受益脱贫村数（个）","受益脱贫户数及防止返贫监测对象户数（户）","受益脱贫人口数及防止返贫监测对象人口数（人）"]
[1,"产业发展项目","配套基础设施项目","小型农田水利设施建设","胭脂湖街道","洞兴村","洞兴村山塘改造","改建","洞兴村","2024-01-01","2024-03-01","乡村振兴局","洞兴村14口山塘改造，清淤增蓄",{"$f":"O9+P9+Q9+R9","v":52},52,0,0,0,1,530,1600,0,40,80,"山塘改造，便于蓄水抗旱，增产增收","1、带动地方产业发展\n2、满足群众农业灌溉用水需求\n3、提高群众生产生活水平"]
[2,"产业发展项目","配套基础设施项目","小型农田水利设施建设","胭脂湖街道","海上社区","海上社区山塘清淤增蓄","新建","海上社区二、五、六、七组","2024-05-01","2024-11-01","乡村振兴局","海上社区二、五、六、七组五口山塘清淤",20,20,0,0,0,1,225,860,0,14,37,"方便农业灌溉，达到增收致富","①提高群众生产生活水平②便利农业灌溉"]
[3,"产业发展项目","配套基础设施项目","小型农田水利设施建设","胭脂湖街道","荷花村","荷花村山塘清淤增蓄建设","新建","荷花村一、三、六、七组","2024-05-01","2024-11-01","乡村振兴局","丁边塘、河塘冲塘、下边塘、光伟塘、圆塘几塘的清淤建设",10,10,0,0,0,1,980,2700,1,42,116,"方便群众生产达到增收","提高群众生产生活水平"]
[4,"产业发展项目","配套基础设施项目","小型农田水利设施建设","胭脂湖街道","黄家湖村","黄家湖村山塘清淤","扩建","黄家湖村","2024-01-01","2024-02-01","乡村振兴局","山塘清\n淤扩容",6,6,0,0,0,1,125,372,0,6,21,"项目（工程）验收合格率100%","①提高群众生产生活水平②周边农户增收，增加集体收入，助推乡村振兴"]
[5,"产业发展项目","配套基础设施项目","小型农田水利设施建设","胭脂湖街道","十里坪村","十里坪村山塘整修工程","新建","十里坪村","2024-01-01","2024-02-01","乡村振兴局","山塘整修",28,28,0,0,0,1,800,3000,0,2,6,"项目工程验收合格率100%","1.提高群众生产生活水平。2.带动农业发展。"]
[6,"产业发展项目","配套基础设施项目","小型农田水利设施建设","胭脂湖街道","胭脂湖村","胭脂湖村山塘清淤","扩建","胭脂湖村","2024-01-01","2024-04-01","乡村振兴局","山塘清\n淤扩容",16,16,0,0,0,1,309,906,0,13,32,"项目（工程）验收合格率100%","①提高群众生产生活水平②周边农户增收，增加集体收入，助推乡村振兴"]
[7,"产业发展项目","配套基础设施项目","小型农田水利设施建设","胭脂湖街道","杨梅山村","杨梅山村山塘清淤","扩建","杨梅山一、五、四、九、六、二、十二、七组","2024-03-01","2024-06-01","乡村振兴局","山塘清\n淤扩容",34,34,0,0,0,1,2403,6637,1,128,354,"方便群众生产达到增收","①提高群众生产生活水平②周边农户增收，增加集体收入，助推乡村振兴"]
[8,"产业发展项目","配套基础设施项目","小型农田水利设施建设","胭脂湖街道","赤塘村","赤塘村山塘\n清淤","扩建","赤塘村","2024-01-01","2024-04-01","乡村振兴局","山塘清淤7口塘",14,14,0,0,0,1,888,2588,0,56,141,"项目（工程）验收合格率100%","①提高群众生产生活水平②周边农户增收，增加集体收入，助推乡村振兴"]
[9,"产业发展项目","配套基础设施项目","小型农田水利设施建设","胭脂湖街道","焦山咀村","焦山咀村山塘清淤基础设施建设项目","改建","焦山咀村","2024-01-01","2024-12-01","乡村振兴局","1组大塘、18组刘家塘、7组茶元村塘、20组塘眼村下边塘共4口山塘清淤",10,10,0,0,0,1,360,1032,0,34,65,"促进农业经济发展，带动农户增收增产，积极发展生产，指导农户参与分享收益，带动乡村振兴和周边农民脱贫致富增收","1、提高群众生产生活水平，为130余亩农田提供水利条件\n2、提高群众生活满意度"]
[10,"产业发展项目","配套基础设施项目","小型农田水利设施建设","胭脂湖街道","莲子塘村","莲子塘村山塘清淤基础设施建设项目","扩建","莲子塘村","2024-04-01","2024-12-01","乡村振兴局","13口山塘清\n淤扩容",32,32,0,0,0,1,628,1895,0,19,46,"促进农业经济发展，带动农户增收增产，积极发展生产，指导农户参与分享收益，带动乡村振兴和周边农民脱贫致富增收","1、提高群众生产生活水平，为540余亩农田提供水利条件\n2、提高群众生活满意度"]
[11,"产业发展项目","配套基础设施项目","小型农田水利设施建设","胭脂湖街道","南竹山村","南竹山村山塘清淤","维修","南竹山村","2024-01-01","2024-04-01","乡村振兴局","13个塘82.9亩",32,32,0,0,0,1,862,3099,0,47,141,"促进农业经济发展，带动农户增收增产，公司积极发展生产，开拓市场，指导农户参与分享收益，带动乡村振兴和周边农民脱贫致富增收","1、带动地方产业发展\n2、新增就业岗位7、打造红色观光产业园"]
[12,"产业发展项目","配套基础设施项目","小型农田水利设施建设","胭脂湖街道","三眼塘村","三眼塘村山塘清淤","扩建","三眼塘村","2024-01-01","2024-03-01","乡村振兴局","山塘清\n淤扩容",54,54,0,0,0,1,830,2480,0,44,89,"项目（工程）验收合格率100%","①提高群众生产生活水平②周边农户增收，增加集体收入，助推乡村振兴"]
[13,"产业发展项目","配套基础设施项目","小型农田水利设施建设","胭脂湖街道","先锋村","先锋村山塘清淤增蓄工程","新建","先锋村1、4、5、6、10、18、19组","2024-01-01","2024-04-01","乡村振兴局","对村内11口山塘进行清淤增蓄",30,30,0,0,0,1,816,3520,0,69,152,"增加灌溉用水量，提高农业综合生产能力，为乡村振兴提供有力保障","1、带动农业增产增收\n2、提升人居环境"]
[14,"产业发展项目","配套基础设施项目","小型农田水利设施建设","胭脂湖街道","永建村","永建村山塘\n清淤","扩建","永\n建\n村","2024-01-01","2024-04-01","乡村振兴局","山塘清\n淤扩容",30,30,0,0,0,1,850,2860,0,30,80,"项目（工程）验收合格率100%","①提高群众生产生活水平②周边农户增收，增加集体收入，助推乡村振兴"]
[15,"产业发展项目","配套基础设施项目","小型农田水利设施建设","胭脂湖街道","回龙山村","回龙山村山塘清淤增蓄","改扩建","一组罗塘、光塘\n二组李家湾塘、\n五组湾前塘、\n八组屋面前大塘、大荷叶塘、\n九组鲤鱼塘、\n十组上边塘、\n十一组罗卜塘、\n十二组朱家塘、\n十三组大塘","2024-01-01","2024-08-01","乡村振兴局","清淤11口",32,32,0,0,0,1,728,2948,0,33,72,"使农民增产增收，\n预计全村人平增收150元","能保障村民旱涝保收，\n提高农民种粮积极性，\n带动农业生产全面发展。"]
[1,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","新湾镇","老屋冲村","老屋冲村一至二组道路加宽","改扩建","老屋冲村一组、二组","2024-04-01","2024-05-01","老屋冲村","道路加宽1.5米",{"$f":"O24+P24+Q24+R24","v":15},15,0,0,0,1,70,190,1,5,14,"项目带动脱贫人口直接受益14人","①提高群众生产生活水平\n②解决脱贫户5户14人的出行便利问题"]
[2,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","新湾镇","老屋冲村","老屋冲村七组300米毛坯路硬化","改扩建","老屋冲村七组","2024-06-01","2024-07-01","老屋冲村","3.5米道路硬化300米",10,10,0,0,0,1,30,100,1,2,10,"目带动脱贫人口直接受益10人","①提高群众生产生活水平\n②解决脱贫户2户10人的出行便利问题"]
[3,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","新湾镇","杨阁老村","七丘组至唐家嘴组道路拓宽","基础设施建设","杨阁老村","2024-01-01","2024-02-01","杨阁老村","七丘至唐家嘴组道路3公里拓宽1.5米",60,60,0,0,0,1,316,693,1,12,29,"项目带动脱贫人口直接受益29人","①提高群众生产生活水平②解决脱贫户12户29人的出行和农副产品运输"]
[4,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","新湾镇","杨阁老村","张九如屋旁至七丘李建军屋前拓宽","基础设施建设","杨阁老村","2024-02-01","2024-03-01","杨阁老村","400米道路拓宽1.5米",4,4,0,0,0,1,39,102,1,5,10,"项目带动脱贫人口直接受益10人","①提高群众生产生活水平②解决脱贫户5户10人的出行和农副产品运输"]
[5,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","新湾镇","杨阁老村","烈士路李介华屋旁至嘴角组道路拓宽","基础设施建设","杨阁老村","2024-03-01","2024-04-01","杨阁老村","1.5公里道路拓宽1.5米",30,30,0,0,0,1,287,652,1,11,23,"项目带动脱贫人口直接受益23人","①提高群众生产生活水平②解决脱贫户11户23人的出行和农副产品运输"]
[6,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","新湾镇","杨阁老村","杨家组道路拓宽","基础设施建设","杨阁老村","2024-01-01","2024-02-01","杨阁老村","500米道路拓宽1.5米",5,5,0,0,0,1,43,139,1,6,14,"项目带动脱贫人口直接受益14人","①提高群众生产生活水平②解决脱贫户6户14人的出行和农副产品运输"]
[7,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","新湾镇","莲花村","道路拓宽","新建","莲花村杉合片","2024-05-01","2024-12-01","莲花村","公路拓宽1米，长2公里",25,25,0,0,0,1,196,687,1,5,12,"项目带动脱贫人口直接受益12人","提高群众生产生活水平，解决脱贫户5户12人道路出行问题"]
[8,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","新湾镇","周公湖村","道路拓宽","新建","周公湖村龙山片","2024-03-01","2024-12-01","周公湖村","公路拓宽1米，长1.5公里",20,20,0,0,0,1,105,410,1,5,12,"项目带动脱贫人口直接受益12人","提高群众生产生活水平，解决脱贫户5户12人道路出行问题"]
[9,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","新湾镇","周公湖村","道路拓宽","新建","周公湖村柏村片","2024-03-01","2024-12-01","周公湖村","公路拓宽1米，长2公里",25,25,0,0,0,1,130,469,1,8,16,"项目带动脱贫人口直接受益16人","提高群众生产生活水平，解决脱贫户8户16人道路出行问题"]
[10,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","新湾镇","周公湖村","红军公路硬化","新建","周公湖村红星组","2024-03-01","2024-12-01","周公湖村","公路硬化380米，宽3.5米",17,17,0,0,0,1,10,32,1,2,5,"项目带动脱贫人口直接受益5人","提高群众生产生活水平，解决脱贫户2户5人道路出行问题"]
[11,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","新湾镇","周公湖村","爱保公路硬化","新建","周公湖村金明组","2024-03-01","2024-12-01","周公湖村","公路硬化400米，宽3.5米",18,18,0,0,0,1,10,35,1,3,8,"项目带动脱贫人口直接受益8人","提高群众生产生活水平，解决脱贫户3户8人道路出行问题"]
[12,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","新湾镇","周公湖村","跃华公路硬化","新建","周公湖村金明组","2024-03-01","2024-12-01","周公湖村","公路硬化420米，宽3.5米",18.9,18.9,0,0,0,1,11,38,1,2,5,"项目带动脱贫人口直接受益5人","提高群众生产生活水平，解决脱贫户2户5人道路出行问题"]
[1,"产业发展项目","生产项目","种植业基地","南嘴镇","兴南村","柑桔品改","扩建","兴南村","2024-03-01","2024-07-01","兴南村","高标准品改180亩",{"$f":"O36+P36+Q36+R36","v":140},140,0,0,0,1,26,64,0,5,9,"满意度指标、服务对象满意度指标、受益建档立卡贫困人口满意度≥95%","完善村级基础设施，提高群众生产生活水平。"]
[2,"产业发展项目","加工流通项目","农产品仓储保鲜冷链基础设施建设","南嘴镇","兴南村","兴南仓储","新建","兴南村","2024-01-01","2024-04-01","兴南村","新建300平方仓储",55,55,0,0,0,1,41,102,0,15,30,"满意度指标、服务对象满意度指标、受益建档立卡贫困人口满意度≥95%","完善村级基础设施，提高群众生产生活水平。"]
[3,"乡村建设行动","农村基础设施","产业路、资源路、旅游路建设","南嘴镇","兴南村","产业路配套设施建设","新建","兴南村","2024-01-01","2024-12-01","兴南村","1.8公里",40,40,0,0,0,1,129,278,0,25,48,"满意度指标、服务对象满意度指标、受益建档立卡贫困人口满意度≥95%","完善村级基础设施，提高群众生产生活水平。"]
[4,"乡村建设行动","人居环境整治","农村垃圾治理","南嘴镇","兴南村","人居环境整治","新建","兴南村","2024-01-01","2024-12-01","兴南村","主干道五公里路边居民房前屋后环境整治",35,35,0,0,0,1,232,521,0,29,55,"满意度指标、服务对象满意度指标、受益建档立卡贫困人口满意度≥95%","完善村级基础设施，提高群众生产生活水平。"]
[5,"产业发展项目","生产项目","种植业基地","南嘴镇","目北村","冻库建设","新建","目北村","2024-01-01","2024-06-01","目北村","200m³",50,50,0,0,0,2,308,920,0,110,330,"满意度指标、服务对象满意度指标、受益建档立卡贫困人口满意度≥95%","完善村级基础设施，提高群众生产生活水平。"]
[6,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","南嘴镇","目北村","公路硬化","新建","目北村","2024-07-01","2024-11-01","目北村","道路硬化3公里",160,160,0,0,0,1,279,830,0,21,66,"通过通行质量，保证生产","保证农户的农产品通行"]
[7,"乡村建设行动","人居环境整治","村容村貌提升","南嘴镇","目北村","人居环境整治","新建","目北村","2024-01-01","2024-12-01","目北村","主干道三公里路边居民房前屋后环境整治",20,20,0,0,0,1,33,92,0,16,48,"群众人口满意度百分之百","优化人居环境"]
[8,"产业发展项目","配套基础设施项目","小型农田水利设施建设","南嘴镇","目平湖南村","农田排灌设施","新建","目平湖南村","2024-01-01","2024-12-01","目平湖南村","3公里",30,30,0,0,0,1,264,550,1,20,43,"满意度指标、服务对象满意度指标、受益建档立卡贫困人口满意度≥95%","完善村级基础设施，提高群众生产生活水平。"]
[9,"乡村建设行动","人居环境整治","村容村貌提升","南嘴镇","目平湖南村","人居环境整治","新建","目平湖南村","2024-01-01","2024-12-01","目平湖南村","30公里",20,20,0,0,0,1,922,2239,1,108,210,"满意度指标、服务对象满意度指标、受益建档立卡贫困人口满意度≥95%","完善村级基础设施，提高群众生产生活水平。"]
[10,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","南嘴镇","新南社区","公路建设","维修加宽","新南社区","2024-01-01","2024-12-01","新南社区","2公里",80,80,0,0,0,1,320,680,0,22,51,"满意度指标、服务对象满意度指标、受益建档立卡贫困人口满意度≥95%","完善村级基础设施，提高群众生产生活水平。"]
[11,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","南嘴镇","百家沟村","百家沟村农村公路建设","新建","百家沟村","2024-03-01","2024-12-01","百家沟村","新建3公里农村公路硬化",120,120,0,0,0,1,1488,4247,1,118,277,"满意度指标、服务对象满意度指标、受益建档立卡贫困人口满意度≥95%","①完善村级基础设施，提高群众生产生活水平；\n②增加村集体经济，带动群众增收增产。"]
[12,"产业发展项目","配套基础设施项目","小型农田水利设施建设","南嘴镇","百家沟村","百家沟村渠道整修建设","新建","百家沟村","2024-03-01","2024-12-01","百家沟村","3公里渠道整修",30,30,0,0,0,1,1488,4247,1,118,277,"满意度指标、服务对象满意度指标、受益建档立卡贫困人口满意度≥95%","①完善村级基础设施，提高群众生产生活水平；\n②增加村集体经济，带动群众增收增产。"]
[13,"产业发展项目","配套基础设施项目","小型农田水利设施建设","南嘴镇","百家沟村","山塘水库护坡","新建","百家沟村","2024-03-01","2024-12-01","百家沟村","三口山塘水库护坡",30,30,0,0,0,1,1488,4247,1,118,277,"满意度指标、服务对象满意度指标、受益建档立卡贫困人口满意度≥95%","①完善村级基础设施，提高群众生产生活水平；\n②增加村集体经济，带动群众增收增产。"]
[14,"产业发展项目","生产项目","种植业基地","南嘴镇","百家沟村","红薯种植基地扩建","新建","百家沟村","2024-02-01","2024-12-01","百家沟村","新建500亩红薯种植基地",80,80,0,0,0,1,1488,4247,1,118,277,"满意度指标、服务对象满意度指标、受益建档立卡贫困人口满意度≥95%","①完善村级基础设施，提高群众生产生活水平；\n②增加村集体经济，带动群众增收增产。"]
[15,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","南嘴镇","和谐村","农村道路建设","新建","和谐村","2024-03-01","2024-12-01","和谐村","公路硬化",40,40,0,0,0,1,23,55,0,2,5,"受益脱贫（监测）户满意度≥100%","完善村级基础设施，提高群众生产生活水平。"]
[16,"产业发展项目","生产项目","种植业基地","南嘴镇","南嘴村","品种改良","新建","南嘴村","2024-02-01","2024-05-01","南嘴村","1000亩",200,200,0,0,0,1,544,2354,0,44,81,"满意度指标、服务对象满意度指标、受益建档立卡贫困人口满意度≥95%","完善村级基础设施，提高群众生产生活水平。"]
[17,"乡村建设行动","农村基础设施","产业路、资源路、旅游路建设","南嘴镇","南嘴村","警民路建设","新建","南嘴村","2024-04-01","2024-05-01","南嘴村","10公里",50,50,0,0,0,1,230,491,0,23,47,"满意度指标、服务对象满意度指标、受益建档立卡贫困人口满意度≥95%","完善村级基础设施，提高群众生产生活水平。"]
[18,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","南嘴镇","南嘴村","公路硬化","新建","南嘴村","2024-03-01","2024-04-01","南嘴村","1.5公里",60,60,0,0,0,1,122,320,0,15,21,"满意度指标、服务对象满意度指标、受益建档立卡贫困人口满意度≥95%","完善村级基础设施，提高群众生产生活水平。"]
[19,"产业发展项目","新型农村集体经济发展项目","新型农村集体经济发展项目","南嘴镇","南嘴村","茶油厂设备扩建","购置","南嘴村","2024-08-01","2024-08-01","南嘴村","1套",80,80,0,0,0,1,280,557,0,53,103,"满意度指标、服务对象满意度指标、受益建档立卡贫困人口满意度≥95%","完善村级基础设施，提高群众生产生活水平。"]
[20,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","南嘴镇","蠡山村","道路硬化","新建","金新花组","2024-03-01","2024-12-01","蠡山村","硬化550米道路",20,20,0,0,0,1,17,55,0,2,5,"满意度指标、服务对象满意度指标、受益建档立卡贫困人口满意度≥95%","完善村级基础设施，提高群众生产生活水平；畅通农产品销售。"]
[21,"乡村建设行动","人居环境整治","农村垃圾治理","南嘴镇","蠡山村","人居环境整治","新建","全村","2024-04-01","2024-12-01","蠡山村","全村环境整治",10,10,0,0,0,1,1351,3562,0,83,179,"满意度指标、服务对象满意度指标、受益建档立卡贫困人口满意度≥95%","完善村级基础设施，提高群众生活质量。"]
[1,"乡村建设行动","人居环境整治","村容村貌提升","草尾镇","草尾社区","渠道硬化","改扩建","草尾社区\n易地搬迁","2024-01-01","2024-12-01","乡村振兴局","2处",{"$f":"O57+P57+Q57+R57","v":15},15,0,0,0,1,92,296,0,44,136,"满意度100%","提高群众生产生活水平"]
[2,"乡村建设行动","人居环境整治","村容村貌提升","草尾镇","长乐村","渠道护坡","新建","长乐村","2024-01-01","2024-12-01","乡村振兴局","1公里",18,18,0,0,0,1,68,196,0,12,38,"满意度100%","提高群众生产生活水平"]
[3,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","长乐村","公路硬化","新建","长乐村","2024-01-01","2024-12-01","乡村振兴局","3公里",23,23,0,0,0,1,124,368,0,26,76,"满意度100%","提高群众生产生活水平"]
[4,"乡村建设行动","人居环境整治","村容村貌提升","草尾镇","新安村","渠道疏洗","改扩建","新安村","2024-01-01","2024-12-01","乡村振兴局","2公里",5,5,0,0,0,1,37,114,0,6,18,"满意度100%","提高群众生产生活水平"]
[5,"乡村建设行动","人居环境整治","村容村貌提升","草尾镇","双东村","渠道疏洗","改扩建","双东村","2024-01-01","2024-12-01","乡村振兴局","2000米",8,8,0,0,0,1,120,872,0,22,51,"满意度100%","提高群众生产生活水平"]
[6,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","双东村","公路维护","改扩建","双东村","2024-01-01","2024-12-01","乡村振兴局","200米",8,8,0,0,0,1,260,1423,0,35,92,"满意度100%","提高群众生产生活水平"]
[7,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","双东村","涵洞维修","改扩建","双东村","2024-01-01","2024-12-01","乡村振兴局","4座",8,8,0,0,0,1,230,1268,0,24,57,"满意度100%","提高群众生产生活水平"]
[8,"乡村建设行动","人居环境整治","村容村貌提升","草尾镇","上码头村","渠道疏洗","改扩建","上码头村","2024-01-01","2024-12-01","乡村振兴局","3000米",10,10,0,0,0,1,160,963,0,21,46,"满意度100%","提高群众生产生活水平"]
[9,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","上码头村","公路维护","改扩建","上码头村","2024-01-01","2024-12-01","乡村振兴局","350米",8,8,0,0,0,1,270,1523,0,25,54,"满意度100%","提高群众生产生活水平"]
[10,"产业发展项目","配套基础设施项目","小型农田水利设施建设","草尾镇","上码头村","电排建设","改扩建","上码头村","2024-01-01","2024-12-01","乡村振兴局","排涝机埠建设2处",15,15,0,0,0,1,654,2780,0,22,54,"满意度100%","提高群众生产生活水平"]
[11,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","三星村","公路新建","改扩建","三星村新胜5、6、14组，三星渠","2024-05-01","2024-12-01","乡村振兴局","居民线路7000米",15,15,0,0,0,1,210,634,0,38,86,"满意度100%","提高群众生产生活水平"]
[12,"乡村建设行动","人居环境整治","村容村貌提升","草尾镇","三星村","渠道清淤","改扩建","三星村","2024-05-01","2024-06-01","乡村振兴局","渠道清淤约7000米",10,10,0,0,0,1,1483,1900,0,113,269,"满意度100%","提高群众生产生活水平"]
[13,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","三星村","公路加宽硬化","改扩建","三星村","2024-06-01","2024-08-01","乡村振兴局","居民线路加宽5000米",10,10,0,0,0,1,238,1380,0,113,269,"满意度100%","提高群众生产生活水平"]
[14,"产业发展项目","配套基础设施项目","小型农田水利设施建设","草尾镇","三星村","电排建设","改扩建","三星村新胜13组","2024-03-01","2024-05-01","乡村振兴局","新建机埠",10,10,0,0,0,1,1300,4300,0,113,269,"满意度100%","提高群众生产生活水平"]
[15,"产业发展项目","配套基础设施项目","小型农田水利设施建设","草尾镇","三星村","灌渠硬化","改扩建","三星村7、9、10、15组","2024-08-01","2024-11-01","乡村振兴局","灌渠硬化长约4000米",10,10,0,0,0,1,430,1700,0,69,139,"满意度100%","提高群众生产生活水平"]
[16,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","三星村","公路硬化","道路提升改质","三星村","2024-02-01","2024-12-01","乡村振兴局","公路硬化",80,80,0,0,0,1,1530,5730,0,113,269,"满意度100%","提高群众生产生活水平"]
[17,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","人和村","公路硬化","改扩建","人和村","2024-01-01","2024-12-01","乡村振兴局","0.4公里",28,28,0,0,0,1,56,209,0,8,26,"满意度100%","提高群众生产生活水平"]
[18,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","民主村","道路维修","维修","民主村五支渠、二支渠","2024-01-01","2024-12-01","乡村振兴局","17500米",20,20,0,0,0,1,84,379,0,23,76,"满意度100%","提高群众生产生活水平"]
[19,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","民主村","新建桥梁","新建","16组与17组交界处","2024-01-01","2024-12-01","乡村振兴局","1座",10,10,0,0,0,1,170,684,0,37,112,"满意度100%","提高群众生产生活水平"]
[20,"乡村建设行动","人居环境整治","村容村貌提升","草尾镇","东红村","渠道疏洗","改扩建","东红村","2024-01-01","2024-12-01","乡村振兴局","1500米",8,8,0,0,0,1,40,178,0,18,76,"满意度100%","提高群众生产生活水平"]
[21,"乡村建设行动","人居环境整治","村容村貌提升","草尾镇","大同闸村","渠道疏洗","改扩建","大同闸村","2024-01-01","2024-12-01","乡村振兴局","1500米",10,10,0,0,0,1,210,892,0,24,62,"满意度100%","提高群众生产生活水平"]
[22,"乡村建设行动","人居环境整治","村容村貌提升","草尾镇","大福村","渠道疏洗","改扩建","大福村","2024-01-01","2024-12-01","乡村振兴局","3000米",10,10,0,0,0,1,210,892,0,24,62,"满意度100%","提高沟渠排灌能力，提升人居环境质量"]
[23,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","大福村","机耕道路基平整","改扩建","大福村大丰片3-5组居民线","2024-01-01","2024-12-01","乡村振兴局","米",5,5,0,0,0,1,120,450,0,12,25,"满意度100%","提升道路运输能力，消除道路交通安全隐患，提高人居环境质量。"]
[24,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","大福村","桥梁拱改平","改扩建","动脉渠公路中心桥","2024-01-01","2024-12-01","乡村振兴局","1座",10,10,0,0,0,1,450,1450,0,32,48,"满意度100%","提升道路运输能力，消除道路交通安全隐患。"]
[25,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","保安垸村","渠道梳洗","改扩建","保安垸村","2024-01-01","2024-12-01","乡村振兴局","3500米",12,12,0,0,0,1,112,268,0,26,38,"满意度100%","提高群众生产生活水平"]
[26,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","保安垸村","公路维修","改扩建","保安垸村","2024-01-01","2024-12-01","乡村振兴局","300米",18,18,0,0,0,1,168,296,0,12,38,"满意度100%","提高群众生产生活水平"]
[27,"乡村建设行动","人居环境整治","村容村貌提升","草尾镇","熙和村","渠道疏洗","改扩建","熙和村","2024-01-01","2024-12-01","乡村振兴局","2000米",5,5,0,0,0,1,125,893,0,23,61,"满意度100%","提高群众生产生活水平"]
[28,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","熙和村","公路维护","改扩建","熙和村","2024-01-01","2024-12-01","乡村振兴局","140米",5,5,0,0,0,1,253,1136,0,31,89,"满意度100%","提高群众生产生活水平"]
[29,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","熙和村","危桥改造","改扩建","熙和村","2024-01-01","2024-12-01","乡村振兴局","1座",20,20,0,0,0,1,296,1313,0,35,97,"满意度100%","提高群众生产生活水平"]
[30,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","熙福村","基础设施","改扩建","熙福村七组","2024-01-01","2024-12-01","乡村振兴局","1千米",15,15,0,0,0,1,65,263,0,6,26,"满意度100%","提高群众生产生活水平"]
[31,"乡村建设行动","人居环境整治","村容村貌提升","草尾镇","熙福村","渠道疏洗","改扩建","熙福村二横渠","2024-01-01","2024-12-01","乡村振兴局","2.5千米",5,5,0,0,0,1,152,613,0,15,53,"满意度100%","提高群众生产生活水平"]
[32,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","熙福村","公路维修","改扩建","熙福村九支渠公路维修","2024-01-01","2024-12-01","乡村振兴局","1千米",5,5,0,0,0,1,184,689,0,21,75,"满意度100%","提高群众生产生活水平"]
[33,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","四民村","基础设施","改扩建","四民村","2024-01-01","2024-12-01","乡村振兴局","80米",3,3,0,0,0,1,73,587,0,6,26,"满意度100%","提高群众生产生活水平"]
[34,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","三码头村","桥梁维修","改扩建","三码头村八组","2024-01-01","2024-12-01","乡村振兴局","1座",5,5,0,0,0,1,56,198,1,15,49,"满意度100%","提高群众生产生活水平"]
[35,"乡村建设行动","人居环境整治","村容村貌提升","草尾镇","三码头村","渠道疏洗","改扩建","三码头村民兵渠","2024-01-01","2024-12-01","乡村振兴局","3500米",8,8,0,0,0,1,896,2642,1,115,352,"满意度100%","提高群众生产生活水平"]
[36,"乡村建设行动","人居环境整治","村容村貌提升","草尾镇","人益村","渠道疏洗","改扩建","人益村","2024-01-01","2024-12-01","乡村振兴局","3000米",6,6,0,0,0,1,120,791,0,21,63,"满意度100%","提高群众生产生活水平"]
[37,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","人益村","公路硬化","改扩建","人益村","2024-01-01","2024-12-01","乡村振兴局","2000米",15,15,0,0,0,1,180,340,0,18,51,"满意度100%","提高群众生产生活水平"]
[38,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","人益村","公路维护","改扩建","人益村","2024-01-01","2024-12-01","乡村振兴局","2000米",5,5,0,0,0,1,320,1021,0,46,131,"满意度100%","提高群众生产生活水平"]
[39,"乡村建设行动","人居环境整治","村容村貌提升","草尾镇","胜天村","渠道梳洗","新建","胜天村","2024-01-01","2024-12-01","乡村振兴局","1000米",18,18,0,0,0,1,168,378,0,12,38,"满意度100%","提高群众生产生活水平"]
[40,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","胜天村","公路新建","改扩建","胜天村","2024-01-01","2024-12-01","乡村振兴局","3500米",12,12,0,0,0,1,112,268,0,26,76,"满意度100%","提高群众生产生活水平"]
[41,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","和平村","道路维修","改扩建","和平村","2024-01-01","2024-12-01","乡村振兴局","2000米",10,10,0,0,0,1,320,450,1,10,24,"满意度100%","提高群众生产生活水平"]
[42,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","乐园村","机耕道修复","新建","乐园村","2024-01-01","2024-05-01","乡村振兴局","1000米",15,15,0,0,0,1,70,180,0,8,21,"满意度100%","提高群众生产生活水平"]
[1,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","阳罗洲镇","富安村","阳罗洲镇2024年富安村7组道路建设","新建","富安村","2024-03-01","2024-04-01","乡村振兴局","道路建设500米",{"$f":"O99+P99+Q99+R99","v":20},20,0,0,0,1,230,870,0,56,120,"方便群众出行、受益农户人均年增收400元","带动生产"]
[2,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","阳罗洲镇","候龙村","阳罗洲镇2024年候龙村公路维修","新建","候龙村","2024-03-01","2024-04-01","乡村振兴局","公路维修400米",20,20,0,0,0,1,125,338,1,10,38,"受益农户人均收入200元","方便农副产品运输"]
[3,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","阳罗洲镇","候龙村","阳罗洲镇2024年候龙村十三斗公路硬化","新建","候龙村","2024-03-01","2024-04-01","乡村振兴局","公路硬化2500米",20,20,0,0,0,1,60,240,1,4,16,"受益农户人均收入200元","方便农副产品运输"]
[4,"产业发展项目","生产项目","种植业基地","阳罗洲镇","候龙村","阳罗洲镇2024年候龙村俊熙稻虾种养合作社","新建","候龙村","2024-04-01","2024-06-01","乡村振兴局","产业发展",20,20,0,0,0,1,125,338,1,125,338,"待定脱贫户及监测户人均年增收1000元","产业分红"]
[5,"产业发展项目","加工流通项目","产地初加工和精深加工","阳罗洲镇","候龙村","阳罗洲镇2024年候龙村四通包装厂","新建","候龙村","2024-04-01","2024-05-01","乡村振兴局","入股分红",20,20,0,0,0,1,125,338,1,125,338,"受益农户人均收入200元","入股分红"]
[6,"乡村建设行动","农村基础设施","产业路、资源路、旅游路建设","阳罗洲镇","候龙村","阳罗洲镇2024年候龙村稻虾基地基础设施提质改造","新建","候龙村","2024-03-01","2024-04-01","乡村振兴局","道路建设400米",20,20,0,0,0,1,125,338,1,125,338,"受益农户人均收入200元","方便农副产品运输"]
[7,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","阳罗洲镇","富民村","阳罗洲镇2024年富民村战备渠拓宽提质改造","新建","富民村","2024-05-01","2024-06-01","乡村振兴局","加宽及白改黑2000米",20,20,0,0,0,1,96,362,0,12,27,"方便群众出行、受益农户人均年增收400元","带动生产"]
[8,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","阳罗洲镇","富民村","阳罗洲镇2024年富民村富强片兴隆片公路建设","新建","富民村","2024-04-01","2024-05-01","乡村振兴局","公路硬化3000米",20,20,0,0,0,1,36,180,0,15,50,"方便群众出行、受益农户人均年增收400元","带动生产"]
[9,"产业发展项目","配套基础设施项目","小型农田水利设施建设","阳罗洲镇","富民村","阳罗洲镇2024年富民村兴丰片渠道护坡","维修","富民村","2024-11-01","2025-03-01","乡村振兴局","渠道护坡4000米",20,20,0,0,0,1,340,1190,0,28,61,"受益农户人均收入600元","带动生产"]
[10,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","阳罗洲镇","东新村","阳罗洲镇2024年东新村战备渠拓宽提质改造","新建","东新村","2024-05-01","2024-06-01","乡村振兴局","白改黑2000米",20,20,0,0,0,1,82,352,0,8,24,"方便群众出行、受益农户人均年增收400元","带动生产"]
[11,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","阳罗洲镇","大中村","阳罗洲镇2024年大中村二支渠7至13斗公路建设","新建","大中村","2024-03-01","2024-04-01","乡村振兴局","公路建设2000米",20,20,0,0,0,1,685,3290,1,81,141,"方便群众出行、受益农户人均年增收400元","带动生产"]
[12,"产业发展项目","配套基础设施项目","小型农田水利设施建设","阳罗洲镇","大中村","阳罗洲镇2024年大中村3斗渠道护坡","维修","大中村","2024-04-01","2024-05-01","乡村振兴局","渠道护坡1000米",20,20,0,0,0,1,160,760,1,60,124,"受益农户人均收入600元","带动生产"]
[13,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","阳罗洲镇","大中村","阳罗洲镇2024年大中村二支渠5斗至9斗公路硬化","新建","大中村","2024-01-01","2024-02-01","乡村振兴局","公路硬化1600米",20,20,0,0,0,1,152,445,1,40,115,"方便群众出行、受益农户人均年增收400元","带动生产"]
[14,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","阳罗洲镇","复兴村","阳罗洲镇2024年复兴村富南支渠公路硬化","新建","复兴村","2024-05-01","2024-06-01","乡村振兴局","公路硬化1000米",20,20,0,0,0,1,80,320,0,15,35,"方便群众出行、受益农户人均年增收400元","带动生产"]
[15,"产业发展项目","配套基础设施项目","小型农田水利设施建设","阳罗洲镇","兴乐村","阳罗洲镇2024年兴乐村胜利渠渠道疏洗","维修","兴乐村","2024-03-01","2024-04-01","乡村振兴局","渠道梳洗2600米",5,5,0,0,0,1,22,65,1,7,19,"受益农户人均收入400元","带动生产"]
[16,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","阳罗洲镇","吕丰村","阳罗洲镇2024年吕丰村东剅口10斗公路硬化","新建","吕丰村","2024-03-01","2024-04-01","乡村振兴局","公路硬化500米",20,20,0,0,0,1,38,115,0,7,17,"方便群众出行、受益农户人均年增收400元","带动生产"]
[17,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","阳罗洲镇","吕丰村","阳罗洲镇2024年吕丰村18斗南公路硬化","新建","吕丰村","2024-03-01","2024-04-01","乡村振兴局","公路硬化500米",20,20,0,0,0,1,62,210,0,5,20,"方便群众出行、受益农户人均年增收400元","带动生产"]
[18,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","阳罗洲镇","吕丰村","阳罗洲镇2024年吕丰村13斗至14斗11支渠公路硬化","新建","吕丰村","2024-03-01","2024-04-01","乡村振兴局","公路硬化500米",20,20,0,0,0,1,75,320,0,5,18,"方便群众出行、受益农户人均年增收400元","带动生产"]
[19,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","阳罗洲镇","俩仪村","阳罗洲镇2024年俩仪村2组瓦岗湖堤公路硬化","维修","俩仪村","2024-05-01","2024-05-01","乡村振兴局","公路硬化500米",20,20,0,0,0,1,86,280,0,8,25,"方便群众出行、受益农户人均年增收400元","带动生产"]
[20,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","阳罗洲镇","俩仪村","阳罗洲镇2024年俩仪村向阳渠13斗至14斗公路硬化","新建","俩仪村","2024-11-01","2024-12-01","乡村振兴局","公路硬化2000米",20,20,0,0,0,1,421,1653,0,15,42,"方便群众出行、受益农户人均年增收400元","带动生产"]
[21,"产业发展项目","配套基础设施项目","小型农田水利设施建设","阳罗洲镇","宝三村","阳罗洲镇2024年宝三村七组北电排护坡","维修","宝三村","2024-09-01","2024-12-01","乡村振兴局","电排护坡300米",20,20,0,0,0,1,380,724,0,35,97,"受益农户人均年增收400元","带动生产"]
[22,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","阳罗洲镇","宝三村","阳罗洲镇2024年宝三村三组五组大寨渠战备渠飞跃渠村级道路硬化","新建","宝三村","2024-05-01","2024-07-01","乡村振兴局","公路硬化2500米",20,20,0,0,0,1,663,1892,0,49,107,"方便群众出行、受益农户人均年增收400元","带动生产"]
[23,"产业发展项目","配套基础设施项目","小型农田水利设施建设","阳罗洲镇","胜利村","阳罗洲镇2024年胜利村北五斗沟渠疏洗","维修","胜利村","2024-05-01","2024-05-01","乡村振兴局","渠道梳洗3000米",10,10,0,0,0,1,89,298,0,10,31,"受益农户人均年增收400元","带动生产"]
[24,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","阳罗洲镇","跃进村","阳罗洲镇2024年跃进村跃进渠西公路硬化","新建","跃进村","2024-05-01","2024-05-01","乡村振兴局","公路硬化1200米",20,20,0,0,0,1,245,520,0,26,62,"方便群众出行、受益农户人均年增收400元","带动生产"]
[25,"产业发展项目","配套基础设施项目","小型农田水利设施建设","阳罗洲镇","跃进村","阳罗洲镇2024年跃进村胜利渠与塞阳运河交界处新建外排机埠","新建","跃进村","2024-04-01","2024-05-01","乡村振兴局","机埠1个",20,20,0,0,0,1,480,1056,0,42,134,"受益农户人均年增收400元","带动生产"]
[26,"产业发展项目","配套基础设施项目","小型农田水利设施建设","阳罗洲镇","跃进村","阳罗洲镇2024年跃进村胜利渠兰香港新建涵闸","新建","跃进村","2024-03-01","2024-04-01","乡村振兴局","涵闸1个",10,10,0,0,0,1,275,823,0,12,28,"受益农户人均年增收400元","带动生产"]
[27,"产业发展项目","配套基础设施项目","小型农田水利设施建设","阳罗洲镇","跃进村","阳罗洲镇2024年跃进村二斗渠渠道梳洗","维修","跃进村","2024-03-01","2024-03-01","乡村振兴局","渠道梳洗2200米",8,8,0,0,0,1,480,1056,0,42,134,"受益农户人均年增收400元","带动生产"]
[28,"乡村建设行动","农村基础设施","产业路、资源路、旅游路建设","阳罗洲镇","七子浃村","阳罗洲镇2024年七子浃村鼎胜稻虾专业合作社","新建","七子浃村","2024-03-01","2024-04-01","乡村振兴局","道路建设800米",20,20,0,0,0,1,50,150,0,3,6,"带动脱贫户及监测户人均年增收500元","带动生产"]
[1,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","四季红镇","四季红村","四季红镇四季红村15组、14组、12组公路路基拓宽","新建","四季红村","2024-02-01","2024-04-01","四季红村","路基拓宽600米",{"$f":"O127+P127+Q127+R127","v":30},30,0,0,0,1,120,359,1,11,28,"改善人民群众出行环境、群众满意度≥100%","改善群众生活条件"]
[2,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","四季红镇","四季红村","四季红镇四季红村16组至11组路基拓宽","新建","四季红村","2024-04-01","2024-04-01","四季红村","路基拓宽800米",40,40,0,0,0,1,77,214,1,6,14,"改善人民群众出行环境、群众满意度≥100%","改善群众生活条件"]
[3,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","四季红镇","四季红村","四季红镇四季红村2组7组、9组路基拓宽","新建","四季红村","2024-02-01","2024-04-01","四季红村","路基拓宽500米",35,35,0,0,0,1,166,455,1,16,35,"改善人民群众出行环境、群众满意度≥100%","改善群众生活条件"]
[4,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","四季红镇","四季红村","四季红镇四季红村6组10组、3组路基拓宽","新建","四季红村","2024-01-01","2024-03-01","四季红村","路基拓宽500米",35,35,0,0,0,1,295,792,1,14,46,"改善人民群众出行环境、群众满意度≥100%","改善群众生活条件"]
[5,"乡村建设行动","人居环境整治","农村垃圾治理","四季红镇","安心村","四季红镇安心村人居环境配套设施","新建","1-11组菜园子六合一","2024-03-01","2024-05-01","安心村","菜园子六合一",120,120,0,0,0,1,465,1692,0,13,30,"改善村民菜园环境","改善群众生活条件"]
[6,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","四季红镇","安心村","四季红镇安心村9-11组道路硬化道路硬化","新建","9-11组道路硬化","2024-02-01","2024-04-01","安心村","道路硬化",80,80,0,0,0,1,152,658,0,15,35,"改善群众生活条件、群众满意度≥100%","改善群众生活条件"]
[7,"产业发展项目","配套基础设施项目","小型农田水利设施建设","四季红镇","安心村","四季红镇安心村5-8组渠道硬化渠道硬化","新建","5-8组渠道硬化","2024-01-01","2024-02-01","安心村","渠道硬化",100,100,0,0,0,1,150,650,0,14,48,"改善群众生产生活条件、群众满意度≥100%","改善群众生活条件"]
[8,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","四季红镇","安心村","四季红镇安心村7组后面400米道路硬化","新建","7组后面400米道路硬化","2024-02-01","2024-04-01","安心村","道路硬化",20,20,0,0,0,1,38,128,0,10,28,"改善群众生活条件、群众满意度≥100%","改善群众生活条件"]
[9,"产业发展项目","配套基础设施项目","小型农田水利设施建设","四季红镇","安心村","四季红镇安心村3-10组道路配套设施","新建","3-10组道路配套设施","2024-01-01","2024-03-01","安心村","道路配套设施",30,30,0,0,0,1,160,645,0,8,45,"改善群众生活条件、群众满意度≥100%","改善群众生活条件"]
[10,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","四季红镇","阳雀洪村","四季红镇阳雀洪村一组道路建设","扩建","阳雀洪村一组","2024-02-01","2024-04-01","阳雀洪村","长300米宽5米",20,20,0,0,0,1,336,1326,1,29,94,"改善人民群众出行环境、群众满意度≥100%","改善群众生活条件"]
[11,"产业发展项目","配套基础设施项目","小型农田水利设施建设","四季红镇","阳雀洪村","四季红镇阳雀洪村三组渠道硬化","新建","阳雀洪村三组","2024-02-01","2024-04-01","阳雀洪村","1000米",60,60,0,0,0,1,336,1326,1,29,94,"改善群众生活条件、群众满意度≥100%","改善群众生活条件"]
[12,"产业发展项目","配套基础设施项目","小型农田水利设施建设","四季红镇","阳雀洪村","四季红镇阳雀洪村十组渠道硬化","新建","阳雀洪村四组","2024-01-01","2024-02-01","阳雀洪村","300米",20,20,0,0,0,1,336,1326,1,29,94,"改善群众生活条件、群众满意度≥100%","改善群众生活条件"]
[13,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","四季红镇","东红新村","四季红镇东红新村三斗渠、四斗渠公路扩宽","扩宽","东红新村","2024-02-01","2024-04-01","东红新村","公路扩宽3500千米×1.5米",105,105,0,0,0,1,692,2410,0,48,154,"改善群众生活条件、群众满意度≥100%","改善群众生活条件"]
[14,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","四季红镇","东红新村","四季红镇东红新村西子堤公路维修","维修","东红新村","2024-01-01","2024-03-01","东红新村","1600米×3.5米",123.2,123.2,0,0,0,1,692,2410,0,48,156,"改善群众生活条件、群众满意度≥100%","改善群众生活条件"]
[15,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","四季红镇","东红新村","四季红镇东红新村四斗渠、五斗渠新建公路","新建","东红新村","2024-03-01","2024-05-01","东红新村","1000米",130,130,0,0,0,1,692,2410,0,48,156,"改善群众生活条件、群众满意度≥100%","改善群众生活条件"]
[16,"产业发展项目","配套基础设施项目","小型农田水利设施建设","四季红镇","东红新村","四季红镇东红新村三斗渠至西子堤渠道硬化","硬化","东红新村","2024-02-01","2024-04-01","东红新村","820米",123,123,0,0,0,1,692,2410,0,48,156,"改善群众生活条件、群众满意度≥100%","改善群众生活条件"]
[17,"产业发展项目","加工流通项目","产地初加工和精深加工","四季红镇","东红新村","四季红镇东红新村腊制品厂新建","新建","东红新村","2024-02-01","2024-05-01","东红新村","2700平方米",270,270,0,0,0,1,692,2410,0,48,156,"改善群众生产生活条件、群众满意度≥100%","增加群众收入"]
[18,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","四季红镇","长征村","四季红镇长征村12.14.15斗渠道路维修","维修","长征村","2024-01-01","2024-03-01","长征村","修补公路",35,35,0,0,0,1,260,1100,0,36,95,"改善群众生活条件、群众满意度≥100%","改善群众生活条件"]
[19,"产业发展项目","配套基础设施项目","小型农田水利设施建设","四季红镇","长征村","四季红镇长征村中心渠道维修","维修","长征村","2024-02-01","2024-04-01","长征村","维修灌溉渠道",40,40,0,0,0,1,360,1420,0,36,95,"改善群众生活条件、群众满意度≥100%","改善群众生活条件"]
[20,"产业发展项目","配套基础设施项目","小型农田水利设施建设","四季红镇","长征村","四季红镇长征村2.6.8.9.10.11组渠道配套设施建设","新建","长征村","2024-01-01","2024-03-01","长征村","污水沟硬化",130,130,0,0,0,1,285,1250,0,36,95,"改善群众生活条件、群众满意度≥100%","改善群众生活条件"]
[21,"产业发展项目","配套基础设施项目","小型农田水利设施建设","四季红镇","玉鹊村","四季红镇玉鹊村九斗渠渠道配套设施建设","改建","玉鹊村九斗渠","2024-01-01","2024-03-01","玉鹊村","渠道硬化\n590米",50,50,0,0,0,1,50,200,0,15,65,"改善群众生活条件、群众满意度≥100%","改善群众生活条件"]
[22,"产业发展项目","配套基础设施项目","小型农田水利设施建设","四季红镇","玉鹊村","四季红镇玉鹊村四组排水渠道硬化","改建","玉鹊村四组","2024-03-01","2024-04-01","玉鹊村","排水渠硬化400米",28,28,0,0,0,1,35,120,0,10,34,"改善群众生产生活条件、群众满意度≥100%","改善群众生活条件"]
[23,"产业发展项目","配套基础设施项目","小型农田水利设施建设","四季红镇","玉鹊村","四季红镇玉鹊村二组、三组屋前渠道硬化","改建","玉鹊村二、三组","2024-02-01","2024-04-01","玉鹊村","渠道硬化1100米",75,75,0,0,0,1,60,240,0,13,66,"改善群众生活条件、群众满意度≥100%","改善群众生活条件"]
[24,"产业发展项目","配套基础设施项目","小型农田水利设施建设","四季红镇","玉鹊村","四季红镇玉鹊村八斗渠-十二斗渠渠道硬化","改建","玉鹊村中心路","2024-01-01","2024-03-01","玉鹊村","渠道硬化900米",55,55,0,0,0,1,150,600,0,14,54,"改善群众生活条件、群众满意度≥100%","改善群众生活条件"]
[25,"产业发展项目","配套基础设施项目","小型农田水利设施建设","四季红镇","四季红社区","四季红镇四季红社区维修各组灌渠","新建","四季红社区","2024-03-01","2024-05-01","四季红社区","5000米",37.5,37.5,0,0,0,1,40,189,0,10,55,"改善群众生产生活条件、群众满意度≥100%","增加群众收入"]
[26,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","四季红镇","四季红社区","四季红镇四季红社区十、七组新建机耕桥及机耕路","新建","四季红社区十、七组","2024-02-01","2024-04-01","四季红社区","机耕路2400米、机耕桥16座",15.6,15.6,0,0,0,1,35,165,0,12,58,"改善群众生活条件、群众满意度≥100%","改善群众生活条件"]
[27,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","四季红镇","四季红社区","四季红镇四季红社区二、九、十二组公路拓宽","新建","四季红社区二、九、十二组公路","2024-02-01","2024-04-01","四季红社区","1200米",63,63,0,0,0,1,55,256,0,12,50,"改善群众生活条件、群众满意度≥100%","改善群众生活条件"]
[1,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","南大膳镇","石东港村","2024年南大膳镇石东港村银花片公路硬化项目","新建","石东港村","2024-03-01","2024-05-01","乡村振兴局","长800米，宽4.5米，厚0.20米",{"$f":"O154+P154+Q154+R154","v":20},20,0,0,0,1,50,150,0,30,90,"提高群众满意度","便利群众出行"]
[2,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","南大膳镇","石东港村","2024年南大膳镇石东港村银花片十组桥梁维修项目","维修","石东港村","2024-10-01","2024-12-01","乡村振兴局","银花片十组通S217桥一座",18,18,0,0,0,1,50,150,0,32,92,"提高群众满意度","便利群众出行"]
[3,"产业发展项目","配套基础设施项目","小型农田水利设施建设","南大膳镇","石东港村","2024年南大膳镇石东港村排积机埠项目","新建","石东港村","2024-03-01","2024-05-01","乡村振兴局","新建排积机埠一座",30,30,0,0,0,1,50,150,0,32,92,"提高群众满意度","便利群众出行"]
[4,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","南大膳镇","灵官嘴村","2024年南大膳镇灵官嘴村新建公路项目","新建","灵官嘴村","2024-01-01","2024-06-30","乡村振兴局","长2000米，宽3.5米，厚0.2米",80,80,0,0,0,1,72,216,0,8,26,"提高群众满意度","便利群众出行"]
[5,"产业发展项目","配套基础设施项目","小型农田水利设施建设","南大膳镇","灵官嘴村","2024年南大膳镇灵官嘴村渠道梳洗项目","维护","灵官嘴村","2024-01-01","2024-06-30","乡村振兴局","3900米",20,20,0,0,0,1,916,2603,0,48,106,"提高群众满意度","便利群众出行"]
[6,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","南大膳镇","灵官嘴村","2024年南大膳镇灵官嘴村公路扩建项目","扩建","灵官嘴村","2024-01-01","2024-06-30","乡村振兴局","长2100米，宽1米，厚0.2米",25,25,0,0,0,1,312,864,0,16,42,"提高群众满意度","便利群众出行"]
[7,"产业发展项目","配套基础设施项目","小型农田水利设施建设","南大膳镇","南丰垸村","2024年南大膳镇南丰垸村渠道梳洗项目","维护","南丰片\n西南片\n东荡片","2024-01-01","2024-04-01","乡村振兴局","12000米",30,30,0,0,0,1,800,2100,0,40,80,"提高群众满意度","提升群众生产生活条件"]
[8,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","南大膳镇","南丰垸村","2024年南大膳镇南丰垸村公路维修项目","维修","西南片\n南丰片","2024-01-01","2024-04-01","乡村振兴局","长2000米，宽3.5米",20,20,0,0,0,1,600,2000,0,30,60,"提高群众满意度","提升群众生产生活条件"]
[9,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","南大膳镇","南京垸村","2024年南大膳镇南京垸村南岭4-5组公路硬化项目","新建","南岭4-5组","2024-02-01","2024-07-02","乡村振兴局","长500米，宽3米，0.2米厚",15,15,0,0,0,1,18,46,0,6,18,"提高群众满意度","提升群众生产生活条件"]
[10,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","南大膳镇","南京垸村","2024年南大膳镇南京垸村南岭6-8组公路硬化项目","新建","南岭6-8组","2024-02-01","2024-07-02","乡村振兴局","长700米，宽3米，0.2米厚",20,20,0,0,0,1,21,61,0,8,21,"提高群众满意度","提升群众生产生活条件"]
[11,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","南大膳镇","南京垸村","2024年南大膳镇南京垸村新建桥梁项目","新建","京局5组","2024-02-01","2024-10-02","乡村振兴局","1座",15,15,0,0,0,1,20,58,0,8,24,"提高群众满意度","提升群众生产生活条件"]
[1,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","共华镇","东合村","共华镇-东合村-基础设施-2024年道路及配套设施建设","新建","东合村","2024-03-01","2024-12-01","乡村振兴局","道路及配套设施建设1公里",5,5,0,0,0,1,50,150,0,4,12,"受益群众满意度≥95%","提高群众生产生活水平"]
[2,"产业发展项目","配套基础设施项目","小型农田水利设施建设","共华镇","福安村","共华镇-福安村-基础设施-2024年渠道疏浚","新建","福安村","2024-03-01","2024-12-01","乡村振兴局","渠道梳洗1公里",5,5,0,0,0,1,30,100,1,5,16,"受益群众满意度≥95%","提高群众生产生活水平"]
[3,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","共华镇","双阜村","共华镇-双阜村-基础设施-2024年道路及配套设施建设","新建","双阜村","2024-03-01","2024-12-01","乡村振兴局","道路及配套设施建设1公里",5,5,0,0,0,1,40,95,1,10,22,"受益群众满意度≥95%","提高群众生产生活水平"]
[4,"产业发展项目","配套基础设施项目","小型农田水利设施建设","共华镇","双阜村","共华镇-双阜村-基础设施-2024年渠道疏浚","新建","双阜村","2024-03-01","2024-12-01","乡村振兴局","渠道梳洗1公里",5,5,0,0,0,1,25,70,1,6,14,"受益群众满意度≥95%","提高群众生产生活水平"]
[1,"产业发展项目","生产项目","种植业基地","茶盘洲镇","/","沅江市茶盘洲镇万亩生态示范产业园（第三期）","新建","茶盘洲镇","2024-01-23","2024-12-31","茶盘洲镇人民政府","围绕生态水稻、生态药材、生态水产、生态水果、生态蔬菜、生态养殖等六个生态建设",{"$f":"O169+P169+Q169+R169","v":480},480,0,0,0,6,679,2007,1,47,98,"围绕六个生态建设","带动生产"]
[2,"产业发展项目","生产项目","养殖业基地","茶盘洲镇","/","茶盘洲镇生态养殖基地建设项目","新建","茶盘洲镇","2024-01-20","2024-12-19","茶盘洲镇人民政府","打造生态养殖基地",240,240,0,0,0,3,367,1002,0,23,49,"打造生态养殖基地","带动生产"]
[3,"产业发展项目","加工流通项目","产地初加工和精深加工","茶盘洲镇","/","茶盘洲镇农产品加工建设项目","新建","茶盘洲镇","2024-01-22","2024-12-30","茶盘洲镇人民政府","对生态水稻、生态药材、生态水产、生态水果、生态蔬菜、生态养殖。六个生态生产的农产品进行初加工",320,320,0,0,0,2,257,685,0,13,24,"对六个生态生产的农产品进行初加工","带动生产"]
[4,"产业发展项目","产业服务支撑项目","智慧农业","茶盘洲镇","/","茶盘洲镇现代化农业基地建设项目","新建","茶盘洲镇","2024-01-23","2024-12-12","茶盘洲镇人民政府","给生态水稻、生态药材、生态水产、生态水果、生态蔬菜、生态养殖六个生态插上科技的翅膀。",340,340,0,0,0,3,336,589,0,36,65,"给生态水稻、生态药材、生态水产、生态水果、生态蔬菜、生态养殖六个生态插上科技的翅膀。","带动生产"]
[5,"产业发展项目","配套基础设施项目","产业园（区）","茶盘洲镇","/","茶盘洲镇蔬菜种植基地建设项目","新建","茶盘洲镇","2024-01-27","2024-12-17","茶盘洲镇人民政府","打造全天候生态试验蔬菜种植大棚，为菜篮子工程增砖加瓦",350,350,0,0,0,4,589,1658,1,66,125,"打造全天候生态试验蔬菜种植大棚","带动生产"]
[6,"产业发展项目","加工流通项目","品牌打造和展销平台","茶盘洲镇","/","茶盘洲镇农产品销售网络平台建设项目","新建","茶盘洲镇","2024-01-13","2024-12-15","茶盘洲镇人民政府","打造网络销售平台，为生态水稻、生态药材、生态水产、生态水果、生态蔬菜、生态养殖增加销售渠道。",200,200,0,0,0,3,368,789,0,33,62,"打造网络销售平台增加销售渠道。","帮助产销对接"]
[7,"产业发展项目","加工流通项目","品牌打造和展销平台","茶盘洲镇","/","茶盘洲镇水果种植基地建设项目","新建","茶盘洲镇","2024-01-15","2024-12-09","茶盘洲镇人民政府","打造茶盘洲镇自己的水果品牌。",300,300,0,0,0,5,662,2351,1,55,103,"打造茶盘洲镇自己的水果品牌。","帮助产销对接"]
[8,"产业发展项目","配套基础设施项目","小型农田水利设施建设","茶盘洲镇","玉竹村","2024年茶盘洲镇玉竹村沟渠清淤项目","拓建","玉竹村","2024-01-23","2024-12-12","玉竹村","沟渠清淤8千米",12,12,0,0,0,1,212,562,0,40,78,"村级沟渠清淤项目","带动生产"]
[9,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","茶盘洲镇","南洲村","2024年茶盘洲镇南洲村公路硬化项目","新建","南洲村1组到2组","2024-01-27","2024-12-15","南洲村","公路硬化2000米",90,90,0,0,0,1,62,210,0,6,12,"公路硬化2000米","带动生产"]
[10,"产业发展项目","配套基础设施项目","小型农田水利设施建设","茶盘洲镇","南洲街社区","2024年茶盘洲镇南洲街社区工程队沟渠疏通项目","改建","南洲街社区","2024-01-13","2024-12-30","南洲街社区","社区工程队下水沟渠疏通，面积约为120m×2m",5,5,0,0,0,1,2198,4701,0,0,0,"社区工程队下水沟渠疏通，面积约为120m×2m","带动生产"]
[11,"产业发展项目","配套基础设施项目","小型农田水利设施建设","茶盘洲镇","南洲街社区","2024年茶盘洲镇南洲街社区幸福分场沟渠疏通项目","改建","南洲街社区","2024-01-27","2024-12-17","南洲街社区","幸福分场下水沟渠疏通，面积约为960m×2m",3.5,3.5,0,0,0,1,2198,4701,0,0,0,"幸福分场下水沟渠疏通，面积约为960m×2m","带动生产"]
[12,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","茶盘洲镇","南洲街社区","2024年茶盘洲镇南洲街社区东灌渠1桥-5桥桥梁改建项目","改建","南洲街社区","2024-01-10","2024-12-09","南洲街社区","南洲街社区东灌渠1桥-5桥改扩建",25,25,0,0,0,2,3345,6681,0,4,8,"南洲街社区东灌渠1桥-5桥改扩建","带动生产"]
[13,"产业发展项目","配套基础设施项目","产业园（区）","茶盘洲镇","幸福村","2024年茶盘洲镇幸福村经济合作社产业发展项目","改建","幸福村","2024-02-20","2024-10-17","幸福村","幸福村经济合作社的发展",20,20,0,0,0,1,77,165,1,77,165,"提升集体经济合作社的创收能力","带动生产"]
[14,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","茶盘洲镇","幸福村","2024年茶盘洲镇茶盘洲镇幸福村六组公路硬化项目","新建","幸福村","2024-01-10","2024-10-17","幸福村","公路硬化300米",10,10,0,0,0,1,20,80,1,3,9,"六组300米的公路硬化","带动生产"]
[15,"产业发展项目","配套基础设施项目","小型农田水利设施建设","茶盘洲镇","幸福村","2024年茶盘洲镇茶盘洲镇幸福村3组至5组沟渠清淤项目","新建","幸福村","2024-03-01","2024-06-17","幸福村","沟渠清淤2400米",5,5,0,0,0,1,220,480,1,12,36,"3至5组2400米沟渠清淤","带动生产"]
[16,"产业发展项目","配套基础设施项目","小型农田水利设施建设","茶盘洲镇","幸福村","2024年茶盘洲镇茶盘洲镇幸福村六组至八组沟渠清淤项目","新建","幸福村","2024-02-15","2024-12-03","幸福村","沟渠清淤3200米",8,8,0,0,0,1,282,560,1,18,54,"六至八组3200米沟渠清淤","带动生产"]
[17,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","茶盘洲镇","柴洲包村","2024年茶盘洲镇柴洲包村四组公路桥建设项目","新建","柴洲包四组彭冬清家处","2024-01-09","2024-12-20","柴洲包村","新建公路桥1座，桥面宽4.5米，桥洞宽2.5米，桥高按建时平公路面",12,12,0,0,0,1,201,442,0,0,24,"新建公路桥1座，桥面宽4.5米，桥洞宽2.5米，桥高按建时平公路面","带动生产"]
[18,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","茶盘洲镇","柴洲包村","2024年茶盘洲镇柴洲包村三组公路桥建设项目","新建","柴洲包三组谢建雄家处","2024-01-15","2024-02-10","柴洲包村","新建公路桥1座桥面宽4.5米，桥洞宽2.5米，桥高按建时平公路面",12,12,0,0,0,1,170,330,0,0,36,"新建公路桥1座桥面宽4.5米，桥洞宽2.5米，桥高按建时平公路面","带动生产"]
[19,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","茶盘洲镇","柴洲包村","2024年茶盘洲镇柴洲包村五组公路硬化项目","新建","柴洲包村五组","2024-02-13","2024-12-14","柴洲包村","公路硬化，长度1000米，路面宽3.5米，厚度0.2米",42,42,0,0,0,1,120,820,0,0,32,"公路硬化，长度1000米，路面宽3.5米，厚度0.2米","带动生产"]
[20,"产业发展项目","配套基础设施项目","小型农田水利设施建设","茶盘洲镇","鹅洲村","2024年茶盘洲镇茶盘洲镇鹅洲村渠道清淤项目","新建","鹅洲村","2024-01-17","2024-12-17","鹅洲村","沟渠清淤10000米",10,10,0,0,0,1,908,1645,1,61,143,"沟渠清淤10000米","带动生产"]
[21,"产业发展项目","配套基础设施项目","小型农田水利设施建设","茶盘洲镇","南洲街社区（天心渔村）","2024年茶盘洲镇天心渔村渔业发展配套设施建设项目","新建","天心渔村","2024-01-18","2024-04-30","天心渔村","沟渠硬化1500米",20,20,0,0,0,1,455,854,0,13,23,"沟渠硬化1500米","带动生产"]
[22,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","茶盘洲镇","南洲街社区（天心渔村）","2024年茶盘洲镇天心渔村公路项目","新建","天心渔村","2024-07-10","2024-10-30","天心渔村","新增公路500米",10,10,0,0,0,1,455,854,0,13,23,"新增公路500米","带动生产"]
[23,"产业发展项目","配套基础设施项目","小型农田水利设施建设","茶盘洲镇","南洲街社区（天心渔村）","2024年茶盘洲镇天心渔村新修机埠项目","新建","天心渔村","2024-02-15","2024-03-30","天心渔村","新增机埠2个",10,10,0,0,0,1,455,854,0,13,23,"新增机埠2个","带动生产"]
[24,"产业发展项目","生产项目","种植业基地","茶盘洲镇","六合村","2024年茶盘洲镇六合村百亩大棚蔬菜基地","新建","六合村二组","2024-02-15","2024-10-30","六合村","54个大棚及130亩露天蔬菜基地",158,158,0,0,0,1,80,150,0,12,23,"新建54个蔬菜大棚","就业帮扶"]
[25,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","茶盘洲镇","花果山村","2024年茶盘洲镇花果山村公路项目","新建","花果山村","2024-01-17","2024-12-14","花果山村","新增公路1000米",40,40,0,0,0,1,120,284,0,12,32,"新增公路1000米","带动生产"]
[26,"产业发展项目","配套基础设施项目","小型农田水利设施建设","茶盘洲镇","花果山村","2024年茶盘洲镇花果山村二组基本农田改造项目","新建","花果山村","2024-01-15","2024-12-20","花果山村","基本农田改造240亩",60,60,0,0,0,1,78,164,0,16,41,"基本农田改造240亩","带动生产"]
[27,"产业发展项目","配套基础设施项目","小型农田水利设施建设","茶盘洲镇","花果山村","2024年茶盘洲镇茶盘洲镇花果山村渠道清淤项目","新建","花果山村","2024-02-15","2024-10-17","花果山村","沟渠硬化1400米",20,20,0,0,0,1,218,467,0,12,26,"沟渠硬化1400米","带动生产"]
[1,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","南洞庭中心","永胜社区","主干道路肩修复项目","改扩建","永胜社区","2024-08-20","2024-09-30","乡村振兴局","主干道建挡土墙3000米",35,35,0,0,0,1,782,2487,0,92,192,"群众满意度100%","①提高群众生产生活水平②便利群众出行③解决53户（其中监测户4户）的农产品运输问题④加强基础设施建设"]
[2,"乡村建设行动","人居环境整治","村容村貌提升","南洞庭中心","永胜社区","农村垃圾治理项目","改扩建","永胜社区","2024-08-20","2024-09-30","乡村振兴局","建设垃圾收集及分类设施5处",9,9,0,0,0,1,782,2487,0,92,192,"群众满意度100%","①提高群众及53户脱贫户（其中监测户4户）的生产生活水平②加强基础设施建设"]
[3,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","南洞庭中心","永胜社区","公路拓宽项目","改扩建","永胜社区","2024-08-20","2024-09-30","乡村振兴局","1500米主干道拓宽",36,36,0,0,0,1,782,2487,0,92,192,"群众满意度100%","①提高群众生产生活水平②便利群众出行③解决53户（其中监测户4户）的农产品运输问题④加强基础设施建设"]
[1,"产业发展项目","配套基础设施项目","小型农田水利设施建设","漉湖中心","柴下洲社区","柴下洲社区4队沟渠衬砌护坡","新建","柴下洲社区4队","2024-03-01","2024-11-01","乡村振兴局","260米*2.6米硬化衬砌护坡",20,20,0,0,0,1,90,280,1,20,60,"群众满意度95%以上","便利群众生产生活"]
[2,"产业发展项目","配套基础设施项目","小型农田水利设施建设","漉湖中心","渔业社区","渔业社区四队出水渠道护坡","新建","渔业社区四队","2024-04-01","2024-05-01","乡村振兴局","出水渠道护坡120米",10,10,0,0,0,1,35,96,0,16,28,"群众满意度","提升群众生产生活条件"]
[3,"产业发展项目","配套基础设施项目","小型农田水利设施建设","漉湖中心","渔业社区","渔业社区一队出水渠道疏洗衬砌护坡","新建","渔业社区一队","2024-03-01","2024-06-01","乡村振兴局","出水渠道疏洗衬砌护坡420米",20,20,0,0,0,1,54,131,0,18,34,"群众满意度","提升群众生产生活条件"]
[4,"产业发展项目","配套基础设施项目","小型农田水利设施建设","漉湖中心","漉湖社区","沟渠疏洗","修建","二排渠至四排渠","2024-04-01","2024-10-01","乡村振兴局","沟渠疏洗1800米",9,9,0,0,0,1,212,625,0,36,78,"提升群众满意度","提升群众生产生活条件"]
[5,"产业发展项目","配套基础设施项目","小型农田水利设施建设","漉湖中心","漉湖社区","渠道疏通","新建","五排渠","2024-06-01","2024-12-01","乡村振兴局","渠道疏通700米",12,12,0,0,0,1,28,106,0,5,14,"提升群众满意度","提升群众生产生活条件"]
[1,"乡村建设行动","农村基础设施","产业路、资源路、旅游路建设","新湾镇","龙虎山国有林场","沅江市龙虎山国有林场2024年度欠发达国有林场巩固提升项目","扩建","沅江市新湾镇龙虎山国有林场","2024-07-01","2024-12-01","乡村振兴局","a、进林场林区道路拓宽1米，路线全场500米。\nb、林场办公楼至神州生态园林区道路拓宽1米，路线全场1000米。",40,40,0,0,0,2,220,950,0,36,84,"产业道路扩建线路全长1.5公里，项目建成后受益脱贫户和防止返贫监测户数共36户84人，增加项目区群众旅游经营收入。","项目实施能吸纳项目区劳动务工60人，带动劳动就业10人。"]
[196,"合计",{"$nulls":11},8223.7,{"$f":"SUM(O8:O204)","v":8223.7},{"$f":"SUM(P8:P204)","v":0},{"$f":"SUM(Q8:Q204)","v":0},{"$f":"SUM(R8:R204)","v":0}]
["注：项目类别中项目类型、二级项目类型、项目子类型需参照《附件9：县级巩固拓展脱贫攻坚成果和乡村振兴项目库项目分类表》填写。"]