{"text_format":"3","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"defined_names":3},"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":34,"n_cols":27,"rows_kept":34,"merged":[[1,0,1,26],[3,0,3,26],[5,0,7,0],[5,1,5,3],[5,4,7,4],[5,5,7,5],[5,6,7,6],[5,7,7,7],[5,8,7,8],[5,9,5,10],[5,11,7,11],[5,12,7,12],[5,13,5,17],[5,18,5,23],[5,24,7,24],[5,25,7,25],[5,26,7,26],[6,1,7,1],[6,2,7,2],[6,3,7,3],[6,9,7,9],[6,10,7,10],[6,13,7,13],[6,14,6,17],[6,18,7,18],[6,19,7,19],[6,20,7,20],[6,21,6,23]]}
["附件4"]
["沅江市2023年度巩固拓展脱贫攻坚成果和乡村振兴项目库动态调整项目申报表（新增入库）"]
[]
["单位：（盖章）                                                                                                                                                                                                                      时间：2023年11月"]
[]
["序号","项目类别",null,null,"乡","村","项目名称","建设性质","实施地点","时间进度",null,"责任单位","建设内容及规模","资金规模和筹资方式",{"$nulls":4},"受益对象",{"$nulls":5},"绩效目标","联农带农机制","备注"]
[null,"项目类型","二级项目类型","项目子类型",{"$nulls":5},"计划开工时间","计划完工时间",null,null,"项目预算总投资（万元）","其中",{"$nulls":3},"受益村数（个）","受益户数（户）","受益人口数（人）","其中"]
[{"$nulls":14},"财政衔接资金（万元）","除财政衔接资金外的统筹整资金（万元）","其他财政资金（万元）","其他筹措资金（万元）",{"$nulls":3},"受益脱贫村数（个）","受益脱贫户数及防止返贫监测对象户数（户）","受益脱贫人口数及防止返贫监测对象人口数（人）"]
[1,"产业发展项目","配套基础设施项目","产业园（区）","琼湖街道","保民村","2023年保民村集体经济组织合作社产业发展项目","新建","保民村","2023-10-01","2023-12-01","保民村","40万投资入股分红",40,40,0,0,0,1,345,504,1,108,272,"满意度指标、服务对象满意度指标、受益建档立卡贫困人口满意度≥95%","增加村级集体经济收入"]
[2,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","胭脂湖街道","洞兴村","洞兴村道路拓宽","改扩建","洞兴村","2023-11-01","2023-12-01","乡村振兴局","洞兴村1.4公里公路拓宽",5,5,0,0,0,1,420,1300,0,28,60,"道路拓宽，提高交通便利，方便群众出行","1、便利群众出行\n2、提高群众生产生活水平"]
[3,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","胭脂湖街道","杨梅山村","公路拓宽","新建","李家坝至联鑫电子厂","2023-11-01","2023-12-01","乡村振兴局","扩建",5,5,0,0,0,1,1050,3800,1,97,260,"方便群众生产达到增收","①提高群众生产生活水平\n②便利群众出行"]
[4,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","胭脂湖街道","先锋村","先锋村道路配套基础设施建设","新建","先锋村七组","2023-11-01","2023-12-01","乡村振兴局","水秀七组修建挡土墙及旁边道路拓宽",5,5,0,0,0,1,229,724,0,11,21,"提高群众生产生活水平，便利群众出行","1、方便群众出行    2、提升人居环境"]
[5,"产业发展","生产项目","种植业基地","胭脂湖街道","荷花村","荷花村蓝莓基地建设","新建","荷花村五组","2023-12-01","2024-01-01","乡村振兴局","新建蓝莓基地30亩，蓝莓种植及基础设施建设",40,40,0,0,0,1,980,2700,1,42,116,"方便群众生产生活，达到增收致富","提高群众生产生活水平"]
[6,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","胭脂湖街道","胭脂湖村","胭脂湖村道路配套设施建设项目","扩建","胭脂湖村5组、6组、7组","2023-11-10","2023-12-25","乡村振兴局","拓宽硬化道路1200米",40,40,0,0,0,1,850,2778,0,60,149,"方便群众生产生活，达到增收致富","①提高群众生产生活水平\n②便利群众出行"]
[7,"乡村建设行动","人居环境整治","村容村貌提升","草尾镇","立新村","渠道疏洗","改扩建","立新村","2023-08-21","2023-12-31","乡村振兴局",500,5,5,0,0,0,1,182,498,0,2,32,"满意度100%","提高群众生产生活水平"]
[8,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","草尾镇","上码头村","公路建设","改扩建","上码头村","2023-08-21","2023-12-31","乡村振兴局","改建上码头村民兵渠公路，长335米，宽4.5米。",20,20,0,0,0,1,654,2780,0,22,54,"满意度100%","提高群众生产生活水平"]
[9,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","四季红镇","阳雀洪村","沅江市四季红镇阳雀洪村村级公路配套建设","新建","阳雀洪村","2023-11-25","2023-12-30","阳雀洪村","公路新建1.2KM",100,100,0,0,0,1,336,1326,1,29,94,"改善群众生产生活条件、群众满意度≥100%","改善群众生产生活条件"]
[10,"产业发展","生产项目","种植业基地","四季红镇","四季红村","沅江市四季红村蔺草产业发展","扩建","四季红村","2023-11-25","2023-12-30","四季红村","产业发展",40,40,0,0,0,1,723,2588,1,74,205,"增加群众收入","增加群众收入"]
[11,"产业发展项目","配套基础设施项目","小型农田水利设施建设","黄茅洲镇","黄茅洲村","村内沟渠清淤","维修","黄茅洲村","2023-11-23","2023-12-23","乡村振兴局","渠道清淤500米",8,8,0,0,0,1,245,785,1,36,105,"收益建档立卡贫困人口满意度≥95%","方便群众出行"]
[12,"乡村建设行动","人居环境整治","村容村貌提升","黄茅洲镇","柳树坪村","配套实施建设","清淤","柳树坪村","2023-03-24","2023-05-24","柳树坪村","和平渠、围提渠清淤扫障",40,40,0,0,0,1,546,1836,0,34,102,"收益建档立卡贫困人口满意度≥95%","农业生产灌溉"]
[13,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","黄茅洲镇","民心村","道路配套设施建设","新建","民心村","1905-07-15T01:26:24","1905-07-15T02:24:00","乡村振兴局","道路建设643.5米",108,108,0,0,0,1,1024,3899,0,55,231,"收益建档立卡贫困人口满意度≥95%","方便群众出行"]
[14,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","泗湖山镇","华红村","2023年泗湖山镇华红村-基础设施-华红村洞庭湖12组、重华片8组与10组交界处公路硬化","新建","洞庭湖12组、重华片8组与10组交界处公路硬化","2023-10-01","2023-12-01","华红村","洞庭湖12组190米、重华片8组与10组交界处240米公路硬化",20,20,0,0,0,1,8,20,0,5,12,"受益群众满意度≥95%","1、完善基础设施建设提高群众生产生活水平，2、方便群众运输"]
[15,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","泗湖山镇","东安垸村","2023年泗湖山镇东安垸村-基础设施-东安垸村八百亩片10组至11组交界处道路硬化","新建","东安垸村","2023-11-20","2023-11-27","东安垸村","硬化140米",6,6,0,0,0,1,4,10,0,2,3,"受益脱贫人口满意度≥98%","完善村级基础设施，提到群众生产生活水平"]
[16,"产业发展项目","加工流通项目","产地初加工和精深加工","沅江市","沅江市","产业发展","新建","沅江市","2023-09-01","2023-12-01","农业农村局","基地基础设施提升",70,70,0,0,0,3,3536,9435,3,136,136,"产地初加 工、精深加工、 与副产物 综合利用、农旅融合 发展经营服务\n、主体培育培育、预制\n菜产业品等基地建设","对脱贫人口、易返贫致贫、低收入人群等监测对象进行带动帮扶"]
[17,"产业发展项目","金融保险配套项目","新型经营主体贷款贴息","沅江市","沅江市","贷款贴息","新建","沅江市","2023-10-01","2023-12-01","农业农村局","基地基础设施提升",296,296,0,0,0,0,142,0,0,0,0,"142家新型农业经营主体贷款贴息","劳务务工"]
[18,"产业发展项目","配套基础设施项目","小型农田水利设施建设","沅江市","沅江市","2023年沅江市小型农业水利设施建设与管护","扩建","琼湖街道榨南湖村、九只树村、新湾镇周公湖村、龙虎山农业村、桥北村、杨阁老村、新湾村、南嘴镇南嘴村、和谐村、南大膳镇南京垸村、牛洲村、南渔口村、黄茅洲镇子母城村、洞庭滨村、阳罗洲镇胜利村、跃进村、复兴村","2023-03-01","2023-11-01","水利局","186口山塘进行清淤、护坡、整治过水设施。渠道清淤及节水改造链接渠道21公里（其中渠道清淤15公里，新建及节水改造连接渠6公里）。",687,687,0,0,0,17,1236,2811,4,19,38,"改善灌溉面积0.45万亩，新增蓄水量40万方","统筹推进小型农业水利设施建设和管护，实现1236户家庭受益，改善灌溉面积4500亩，新增蓄水能力40万方。"]
[19,"乡村建设行动","农村基础设施","农村供水保障设施建设","沅江市","沅江市","沅江市农村供水工程管道提质改造项目（2023年度）","扩建","草尾镇草尾社区，茶盘洲镇幸福村、南洲村、南洲街社区、幸福港社区、六合村、花果山村、鹅洲村、玉竹村、柴洲包村、新华村","2023-11-01","2023-12-01","水利局","草尾集镇供水管道更新改造长64430m、供水管道设阀门井17个，茶盘洲镇供水管道更新改造47028m、供水管道改造排气阀144个、供水管道设阀门井5个。",1000,1000,0,0,0,11,13469,47142,2,329,685,"保障用水户（包括脱贫户）的饮水安全。","群众参与"]
[20,"产业发展项目","金融保险配套项目","小额信贷贴息","沅江市","沅江市","小额信贷贴息","新建","沅江市","2023-01-01","2023-12-01","乡村振兴局","小额信贷贴息",172.747903,172.747903,0,0,0,147,1114,3342,28,1114,3342,"带动脱贫人口产业增收，且获贷率超过5%","为脱贫户、监测户提供小额免息贷款,防止脱贫人口和农村低收入人口返贫致贫"]
[21,"产业发展项目","产业服务支撑项目","人才培养","沅江市","沅江市","乡村振兴致富带头人培训","新建","沅江市","2023-01-01","2023-12-01","乡村振兴局","致富带头人培训",{"$f":"O29+P29+Q29+R29","v":18.48},18.48,0,0,0,128,4696,11916,29,1957,3972,"致富带头人培训带动群众受益","培养造就一支素质优良、结构合理、作风过硬、群众公认的能带领农民群众奔小康的致富带头人队伍"]
[22,"产业发展项目","产业服务支撑项目","智慧农业","胭脂湖街道","先锋村","乡村振兴产业引导","新建","沅江市","2023-01-01","2023-12-01","乡村振兴局","产业引导",{"$f":"O30+P30+Q30+R30","v":20},20,0,0,0,1,520,3520,0,69,154,"乡村振兴文旅产业引导","带动当地特色产业发展"]
[23,"就业项目","公益性岗位","公益性岗位","沅江市","沅江市","就业帮扶车间稳岗补贴","新建","沅江市","2023-01-01","2023-12-01","乡村振兴局","就业帮扶车间稳岗补贴",87,87,0,0,0,35,455,1894,35,455,1894,"帮扶脱贫人口解决就业，争取帮扶车间超过40家","解决脱贫人口就业问题"]
[24,"巩固三保障成果","教育","享受“雨露计划”职业教育补助","沅江市","沅江市","就学补助","新建","沅江市","2023-01-01","2023-12-01","乡村振兴局","就学补助",134.595314,134.595314,0,0,0,147,710,2130,28,710,2130,"脱贫家庭就读中高职学生解决部分学费及生活费，做到应补尽补","减少脱贫户和监测对象家庭子女接受职业教育的支出。"]
[25,"就业项目","公益性岗位","公益性岗位","沅江市","沅江市","公益性岗位","新建","沅江市","2023-01-01","2023-12-01","乡村振兴局","公益性岗位",36,36,0,0,0,95,150,180,28,150,180,"解决就业困难人群的就业问题，力争公益性岗位达到150个","促进了农村就业稳定，还减轻了农民的生活负担，提高了农民的生活水平"]
[25,"合计",{"$nulls":11},{"$f":"SUM(N9:N33)","v":3003.823217},{"$f":"SUM(O9:O33)","v":3003.823217},{"$f":"SUM(P9:P33)","v":0},{"$f":"SUM(Q9:Q33)","v":0},{"$f":"SUM(R9:R33)","v":0}]